## CY14 Q1 CIF Releases
Health? | Based in VistA? | Count? | In FY14 BL? | 1 Release Provided? | FY14 EPS | EPS Project Name | CIF Compliance | Version | Build | Primary Custodial Product | PM | Deliverable | 1st Contact | Running Clock | 1st Reminder | 14 Day Clock | 2nd Reminder | 21 Day Clock | 3rd Reminder | 28 Day Clock | 35 Days | 42 Days | Docs Received | Docs Complete? | Build received | Build Complete? | What We Got | Date Back to PM | 7 Day Clock | 14 Day Clock | 21 Day Clock | Redaction Start | Percent Complete | Target Release Date | Doc Posted in TJ | Build Posted in TJ | Tech Journal URL | Revised Tech Journal URL | Notes | Action On
Y | Y | Y |  |  | 01-02-03-05-01-005 | CPRS |  | 29 |  | CPRS | [26 empty] | http://hdl.handle.net/10909/21
Y | Y |  |  |  |  | SQWM |  | SR*3*179 v3.0 |  | Surgery | [26 empty] | http://hdl.handle.net/10909/39
Y | Y | Y | N |  |  | Vista Challenge Project, Kernal Patch XU*8*345 VistA Auto Patch Utility (VAPU) |  | XU*8*345 |  | Kernel | [26 empty] | http://hdl.handle.net/10909/52
Y | N |  | N |  |  | Health Management Platform Pre-Release Build |  | V1P34 |  | Health Management Platform | [26 empty] | http://hdl.handle.net/10909/53
Y | Y |  |  |  |  | CPRS |  | V29T21 |  | CPRS | [14 empty] | 2013-03-06 | [11 empty] | http://hdl.handle.net/10909/66
Y | N |  | N |  | Sustainment | Health Management Platform (HMP) |  | 1 |  | Health Management Platform | Marcia Pickard | [13 empty] | 2013-03-13 | [11 empty] | http://hdl.handle.net/10909/53
Y | N |  | N |  |  | VA Homeless Point in Time iOS App |  |  |  | Homeless Veterans | [26 empty] | http://hdl.handle.net/10909/61
Y | N |  | N |  |  | VA Point of Service Kiosk |  | 1*2 |  | Kiosk | [14 empty] | 2013-03-19 | [11 empty] | http://hdl.handle.net/10909/71
Y | N |  | N |  |  | VA Point of Service Kiosk |  | 1*3 |  | Kiosk | [14 empty] | 2013-03-19 | [11 empty] | http://hdl.handle.net/10909/73
Y | N |  | N |  |  | Nationwide Health Information Network C32 Adapter |  | 5 |  | NHIN | [14 empty] | 2013-04-18 | [11 empty] | http://hdl.handle.net/10909/77
Y | Y | Y | N |  |  | Mental Health Assessment Tool |  | Incr4 |  | Mental Health | [14 empty] | 2013-05-02 | [11 empty] | http://hdl.handle.net/10909/81
Y | Y | Y | N |  |  | RPC Broker Security Patch |  | XWB*1.1*50 |  | RPC Broker | [14 empty] | 2013-05-14 | [11 empty] | http://hdl.handle.net/10909/82
Y | Y | Y |  |  | 01-02-03-05-03-002 | SQWM |  | 1 |  | Surgery | [14 empty] | 2013-06-19 | [11 empty] | http://hdl.handle.net/10909/39
Y | Y | Y | N |  |  | Portland C3 Surgery Scheduler/Manager |  |  |  | Surgery | [14 empty] | 2013-07-17 | [11 empty] | http://hdl.handle.net/10909/88
Y | Y | Y | N |  | 01-02-03-05-03-004 | EDIS |  | 2 |  | EDIS | Jim Plastow |  | 2013-08-13 | [11 empty] | 2013-07-15 | [11 empty] | http://hdl.handle.net/10909/89 |  | Project Closed 10/24/13
Y | Y | Y | N |  | 01-02-04-04-02-001 | Lab Data Sharing and Interoperability (LDSI) |  | LA*5.2*74, LR*5.2*35, LR*5.2*427, LA*5.2*80 |  | Laboratory | [14 empty] | 2013-07-16 | [11 empty] | http://hdl.handle.net/10909/90 |  | Project Closed 10/29/13
Y | Y |  | N |  |  | M2M Broker |  | XWB*1.1*62 |  | RPC Broker | James Campbell | [13 empty] | 2013-09-11 | [11 empty] | N/A |  | Provided to Matt McCall outside of TJ
Y | N |  |  |  | 01-02-08-03-02-002 | Medical Domain Web Services (MDWS) |  | 2.8 |  | VIA | Joe McDowell | [13 empty] | 2013-10-01 | [11 empty] | http://hdl.handle.net/10909/92
Y | Y | Y | Y | Y | 01-03-03-04-05-001 | Vista Service Assembler (VSA) - Phase I | Compliant | 1 |  | VSA | Mary Anthony | Project Charter, BRD | 2013-08-15 | 4737 |  | 2013-08-29 |  | 2013-09-05 |  | 2013-09-12 |  |  | 2013-08-22 |  |  |  | Docs | [7 empty] | 2013-10-24 |  | http://hdl.handle.net/10909/95 |  | PM contacted us about CIF.
Y |  |  |  |  | 01-02-08-03-04-002 | Administrative Data Repository (ADR) |  | 3.3 | 3.3x | ADR | Michael Dore |  | 2013-08-13 | [11 empty] | 2013-08-29 | [6 empty] | 2013-10-24 |  |  |  |  | http://hdl.handle.net/10909/96
Y | Y |  | N |  | 01-02-03-02-10-003 | Behavioral Health Lab Software |  |  |  | Laboratory | Robert Longo/John Tirrell |  | 2013-07-23 | [11 empty] | N/A | [6 empty] | N/A | [6 empty] | Project in Closed state 10/3/13. COTS product.
Y | N |  | N |  | 01-02-08-01-02-001 | Enterprise Mobile Applications |  |  |  |  | Paul Mancini |  | 2013-07-23 | [11 empty] | 2013-08-20 | [6 empty] | N/A | [6 empty] | Note - determined on 8/20 not a CIF candidate at this time.
Y | Y | Y | N |  | 01-02-03-05-03-003 | Bed Management Solution (BMS) Version 1 |  |  |  | BMS | Victor Mercado |  | 2013-07-23 | [11 empty] | N/A | [6 empty] | N/A | [6 empty] | Project is in Production.
Y |  |  | N |  |  | Veterans Implant Tracking and Alert System (VITAS) |  |  |  |  | Warren Beck |  | 2013-07-23 | [18 empty] | N/A | [6 empty] | Dashboard status as of 7/26 is Closed-Stopped
Y |  |  | N |  | 01-02-03-05-03-008 | (Sustainment of) National Utilization Management Integration (NUMI) |  |  |  | NUMI | Jill Coleman |  | 2013-07-23 | [11 empty] | N/A | [6 empty] | N/A | [6 empty] | Project is Closed/in Production
Y | Y |  | N |  | Sustainment | Laboratory System Re-Engineering Project |  |  |  | LSRP | Nick Strong |  | 2013-07-23 | [11 empty] | N/A | [6 empty] | N/A | [6 empty] | Project is Closed as of 9/26/13.
Y | Y |  | N |  | 01-02-03-03-01-013 | 21st Century Medical Scheduling Contest |  |  |  | Scheduling | Dan Reed |  | 2013-07-23 | [11 empty] | N/A | [6 empty] | N/A | [6 empty] | Per Julie on 10/22/13, remove this from the list unless we get a FOIA release.
Y | Y | Y | N |  |  | Purchase Care - VistA Fee Authorization Menus Enhancements |  |  |  | Fee Basis | Ray Vogel |  | 2013-07-23 | [18 empty] | N/A | [6 empty] | Dashboard shows Closed - Stopped on 7/26/13.
|  |  | N |  | 01-02-04-04-01-001 | Warrior Support Federal Case Management Tool (FCMT) |  |  |  | VLER | Kristi Grabenstein |  | 2013-07-23
Y | Y | Y | Y |  | 01-02-03-02-10-006 | High Risk Mental Health Patient - National Reminder and Flag | Delinquent |  |  | Mental Health | Al Ebert |  | 2014-01-07 | 4592 |  | 2014-01-21 |  | 2014-01-28 |  | 2014-02-04 | [18 empty] | Looking for CIF for Incr 7, Iteration 2
Y | Y | Y | Y | Y | 01-02-03-02-10-001 | Mental Health Enhancements - Outcome Monitoring | Compliant | 11 | Patch 105, YS_501_105V8.KID | Mental Health | O Robert Longo | Checklist, Source Code, Test Cases, Test Scripts | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-09-23 | Y | 2013-09-23 | Y | Both code and docs | [12 empty] | CIF
Y | Y | Y | Y |  | 01-02-03-02-10-002 | Distribution of Mental Health Clinical Reminders | Delinquent |  |  | Mental Health | Frank Sager |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20
Y | N |  | Y | Y | 01-02-08-01-01-001 | My Recovery Plan (MRP) | Compliant | MHV 12.6 | 47 | My HealtheVet | Julius Allen | RSD, VDD, SDD Test Cases | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-09-09 | Y | 2013-09-09 | Y | Both code and docs | 2013-12-03 |  |  |  | 2013-11-07 |  | 2014-02-28 | [5 empty] | Dev
Y | N |  | Y |  | 01-02-03-02-10-004 | Enhancements to the Veterans Crisis Line Software Application | Delinquent |  |  | Mental Health | Frank Sager | Checklist | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  |  | N |  |  |  | 2013-12-03 | [11 empty] | Dev
Y | Y | Y | Y | Y | 01-02-03-02-10-005 | Patient Record Flags for Suicide Risk and Missing Patients | Compliant | 3 | DG_53_P869_TV03.KID and TIU_1_P279_TV03.KID | Mental Health | Al Ebert | Checklist, RSD, SDD, Source Code, Test Cases, Test Scripts | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-09-23 | Y | 2013-09-23 | Y | Both code and docs | [12 empty] | CIF
Y | N |  | Y |  | 01-02-08-01-01-002 | MHV Veteran-Facing Enhancements | Compliant |  |  | My HealtheVet | John Brekke |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | M1 apprvl for Active 11/8/13
Y | N |  | N |  |  | My HealtheVet - Secure Messaging |  |  |  | My HealtheVet | Greg Kirk |  | 2013-07-23 | [11 empty] | N/A | [13 empty] | PM included in MRP release; Project is Closed
Y |  |  | N |  |  | Patient Education Management System (PEMS) |  |  |  | My HealtheVet | Greg Kirk |  | 2013-07-23 | [11 empty] | 2013-09-09
Y | N |  | Y | Y | 01-02-08-01-01-005 | My HealtheVet Capabilities Enhancement | Compliant | MHV 12.6 | 47 | My HealtheVet | Kevin Hope |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-09-12 | Y | 2013-09-12 | Y | Both code and docs | 2013-12-03 |  |  |  | 2013-11-07 |  | 2014-02-28 |  |  |  |  | Project Closed 10/30/13 | Dev
Y | N |  | Y | Y | 01-02-08-01-01-006 | My HealtheVet and eBenefits Portal Integration | Compliant | MHV 12.6 | 47 | My HealtheVet | John Brekke |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-09-09 | Y | 2013-09-09 | Y | Both code and docs | 2013-12-03 |  |  |  | 2013-11-07 |  | 2014-02-28 |  |  |  |  | PM included in MRP release; project Closed 10/30/13. | Dev
Y | N |  | N |  |  | MHV Website Redesign |  |  |  | My HealtheVet | Richard Beaudoin |  | 2013-07-23
Y | N |  | Y |  | 01-02-08-01-01-003 | MHV Infrastructure and Interface Enhancements | Compliant |  |  | My HealtheVet | Greg Kirk |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | M1 apprvl for Active 11/8/13
Y | N |  | Y | Y | 01-02-03-05-02-001 | Health Mgmt Platform - Extended Version | Compliant | 1 |  | Health Management Platform | Deborah Migliore | Checklist | 2014-01-07 | 4592 |  | 2014-01-21 |  | 2014-01-28 |  | 2014-02-04 |  |  | 2013-09-10 | Y | 2013-09-12 | Y |  | 2013-10-24 | [5 empty] | 2014-01-31 |  |  |  |  | Went back 10/29 and 12/4/13 also | Dev
Y | Y |  | Y | Y | 01-02-03-05-01-004 | CPRS | Delinquent | 30 |  | CPRS | Kenny Condie |  | 2014-01-07 | 4592 |  | 2014-01-21 |  | 2014-01-28 |  | 2014-02-04
Y | Y |  | Y |  | 01-02-03-05-01-001 | CPRS | Delinquent | 31 |  | CPRS | Kenny Condie |  | 2014-01-07 | 4592 |  | 2014-01-21 |  | 2014-01-28 |  | 2014-02-04
Y | Y | Y | Y |  | 01-02-03-05-01-003 | CPRS Notification Abnormal Test Results | Compliant | CPRS 31 |  | CPRS | Kenny Condie | Email conversation only | 2013-07-23 | 4760 | 2013-12-17 | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [7 empty] | 2013-10-25 | [5 empty] | 2014-01-31 |  |  |  |  | As of 8/1/13, CD ready - project team awaiting place to send it. 10/25/13 - still waiting on code/checklist. Paused - planning | Dev
Y | N |  | N |  | Sustainment | Breast Cancer Clinical Case Registry |  |  |  | Registries | Thomas Venne, Don Michalak | Email conversation only | 2013-07-23 | [25 empty] | As of 8/1/13, CD ready - project team awaiting place to send it. Stream in RTC created as BCCR.
Y | Y | Y | Y |  | 01-02-03-05-03-010 | Notification of Teratogenic Drugs | Compliant | CPRS 31 |  | Pharmacy | Thomas Venne, Don Michalak | Email conversation only | 2013-07-23 | 4760 | 2013-12-17 | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [7 empty] | 2013-10-25 | [5 empty] | 2014-02-28 |  |  |  |  | As of 8/1/13, CD ready - project team awaiting place to send it. 10/25/13 - still waiting on code/checklist. Paused - planning | Dev
|  |  | N |  |  | Patient-Centered Non-Institutional Long Term Care (LTC) |  |  |  |  | James Reich |  | 2013-07-23
[6 empty] | Breast Cancer Clinical Case Registry |  | CPRS 31 | [25 empty] | 2014-02-28
Y | N |  | Y | Y | 01-02-08-01-02-002 | Mobile Development | Compliant | Move Coach Mobile | Move Coach Mobile |  | Enrique Gomez |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-08-02 | Y | 2013-08-02 | N | Both code and docs | 2013-08-22 |  |  |  | 2013-08-21 |  | 2014-03-31 |  |  |  |  | Move Coach Mobile was received. We have questions about copyrighted material. Action on dev team to respond. | Dev
Y | N |  | N |  | 01-02-08-01-02-004 | Mobile Health External Development (MHED) |  |  |  | C3 to C1 process | Paul Mancini | Checklist | 2013-07-23 | [11 empty] | 2013-10-22 | [13 empty] | Not a CIF candidate. The MHED project is basically a process to ensure that externally developed mobile applications complete the PMAS process.
Y | Y |  | Y | Y | 01-02-03-05-03-009 | Veterans Transportation Service (VTS) | Compliant | DG5*3*853* | 7 | VTS | Rich LeBlanc | RSD, SDD, VDD, Source Code, Test Cases | 2014-01-07 | 4592 |  | 2014-01-21 |  | 2014-01-28 |  | 2014-02-04 |  |  | 2013-10-22 | Y | 2013-10-22 | Y | Both code and docs | [12 empty] | CIF
Y | Y |  | Y | Y | 01-02-05-03-01-007 | eCMS Interface to IFCAP Phase 2 | Compliant | PRC*5.1*174 | 23 | IFCAP | Robert Miller | RSD, SDD, VDD, Source Code, Test Scripts, Test Cases | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-09-18 | Y | 2013-09-18 | Y | Both code and docs |  |  |  |  | 2013-12-05 |  |  | 2013-12-05 | 2013-12-05 | http://hdl.handle.net/10909/101
Y | N |  | N |  | 01-02-03-02-11-001 | (Sustainment of) The Genomic Informatics System for Integrative Science (GenISIS) |  |  |  | GenISIS | Gary Pickwoad |  | 2013-07-23 | [25 empty] | 9/25/13 - M3/M4 approval for closure.
Y | N |  | Y |  | 01-02-03-02-11-002 | GenISIS Data Integration | Delinquent |  |  | GenISIS | Gary Pickwoad |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [7 empty] | 2013-12-17
Y | N |  | Y |  | 01-02-03-02-11-003 | Veterans Informatics and Computing Infrastructure Consortium for Health Informatics Research (VINCI CHIR) | Delinquent |  |  | VINCI | Mark Cheshire |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20
Y | Y |  | N |  | 01-02-03-03-11-002 | (Sustainment of) Non-VA Care - Claims Processing |  |  |  | Fee Basis | Christan Govich |  | 2013-07-23 | [25 empty] | In national release (10/22/13).
Y | Y | Y | Y | Y | 01-02-03-03-11-001 | Non-VA Care Claims Processing Enhancements | Compliant |  |  | Fee Basis | Christan Govich | RSD, SDD | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-12-12 | N |  |  | Docs | [12 empty] | CIF
Y | N |  | N |  |  | ICD-10 HAPE PMO Support |  |  |  | DRG Grouper | Larry Weldon |  | 2013-07-23 | [25 empty] | Is this even a CIF candidate? Not in TSPR or Dashboard
Y | Y |  | Y | Y | 01-02-03-05-04-001 | Safety Updates for Medication Prescription Management | Compliant | PSS*1*172, PSJ*5*289 | PSS*1*174 v7 and PSJ*5*289 v2 | Pharmacy | Roberto Santos | RSD, VDD, SDD, Source Code, Test Cases | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-10-25 | Y | 2013-10-25 | Y | Both code and docs | [11 empty] | Previously Pharmacy Legacy Enhancements | CIF
Y | Y | Y | Y | Y | 01-02-03-05-04-002 | Bar Code Medication Administration (BCMA) - SFG IRA | Compliant | Incr 8 | PSJ*5*279,PSB*3*70,PSS*1*172,OR*3*266,PSB*3*73 | BCMA | Roberto Santos | RSD, VDD, Source Code | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-10-25 | Y | 2013-10-25 | Y | Both code and docs | [12 empty] | CIF
Y | Y | Y | Y | Y | 01-02-03-05-04-003 | Bar Code Expansion (BCE) Positive Patient Identification | Compliant | 1 | MJCF*1.0 TIU*1.0*281 | BCMA | Katie Thomas | RSD, VDD, SDD, Source Code, Test Cases | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-10-23 | Y | 2013-10-23 | Y | Both code and docs | [12 empty] | CIF
Y | N |  | N |  | 01-02-03-05-04-004 | VA Medication Reconciliation |  |  |  | Pharmacy | Roberto Santos |  | 2013-07-23 | [25 empty] | New Start state. PM reports no funding for FY4.
Y | Y | Y | Y | Y | 01-02-03-06-03-001 | Pharmacy Enterprise Customization System (PECS) | Compliant | 3 | 347 | PRE/PECS | Sophia Myles | VDD, Source Code | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-08-14 | Y | 2013-08-14 | Y | Both code and docs | 2013-11-06 |  |  |  | 2013-11-06 |  | 2014-02-28 | [5 empty] | Dev
Y | Y |  | Y |  | 01-02-03-06-03-001 | Pharmacy Enterprise Customization System (PECS) | Compliant | 4 | 56 | PRE/PECS | Sophia Myles | RSD, VDD, SDD, Source Code, Test Cases | 2014-01-07 | 4592 |  | 2014-01-21 |  | 2014-01-28 |  | 2014-02-04 |  |  | 2013-10-01 | Y | 2013-10-01 | Y | Both code and docs | 2013-11-06 |  |  |  | 2013-11-06 |  | 2014-02-28 |  |  |  |  | Never released. | Dev
Y | Y |  | Y |  | 01-02-03-06-03-001 | Pharmacy Enterprise Customization System (PECS) | Compliant | 5 |  | PRE/PECS | Sophia Myles | RSD, SDD, VDD, Source Code | 2014-01-07 | 4592 |  | 2014-01-21 |  | 2014-01-28 |  | 2014-02-04 |  |  | 2013-12-19 | Y | 2013-12-19 | Y | Both code and docs | [12 empty] | CIF
Y | Y | Y | Y | Y | 01-02-03-06-03-003 | Medication Order Check Healthcare Application (MOCHA) | Compliant | 2 | 9 | PRE/MOCHA | Dianne McCance | SDD, Source Code, Test Cases | 2014-01-07 | 4592 |  | 2014-01-21 |  | 2014-01-28 |  | 2014-02-04 |  |  | 2013-09-03 | Y | 2013-09-03 | Y | Both code and docs | 2013-11-07 |  |  |  | 2013-11-07 |  | 2014-02-28 | [5 empty] | Dev
Y | Y | Y | Y | Y | 01-02-03-06-03-002 | Pharmacy Re-Engineering - PRE Pharmacy Product System National (PPS-N) | Compliant | 1.1 | 1 | PRE/PPS-N | Ryan VanVickle | RSD, SDD, Source Code | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-08-08 | Y | 2013-08-08 | Y | Both code and docs | 2013-11-04 |  |  |  | 2013-11-04 |  | 2014-02-28 |  |  |  |  | Docs received 8/8/13 for PPS | Dev
Y | Y | Y | Y | Y |  | Pharmacy Re-Engineering - PRE Pharmacy Data Update (DATUP) | Compliant | 2 |  | PRE/DATUP | Ryan VanVickle | Source Code | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  |  |  | 2013-09-09 | Y | Code | 2013-11-06 |  |  |  | 2013-11-06 |  | 2014-02-28 | [5 empty] | Dev
Y | Y | Y | Y | Y | 01-02-03-03-01-007 | Compensation and Pension Record Interchange (CAPRI) Tactical Enhancements | Compliant | P186 | 186 | CAPRI | Ricky Stephens | Source Code, Docs | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-10-22 | Y | 2013-10-22 | Y | Both code and docs | [12 empty] | CIF
Y | Y |  | Y | Y | 01-02-03-03-01-017 | Disability Exam and Assessment Program (DEAP) | Compliant | Incr1 |  | CAPRI | Ricky Stephens | Source Code, Docs | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-10-22 | Y | 2013-10-22 | Y | Both code and docs | [12 empty] | CIF
Y | Y | Y | Y |  | 01-02-03-03-12-001 | ICD-10 Changes for Lexicon, Encounter Forms, and Clinical Reminders | Delinquent |  |  | DRG Grouper | Curtis Clay |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20
Y | Y | Y | Y | Y | 01-02-03-03-12-002 | ICD-10 Conversion of Class 1 Clinical Remaining Products | Compliant | 2013-10-01 | 2013-10-01 | DRG Grouper | Elizabeth Feszczenko | RSD, VDD, SDD, Test Cases | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-10-25 | Y |  |  | Docs | 2013-11-01 | [5 empty] | 2014-01-31 |  |  |  |  | 16 applications included. Awaiting executable from Ron Massey | Dev
Y | Y | Y | Y | Y | 01-02-03-03-12-003 | ICD-10 Changes for Class 1 Financial Products | Compliant | 1 | 1 | DRG Grouper | Richard Holmes | Checklists, RSD, SDD, Source Code | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-12-03 | Y | 2013-12-03 | Y | Both code and docs | [11 empty] | 5 products included | CIF
Y | Y |  | Y | N | 01-02-03-03-12-004 | ICD-10 Class 3 Field Level Assessment | Delinquent |  |  | DRG Grouper | Robert Cleveland |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | Project not a CIF candidate.
Y | Y |  | Y | Y | 01-02-03-03-12-005 | ICD-10 Remediation of the Cache System | Compliant | v6 | ICD10_3_0_1.KIDS | DRG Grouper | Richard Holmes | RSD, SDD, Source Code | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-12-16 | Y | 2013-12-16 | Y | Both code and docs | [12 empty] | CIF
Y | Y | Y | N |  |  | Reasonable Charges Billing Enhancements - Annual Updates |  | 1 | IB*2*458 | Fee Basis | Kimberly Nix | RSD, SDD, Test Cases | 2013-07-23 | [11 empty] | 2013-10-24 | [13 empty] | Project closed 10/22/13. Doc submission only.
Y | Y |  | Y |  | 01-02-03-03-12-006 | ICD-10 Patient Treatment File Modifications | REMOVE |  |  | DRG Grouper | Glen Caneel |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27 | [18 empty] | In 14.0.0.1 EPS. New 12/3/13
Y | Y | Y | Y | Y | 01-02-03-03-03-046 | VA DoD VistA Fee - IPAC Interface Enhancement | Compliant | 1 | FB*3.5*123 | Fee Basis | James Bly | RSD | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-10-02 | N |  |  | Docs | [12 empty] | CIF
Y | Y | Y | Y |  | 01-02-03-03-03-047 | VistA Fee Separation of Duties | Delinquent |  |  | Fee Basis | Stephanie Simms |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | Planning state 11/5/13
Y | Y | Y | Y |  | 01-02-03-03-03-048 | Prosthetics Inventory Package Enhancements | Delinquent |  |  | Prosthetics | David McLeod |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | Project in Planning state as of 10/22/13. PM will provide CIF as it's developed.
Y | Y | Y | Y |  | 01-02-08-02-02-006 | Enrollment Legislative Changes | Delinquent |  |  | Kiosk | Dan Soraoka |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | Project closed 11/26/13
Y | Y | Y | Y | Y | 01-02-03-03-06-001 | Caregivers - Newborn Claims Processing Enhancement | Compliant | 1 | v9 | Registration, Enrollment | Donna Ellis | RSD, SDD, VDD, Source Code, Test Cases, updated docs | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 |  |  | 2013-10-24 | Y | 2013-10-24 | Y | Both code and docs | [12 empty] | CIF
Y | Y | Y | N |  | 01-02-03-03-06-002 | Caregivers - Title 1, Sections 101-104 |  |  |  | Enrollment | Loren Behuniak | [27 empty] | Dashboard shows Paused
Y | Y |  | N |  |  | RISE - National Insurance File (NIF) |  | 1 |  | EDI Electronic Data Interchange | Jean Sheppard | Source Code, Test Cases | 2013-07-23 | [11 empty] | 2013-09-25 | [13 empty] | PM contacted us on 9/11. Project closed 10/1/13.
Y | Y |  | N |  | 01-02-03-03-08-001 | Eligibility Transaction Compliance |  |  |  |  | Ray Vogel |  | 2013-07-23 | [25 empty] | Project closed
Y | Y |  | Y | N | 01-02-03-03-08-002 | Claims Status Transaction Compliance | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | M3 approval 1/8/14
Y | Y |  | Y | N | 01-02-03-03-08-003 | EDI Front End Compliance | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | M3 approval 1/8/14
Y | Y | Y | Y | N | 01-02-03-03-08-004 | Fee Basis Claims Compliance | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | M3 approval 1/8/14
Y | Y | Y | Y |  | 01-02-03-03-08-005 | Purchase Care System Enhancements | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | Planning state
Y | Y | Y | Y | N | 01-02-03-03-08-006 | Vendor Files Enhancements | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | M3 approval 1/8/14
Y | Y | Y | N |  | 01-02-03-03-08-007 | EDI Pharmacy System Enhancements |  |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | [25 empty] | Closed - Stopped
Y | N |  | Y |  | 01-02-03-03-08-008 | HAC EDI Claims Systems Enhancements | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20
Y | Y |  | N |  | 01-02-03-03-08-009 | Electronic Funds Transfer (EFT) Compliance |  |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | [25 empty] | Closed - Stopped
Y | Y |  | Y |  | 01-02-03-03-08-010 | Electronic Remittance Advice (ERA) Compliance | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | Planning state
Y | Y |  | Y |  | 01-02-03-03-08-011 | Health Plan Identifier (HPID) Compliance | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | Planning state
Y | Y |  | Y |  | 01-02-03-03-08-012 | Claims Attachments Compliance | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | Planning state
Y | Y |  | Y |  | 01-02-03-03-09-001 | eInsurance Eligibility Inquiry Compliance | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20
Y | Y |  | Y |  | 01-02-03-03-09-002 | eInsurance Eligibility Response Compliance | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20
Y | Y |  | Y |  | 01-02-03-03-09-003 | ePharmacy Claims Compliance | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20
Y | Y |  | Y |  | 01-02-03-03-09-004 | eBilling Claims Compliance | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | Provisioning state
Y | Y |  | Y |  | 01-02-03-03-09-005 | eClaims Billing Provider Compliance | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | Provisioning state
Y | Y |  | Y |  | 01-02-03-03-09-006 | eInsurance System Modifications | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20
Y | Y |  | Y |  | 01-02-03-03-09-007 | Medical ePayments Compliance | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | Provisioning state
Y | Y |  | Y |  | 01-02-03-03-09-008 | ePayments ePharmacy Compliance | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | Provisioning state
Y |  |  | Y |  | 01-02-03-03-09-010 | Version Control System (VCS) Implementation | Delinquent |  |  | EDI Electronic Data Interchange | Ray Vogel |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20 | [18 empty] | Provisioning state
Y | Y | Y | Y |  | 01-02-08-03-02-001 | VistA Integration Adapter (VIA) | Delinquent |  |  | VIA | Joe McDowell |  | 2013-07-23 | 4760 |  | 2013-08-06 |  | 2013-08-13 |  | 2013-08-20
Y | N |  | Y |  | 01-02-08-03-03-001 | IAM Identity Services (IdS) | Delinquent |  |  | IAM | Jeff Podolec |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10
Y | N |  | N |  |  | IAM Authentication Services |  |  |  |  | Robert Schmidt |  | 2013-08-13 | [25 empty] | M3 approval received 9/18/13, M4 received 10/24
Y | N |  | N |  |  | IAM Authorization Services |  |  |  |  | Robert Schmidt |  | 2013-08-13 | [25 empty] | M3 approval received 9/18/13, M4 received 10/24
Y | N |  | Y |  | 01-02-08-03-03-002 | IAM Access Services (AcS) | Delinquent |  |  | IAM | Robert Schmidt |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10 | [18 empty] | Active 11/13/13. RSD, SDD to be completed by 12/15/13.
Y | N |  | N |  | 01-02-08-03-03-003 | Sustainment of IAM Identity Services (IdS) |  |  |  |  | Jeff Podolec |  | 2013-08-13
Y | Y | Y | Y |  | 01-02-08-02-02-004 | Camp Lejeune-Veterans | Delinquent |  |  | Enrollment | Annie Omotosho |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10
Y | Y | Y | Y |  | 01-02-03-05-03-001 | Primary Care Management Module (PCMM) Rehost_Reengineering | Delinquent |  |  | PCMM | Aaron Lindstrom |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10
Y | N |  | Y | Y | 01-02-08-01-01-004 | Health Risk Assessment (HRA) | Compliant | 1 | 47 | My HealtheVet | James Reich | RSD, SDD, VDD, Source Code, Test Cases | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10 |  |  | 2013-10-22 | Y | 2013-11-04 | Y | Both code and docs | [11 empty] | Included in MHV release from 9/12/13, V1 docs received 10/22/13 and code received 10/31 and 11/4 | CIF
Y | N |  | N |  |  | eMOVE! Web-based Self Management Care for Weight Management |  |  |  |  | John Brekke |  | 2013-08-13
Y |  |  | N |  |  | Veterans Health Library CPRS Integration |  |  |  |  | John Brekke |  | 2013-08-13
Y |  |  | N |  |  | Sustainment of Multiple Sclerosis Home Automated Telemanagement (MS HAT) |  |  |  |  | Don Michalak |  | 2013-08-13
Y |  |  | Y |  | 01-02-03-02-12-005 | Home TeleHealth (HT) Capabilities Enhancements | Delinquent |  |  | Telehealth | Ellen Hans |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10
Y |  |  | N |  | 01-02-03-02-12-001 | Telemedicine (Store and Forward Telepathology Teleaudiology) |  |  |  | Telehealth | Larry Carlson |  | 2013-08-13 | [25 empty] | PM reports project is complete
Y | Y | Y | Y |  | 01-02-03-02-12-002 | VistA Imaging Core DICOM Services Phase I | Delinquent |  |  | Imaging | Larry Carlson |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10
Y | Y |  | Y |  | 01-02-03-02-12-003 | VistA Imaging Storage Management Enhancements Phase 1 | Delinquent |  |  | Imaging | Larry Carlson |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10
Y | N |  | Y |  | 01-02-03-02-12-006 | Clincial Video Teleconferencing (CVT) | Delinquent |  |  | Telehealth | Harpreet Sodhi |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10 | [18 empty] | Only COTS code in use so far.
Y | Y | Y | Y |  | 01-02-03-02-12-004 | Document and Ancillary Imaging | Delinquent |  |  | Imaging | Larry Carlson |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10
Y | Y |  | Y |  | 01-02-03-02-12-007 | VistA Imaging Storage Infrastructure | Delinquent |  |  | Imaging | Larry Carlson |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10
|  |  | N |  | 01-02-05-04-03-003 | Child Care Records Management System |  |  |  |  | Portia Vertreese |  | 2013-08-13 | [25 empty] | M3/M4 approval received 9/25/13
|  |  | N |  |  | Sustainment of Point of Care Research (POC-R) |  |  |  |  | Gary Pickwoad |  | 2013-08-13
N | N |  | N |  | Sustainment | Portfolio Classification and Reporting Tools (PCRT) |  |  |  |  | John Tirrell |  | 2013-08-13
N | N |  | Y |  | 01-02-03-03-10-001 | Real Time Location System (RTLS) Enterprise Systems Engineering (ESE) | Delinquent |  |  | HCE (Health Care Efficiency) Facilities Automation | Steve Waldman |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10 | [18 empty] | PM responded 11/20/13. Provisioning state
N | N |  | Y |  | 01-02-03-03-10-002 | Real Time Location System (RTLS) National Data Repository (NDR) | Delinquent |  |  | HCE (Health Care Efficiency) Facilities Automation | Steve Waldman |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10 | [18 empty] | Planning state. PM responded 11/20/13
Y |  |  | Y |  | 01-02-08-03-04-001 | Health Data Repository (HDR) II | Delinquent |  |  | HDR | James Plastow |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10
Y | N |  | N |  | 01-02-03-06-02-001 | Sustainment of STS - VA Enterprise Technology Services (VETS) |  |  |  | VETS | Paul Long |  | 2013-08-13
Y | N |  | Y |  | 01-02-08-03-01-001 | Clinical Case Registry (CCR) | Delinquent |  |  | Registries | John Sanders |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10
Y | N |  | Y |  | 01-02-08-03-01-002 | Oncology Tumor Registry (ONC) | REMOVE |  |  | Registries | John Sanders |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27
Y | N |  | N |  | 01-02-08-03-01-003 | Embedded Fragment Registry |  |  |  | Registries | Kathleen Kern | [27 empty] | Dashboard shows Paused - Unfunded
Y | N |  | N |  | 01-02-08-03-01-004 | Military Eye Vision Injury Registry |  |  |  | Registries | Kathleen Kern | [27 empty] | Dashboard shows Paused - Unfunded
Y | N |  | Y |  | 01-02-08-03-01-006 | Traumatic Brain Injury Registry (TBI) | REMOVE |  |  | Registries | John Sanders |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27
Y | N |  | N |  | 01-02-08-03-01-007 | Sustainment of Converged Registries |  |  |  | Registries | Kathleen Kern |  | 2013-08-13
Y | N |  | N |  | 01-02-08-03-01-008 | Sustainment of Oncology Tumor Registry |  |  |  | Registries | John Sanders |  | 2013-08-13
Y | N |  | N |  | 01-02-08-03-01-009 | Sustainment of Embedded Fragment Registry |  |  |  | Registries | Katrina Tuisamatatele |  | 2013-08-13
Y | N |  | N |  | 01-02-08-03-01-010 | Sustainment of Military Eye Vision Injury Registry |  |  |  | Registries | Katrina Tuisamatatele |  | 2013-08-13
Y | N |  | N |  | 01-02-08-03-01-011 | Sustainment of Breast Cancer Clinical Case Registry |  |  |  | Registries | Katrina Tuisamatatele |  | 2013-08-13
Y | N |  | Y |  | 01-02-08-03-01-012 | Open Burn Pit Registry | Delinquent |  |  | Registries | Richard Karbarz |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10
Y | N |  | Y |  | 01-02-08-03-01-013 | Multiple Sclerosis Surveillance Registry | Delinquent |  |  | Registries | Frankie Rios |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10
Y | N |  | N |  |  | James A Lovell Federal Health Care Center (JAL-FHCC) - Financial Management |  |  |  | JAL | Steve Gribschaw |  | 2013-08-13
Y | N |  | Y |  | 01-02-08-03-05-001 | SPS Scope Action Plan (ISO-9001) - PRISM iQMS | Delinquent |  |  | SPS (Sterile Processing Service) | Rick Wikberg |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10 | [18 empty] | Dashboard shows Paused - Planning
Y | N |  | Y |  | 01-02-08-03-05-002 | SPS Scope Action Plan (ISO-9001) - Identify Reusable Medical Equipment (IRME) | Delinquent |  |  | SPS (Sterile Processing Service) | Rick Wikberg |  | 2013-08-13 | 4739 |  | 2013-08-27 |  | 2013-09-03 |  | 2013-09-10 | [18 empty] | Provisioning
|  |  | N |  | 01-04-01-01-01-001 | Sustainment of STS - ICD-10 Lexicon Work Transition |  |  |  |  | Jean Walker |  | 2013-08-13
|  |  | N |  | 01-04-01-01-01-002 | VistA Maintenance |  |  |  | VistA | Gerry Lowe |  | 2013-08-13
|  |  | N |  | 01-04-01-01-01-003 | Enterprise Application Maintenance (HeV maintenance) |  |  |  | My HealtheVet | Vanessa Davis |  | 2013-08-13
N | N |  | N |  |  | Sustainment of Business Ware (BW) Migration v4.3 (VIE) |  |  |  | VIE | Daniel Territo |  | 2013-08-13
|  |  | N |  |  | Miami MedRecon |  |  |  | Pharmacy | Robert Silverman | Source Code, Overview Docs | 2013-10-24 | [11 empty] | 2013-09-23 | [13 empty] | PM contacted us at OSEHRA Summit
Y | N |  | Y |  | 01-02-08-02-02-001 | Enrollment System Enhancements | REMOVE |  |  | Kiosk | William Wigton |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27 | [18 empty] | Provisioning state
Y | N |  | Y |  | 01-02-08-02-02-002 | Enrollment Customer Enhancements | REMOVE |  |  | Kiosk | Louise Rodebush |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27 | [18 empty] | Provisioning state
Y | N |  | Y |  | 01-02-08-02-02-005 | Healthcare Reform/Affordable Care Act | REMOVE |  |  | Kiosk | Mark Shaughnessy |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27
Y | Y |  | Y |  | 01-02-03-03-08-018 | Healthcare Claims 837 Compliance - Phase 2, Iteration 1 | REMOVE |  |  | EDI Electronic Data Interchange | Ray Vogel |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27 | [18 empty] | Planning state
Y | Y |  | Y |  | 01-02-03-03-09-011 | Eligibility Benefits, & Claim Status Data Content & Infrastructure (Phase 2, Iteration 2) | REMOVE |  |  | EDI Electronic Data Interchange | Ray Vogel |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27 | [18 empty] | Planning state
Y | Y |  | Y |  | 01-02-03-03-09-012 | Insurance Verification Processor (IVP) (Phase 1, Iteration 1) | REMOVE |  |  | EDI Electronic Data Interchange | Ray Vogel |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27 | [18 empty] | Planning state
Y | Y |  | Y |  | 01-02-03-03-09-013 | Medical ePayments Compliance (Phase 2, Iteration 2) | REMOVE |  |  | EDI Electronic Data Interchange | Ray Vogel |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27 | [18 empty] | Planning state
Y | Y |  | Y |  | 01-02-03-03-09-015 | NCPDP Continuous Maintenance Standards (Phase 2, Iteration 2) | REMOVE |  |  | EDI Electronic Data Interchange | Ray Vogel |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27 | [18 empty] | Planning state
Y | Y |  | Y |  | 01-02-03-03-09-016 | Uniform Use of CARC/RARC (835) Rule (Phase 2, Iteration 2) | REMOVE |  |  | EDI Electronic Data Interchange | Ray Vogel |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27 | [18 empty] | Planning state
Y | N |  | Y |  | 01-02-03-02-11-005 | Research Administrative Management System (RAMS) | REMOVE |  |  |  | Glenda Miller |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27 | [18 empty] | Paused-Planning
Y | Y |  | Y |  | 01-02-03-03-03-049 | Cross Servicing | REMOVE |  |  | Fee Basis | Chris Minardi |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27 | [18 empty] | NewStart state
Y | Y |  | N |  | 01-02-03-05-04-006 | Bar Code Medication Administration (BCMA) and Inpatient Medication |  |  |  | BCMA | Roberto Santos | [27 empty] | 12/3/13 No longer in EPS 14.0.0.1
Y | N |  | Y |  | 01-02-03-05-04-007 | Replacement System for RAI/MDS (Resident Assessment Instrument/Minimum Data Set) | REMOVE |  |  |  | Patricia Medeiros |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27
Y | N |  | Y |  | 01-02-08-02-01-001 | VHA Point Service (Kiosks) Phase II | REMOVE |  |  | Kiosk | Kathy L MacDonald |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27 | [18 empty] | Planning as of 11/1/13
Y | N |  | Y |  | 01-02-08-02-01-002 | VHA Point Service (Kiosks) | REMOVE |  |  | Kiosk | Kathy L MacDonald |  |  | 46238 |  | 1900-01-13 |  | 1900-01-20 |  | 1900-01-27
N | N |  | Y | Y | 01-02-05-03-01-008 | SCIP Automation Tool (SAT) - Construction Capital | Compliant |  |  | Captial Asset Management | Rashida Franklin | Docs, Code | 2013-12-05 | 4625 |  | 2013-12-19 |  | 2013-12-26 |  | 2014-01-02 |  |  | 2013-12-06 | Y | 2013-12-06 | Y | Both code and docs | [11 empty] | PM solicited us | CIF
Y | Y |  | N | Y |  | Miami MedRecon | REMOVE | 2013-09-01 | 2013-09-01 | Pharmacy | Robert Silverman |  |  | 46238 | [8 empty] | 2013-09-23 | Y | 2013-09-23 | Y | Both code and docs | 2013-10-24 | [5 empty] | 2014-01-31
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238
46238