Clinical Information Support System

Patient-Centered Management Module

ReHost/ReEngineering

Deployment Plan

Version 2.0

August 2014

Office of Information and Technology

Enterprise Systems Engineering

Project Management Office

Revision History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| August 2014 | 2.0 | Updated Draft for New Contract and Production Deployment. Technical edit. | Shawnta Davis / Kate Hula |
| Janaury 2013 | 1.9 | Technical edit | Brian Lynch |
| January 2013 | 1.8 | Technical Review | Noel Morrison |
| November 2012 | 1.7 | Content added to address production at test sites | Connor Barry, Noel Morrision, Slava Uchitel |
| November,2012 | 1.6 | Technical edit | Brian Lynch |
| August 2012 | 1.5 | Removed “DRAFT” watermark | Dan Dunn |
| July 2012 | 1.4 | Added text to document | Noel Morrison |
| July 2012 | 1.3 | Added text to document | Brian Lynch, Dan Dunn |
| July 2012 | 1.2 | Updated with IMS and site information | Dan Dunn |
| July 2012 | 1.1 | Updated per reviewer’s comments | Brian Lynch, Dan Dunn |
| June 2012 | 1.0 | Added text to section 4.1.4 | Jan Joubert |

Table of Contents

1.	Introduction	1

1.1	Purpose	1

1.2	Key Definitions	1

1.3	Plan Overview	2

1.4	Assumptions	2

2.	Roles and Responsibilities	3

3.	Schedule	4

3.1	Timeline	4

3.2	Master Deployment Schedule	4

3.3	Schedule Activities	4

4.	Site Readiness Assessment	5

4.1	Special Operational Requirements	5

4.2	Deployment Topology	5

4.3	Site Information (Locations/Deployment Recipients/Etc.)	5

4.4	Site Preparation	5

4.5	Assessment of Deployment Readiness Checklist	5

5.	Deployment Sequence	6

5.1	Pre-Deployment	6

5.2	Deployment (Initial / Pilot Sites)	7

5.3	Post Deployment (Add Additional Sites)	8

6.	Resources	8

6.1	Facility Specifics	9

6.2	Hardware - ESE	9

6.3	Software – ESE	9

7.	Training and Documentation	9

7.1	Training (Optional)	9

7.2	Documentation - ESE	10

7.3	Communications - ESE	10

8.	Appendix A:  Deployment Process	11

9.	Appendix B:  Reference Documents	12

9.1	Attachment A – Approval Signatures	13

# Introduction

This document describes the plan to deploy and install the Patient-Centered Management Module Re-host/ReEngineering (PCMMR) Java Web Application, as managed through the PCMMR project.

NOTE: The scope of this plan is limited to the deployment of the PCMMR to the four test sites identified by the VA customer.

## Purpose

The purpose of this plan is to provide a single common document that describes how, when, where, and to whom the PCMMR web application will be deployed and installed. Appropriate communications planning should also be completed, as well as the training plan and rollout schedule.

## Key Definitions

Systems Development Life Cycle (SDLC) - The overall process of developing, implementing, and retiring information systems through a multistep process from concept definition, concept development, system design and prototype, system development and testing, system deployment, and system operation and disposal.

The SDLC is a collaborative process across many disciplines and VA organizational entities including the Office of Enterprise Systems Engineering (ESE), Field Operations (FO), National Data Center Program (NDCP), Austin Information Technology Center (AITC), Product Development, Office of Information Protection and Risk Management (IPRM) and Field Security Operations, Veterans Health Administration (VHA), Veterans Benefits Administration (VBA), and National Cemetery Administration (NCA).

Deployment Design – Starting phase of the overall solution lifecycle where architectural design and implementation specifications are developed and tested.  The preparation of plans and specifications necessary to implement the solution are part of the deployment design stage.  Developed solutions are implementation-ready for the production environment at the end of the deployment design stage.

ESE and Product Development (as applicable based on primary project ownership) are responsible for deployment design and complete release package specifications, including user and technical documentation, procurement, shipping and training plans.  Architectural design artifacts, release package specifics and testing plans and results are vetted with FO and NDCP.

Implementation – Installation and activation of newly designed or changed hardware, software, process, etc. into the production environment. During the implementation phase of the solution life cycle you work from specifications and plans created during deployment design for rolling out the solution into the production environment.

FO, NDCP, and/or AITC are responsible for installation and the installation schedule, selection and validation of shipping locations/schedule, site readiness to support installation, acceptance of equipment using Asset Inventory processes, coordination and actual training working with ESE and Product Development (if applicable), communication and vetting changes through the field and FO management.

Release -ESE is responsible for Release Management, including certification of production readiness.  ESE must validate that the project owner has provided an adequate release package.  ESE also validates the release baseline.   The ‘release package’ is the subset of documents, as defined by the OIT Testing and Release Checklist, that are provided to the field along with the product. The complete Release Package  will be made available to FO at deployment  The ‘release baseline’ is defined as the product build (software and hardware specifications) along with the body of documents that support testing, install, operations, training and support of the product. Projects will determine early in the development cycle the project’s ‘release baseline’. The ‘release baseline’ components enter change control once the project is approved for deployment.

## Plan Overview

The initial deployment and installation of the PCMMR web application is planned as an online rollout to users over a two month period per the Integrated Master Schedule.

The deployment to four initial production sites will be a joint activity between the PCMM team and the VA customer. The installation will be performed by PCMMR team members.

## Assumptions

It is assumed that prior to deployment and installation ESE, FO, NDCP and/or AITC know what is coming to deployment and are aware of testing issues, design, etc. FO will assess and assure site readiness..

This process is based upon projects that are required to go through the Systems Engineering and Design Review (SEDR) process.  FO, NDCP and AITC are notified of upcoming deployments early in the project lifecycle, as indicated in the ESE project management process documentation. ESE is responsible for deployment. ESE PMs manage the deployment phase; FO PMs and Implementation Managers and NDCP and AITC representatives participate as team members.

FO, NDCP and AITC are responsible for installation and during this phase projects are led by the PMs from those entities; ESE representatives participate as team members. ESE is responsible for design.  FO, NDCP and AITC are informed of design and testing issues, and participate in the Systems Engineering and Design Review (SEDR) process. ESE, FO, NDCP and AITC collaborate on the development of the Deployment-Installation Plan. Topology determinations are made by ESE and vetted with FO, NDCP, and AITC. Site readiness is verified through FO (adequate lead time is provided). FO, NDCP and AITC are involved from the beginning of the project planning within ESE.

New requirements that require Operations and Maintenance (OM) resources must be funded.  Deployment, installation and ongoing maintenance costs (including capacity planning, recurring costs) costs must be identified and funded.  All funding sources and issues should be resolved and documented prior to deployment and installation. Product Development or ESE (depending upon project ownership) should complete collaborative field testing prior to deployment.

ESE Release Management will certify production readiness based upon the level of testing that has occurred prior to deployment.  As part of the release baseline, this information would be identified in the Release Profile.

Product Development or ESE (depending upon project ownership) should provide a training plan prior to deployment.

# Roles and Responsibilities

This section describes the teams who perform the steps described in this Plan.

Deployment and installation activities are performed by representatives from the teams listed in the following table.  This phase begins after the solution design (including deployment topology) is complete.  Design activities are not included in this phase:

| ID | Team | Phase / Role | Tasks | Phase (See “Schedule”) |
| --- | --- | --- | --- | --- |
|  | FO | Deployment | Fully communicate ratified deployment topology |  |
|  | FO or Product Development (depending upon project ownership) | Deployment | Deployment planning and scheduling (including orchestration with vendors) |  |
|  | FO | Deployment | Develop Communications Plan and key messages well in advance |  |
|  | FO or Product Development (depending upon project ownership) | Deployment | Develop Operations and Maintenance (OM) Plan |  |
|  | FO or Product Development (depending upon project ownership) | Deployment | Develop appropriate training materials |  |
|  | FO | Deployment | Ensure release package contains full complement of artifacts and authorizations required for deployment |  |
|  | FO | Deployment | Operational readiness testing |  |
|  | FO | Deployment | Release certification |  |
|  | FO | Deployment | Validate release baseline |  |
|  | FO | Deployment | Execute deployment |  |
|  | FO / NDCP / AITC | Installation | Installation planning and scheduling |  |
|  | Regional PM/FIS/OPP PM | Installation | Collaborate on Field Operations communication plan that touches various field operations stakeholders and execute the communications plan. |  |
|  | Regional PM/FIS/OPP PM | Installation | Ensure authority to operate. Ensure CA / Security Documentation is in place. |  |
|  | Regional PM/FIS/OPP PM | Installation | Ensuring collection of current drawings and kept as part of project documentation and forwarded to ESE/Change control process owners. |  |
|  | Facility POCs/CTOs/Regional PM/FIS/OPP PM | Installation | Facilities will install equipment as scheduled. |  |
|  | Facility POCs/CTOs/Regional PM/FIS/OPP PM Property Manager at each site/ | Installation | Disposition – disposing of software/equipment |  |
|  | Facility POCs/CTOs/Regional PM/FIS/OPP PM/Facility Manager | Installation | Site Readiness – Checklist of Power, HVAC, Space for each facility |  |
|  | Regional PM/FIS/OPP PM/ | Installation | Validate thru Facility POC to ensure IT equipment has been accepted using Asset Inventory processes |  |
|  | Regional PM/FIS/OPP PM/National Education and Training | Installations | Coordinate training |  |

# Schedule

The deployment is planned as an online rollout.  The rollout should be scheduled on a site by site basis to facilitate data migration, data reconciliation and certification on a controlled timeline.

This section provides the schedule and milestones for the deployment.  ESE provides the overall timeline parameters as agreed with the vendor and FO, NDCP and/or AITC.  For field installation, FO provides the site-specific scheduled within those parameters. The PCMMR is a web-based application.

## Timeline

See section 5.0 – Deployment Sequence.

## Master Deployment Schedule

ESE maintains master schedule in MS Project Server; FO maintains schedule in Clarity.  FO provides site scheduling to meet parameters and milestones enumerated above.

## Schedule Activities

See the PCMMR Integrated Master Schedule for scheduled activities.

# Site Readiness Assessment

This section discusses the locations that will receive the PCMMR deployment.  Topology determinations are made by ESE and vetted with FO, NDCP and AITC during the design phase as appropriate.  Field site coordination is done by FO unless otherwise stipulated by FO.

## Special Operational Requirements

Execution of Data Migration Plan – patches, preinstallation requirements.

## Deployment Topology

TBD

## Site Information (Locations/Deployment Recipients/Etc.)

Initial Operating Capacity Deployment is planned at the following sites: The four sites below are the PCMMR Pilot Sites.

- CRDC (Falling Waters)/CRRC (Martinsburg) Primary Datacenter – PCMM Web App

- Hines, IL Datacenter (Disaster Recovery site) – PCMM Web App

- Portland, OR – VistA + patches

- Memphis, TN– VistA + patches

- Iron Mountain, MI– VistA + patches

- Los Angeles, CA– VistA + patches

National deployment is planned after successful deployment and implementation at the four pilot sites.

## Site Preparation

The following table describes preparation required by the site prior to deployment:

| Site/Other | Problem/Change Needed | Features to Adapt/Modify to New Product | Actions/Steps | Owner |
| --- | --- | --- | --- | --- |
| Production DB | PCMM Schema | Add tables, users | Add | Jan Joubert |
| Production DB | Data Migration | VistA Site Data from CDW | Migrate | Jan Joubert / Aditya Badhwar |
| Production Weblogic Domain | Creation of New Weblogic Domain | New JVM’s & VistaLink connectors | Add | Noel Morrison |
| VistA patches | Install | Apply VistA patches | Add | IRM representatives at each VistA site (POCs on PCMM) |

## Assessment of Deployment Readiness Checklist

Refer to Operations Implementation Plan.

# Deployment Sequence

The following table lists the sequence of steps that must occur for proper deployment of PCMMR during the release cycle.  Some steps may be executed in order in parallel (unless annotated as such).  The timeline indicates the recommended earliest start date and the recommended latest start date. “T” is defined as the cutover date when PCMMR is activated for a site, legacy PCMM Delphi application is disabled, and production users begin to exclusively use PCMMR.

Note: When executing these steps, update this document by the status column to indicate when a task has been completed for a site.

## Pre-Deployment

Pre-deployment is the phase when data is migrated (from CDW) for a site and initial data comparisons and cleanup are performed by members at the site. Contingent on IOC test site approvals, additional testing is performed by requesting a data backup into the mirror (test) systems for these sites, for the purpose of validating the three new PCMMR Vista patches, Vista synchronization functionality and extra Vista-level raw data comparisons.

| Starts on | Title | Details | Owner | Status |
| --- | --- | --- | --- | --- |
| T-120 days | Run ETL Scripts | Run data migration from CDW into PCMMR DM environment | ETL specialist |  |
| T-120 days | Request Production account mirror refresh | The production mirror account is set up with copy of production data | PCMMR Project Team |  |
| T-60 days | Request VistA access to Prod Mirror account | Obtain Access and Verify codes for the local site test Vista | PCMMR Project Team |  |
| T-45 days | Install VistA Patches into Prod Mirror | Install VistA Patches in test account - Execute Report Templates - Perform initial automated data comparisons using stored procedure | PCMMR Project Team and Site IT POC |  |
| T-45 days | Configure VistaLink to point to Prod Mirror account | Pre-Prod testing of Vista Synchronization, auto-inactivation, notifications. | Dev Team |  |
| T-45 days | Perform iterative remediation testing and data reconciliation | - Execute data reconciliation reports and team validation (PCMMR-driven) reports for analysis by PCMMR and site teams - Identify bad data and request SMEs complete data cleanup in legacy PCMM production account - Repeat steps 1 & 2 to certify data is as expected in PCMMR | SME |  |
| T-7 days | Obtain site sign-off on Data in new PCMMR | Site agrees in writing that the data migration is successful and data integrity is as expected. | SME |  |

## Deployment (Initial / Pilot Sites)

Deployment occurs after data validations and cleanup have been finished for a site. Any remaining validation problems or data discrepancies which are unresolvable (or acceptable by the site) will be documented. PCMMR will then be activated for a site, legacy PCMM Delphi application security keys will be revoked (blocking access to the legacy application), and production users begin to exclusively use PCMMR. For the initial / pilot sites, code and PCMMR enterprise database changes are still acceptable during the IOC phase if bugs are discovered.

| Timeline | Title | Details | Owner | Status |
| --- | --- | --- | --- | --- |
| T-7 days | Assure Site Readiness | - Site has signed off on data migration - Site POC has been notified of pending deployment | Project Team & Implementation Team |  |
| T-0 days | Install VistA patches | - Run routine to back up VistA globals - Install VistA patches according to their patch descriptions | Project Team or Site IT Staff |  |
| T-0 days | Register Patients with MVI | - Register Patients with MVI according to Installation Guide | Project Team or Site IT Staff |  |
| T-0 days | Start / enable Vista Sync process | - Enable VistA-sync process according to Installation Guide | Product Support |  |
| T-0 days | Remove access to Legacy Application | - Run VistA Post Routines to turn off legacy PCMM according to VistA patch description | Site IT Staff |  |
| T-0 days | Grant user access to PCMMR | - Set up users in user management in PCMMR web | Product Support |  |
| T-0 days | Reconcile Teams with models | - Generate CSV list of team IDs via DB query - Execute MBean which reconciles multiple teams with applicable models | PCMMR Project Team |  |
| T-0 days | Set site transition date and alert CDW | - Update PCMMR DB table with date & time of data migration for site being migrated - Alert CDW to disable Vista feed as of the above date and enable feed for site from the PCMMR DB | PCMMR Project Team / CDW support |  |
| Initial Deployment only | Deploy the web application | - Deploy PCMMR to the web server - Perform Smoke Test - Approve deployment | PCMMR Project Team |  |
| T-0 days | Finalize installation | - Announce availability of the Web Application for users at migrated site | PCMMR Project Team |  |

## Post Deployment (Add Additional Sites)

| Timeline | Title | Details | Owner | Status |
| --- | --- | --- | --- | --- |
| T-7 days | Assure Site Readiness | - Site has signed off on data migration - Site POCs have been notified of pending deployment schedule | Project Team & Implementation Team |  |
| T-0 days | Install VistA patches | - Install VistA patches according to patch descriptions | Project Team or Site IT Staff |  |
| T-0 days | Register Patients with MVI | - Register Patients with MVI according to Installation Guide | Project Team or Site IT Staff |  |
| T-0 days | Enable Vista Sync process | - Enables VistA sync process according to Installation Guide | Project Team or Site IT Staff |  |
| T-0 days | Turn- off Legacy Application | - Run VistA post routines which turn off legacy PCMM access according to VistA patch description | Product Support |  |
| T- 0 days | Grant user access to PCMMR | - Set up users in user management in PCMMR web. | Product Support |  |

# Resources

This section describes hardware, software, facilities, and documentation required for the deployment and installation.

Hardware / Software / Systems Post-Deployment Support

System Support Roles and Responsibilities are defined in the Project Operation and Maintenance (POM) Plan.

## Facility Specifics

The following table lists facility-specific features required for deployment:

| Site | Space/Room | Features Needed | Other |
| --- | --- | --- | --- |
| CRDC/CRRC | n/a – Using existing CISS Hardware & Virtual Machines | n/a |  |
| Hines, IL | n/a – Using existing CISS Hardware & Virtual Machines | n/a |  |

## Hardware - ESE

The following table describes hardware specifications required at each site prior to deployment.

| Required Hardware | Model | Version | Configuration | Manufacturer | Other |
| --- | --- | --- | --- | --- | --- |
| n/a – Using existing CISS Hardware | D380 | G5 | n/a | HP | n/a |
| Migrated to Virtualized Servers | - | - | - | - | - |

Please see the Roles and Responsibilities section above for details about who is responsible for preparing the site to meet these hardware specifications.

## Software – ESE

The following table describes software specifications required at each site prior to deployment.

| Required Software | Make | Version | Configuration | Manufacturer | Other |
| --- | --- | --- | --- | --- | --- |
| SQLServer | - | 2012 | - | Microsoft | - |
| Weblogic | - | 10.3.6 | - | Oracle | - |
| Java JDK | - | 1.7 Build 60 | - | Oracle | - |

Please see the Roles and Responsibilities section above for details about who is responsible for preparing the site to meet these software specifications.

# Training and Documentation

Refer to Training Implementation Plan.

## Training (Optional)

The following training is provided with deployment:

- WebHelp files

- PCMMR User Guide

- PCMMR Training Plan

## Documentation - ESE

Each Project establishes a ‘release baseline’ at project inception. These are the documents that enter into change control at deployment. A subset of these documents accompanies the product release to the Field. This is referred to as the ‘release package’. The Master Go No Go Checklist defines the Release Baseline for each Project. The Master Go No Go Testing & Release Checklist can be found at http://DNS  eie.DNS   /lifecycle/default.aspx.

The following documents support installation and administration of the product:

- Appendix A, Summary of End-to-End Deployment Process

- PCMMR User Guide

## Communications - ESE

Not applicable.

# Appendix A:  Deployment Process

Summary of End-to-End Deployment Process

- Web application is deployed only once after approval for national deployment is received.

  - Content Management (CM) manager pulls approved code from repository, builds EAR, WebHelp ZIP, and SQL script files for deployment (artifacts).

  - Systems Administrator (SA) stops any applicable applications [CISS/PCMM], notifies deployment team of status, and stages appropriate artifact files on the server.

  - SA deploys WebHelp ZIP files to an appropriate location and stands by for the team’s readiness to continue to next steps.

  - Database Administrator (DBA) retrieves SQL script files and stages them on a database (DB) server.  The DBA applies any DB updates to the appropriate databases via SQL scripts.

  - Once the DBA and SA have communicated completion of their respective tasks, the SA will start all affected applications, monitoring progress and any LOG files deemed necssary.

  - Once all applications are running, the SA and DBA will check all respective systems for any problems, notifying deployment team of status, and resolving any issues that arise.

- Project testers are notified that the application is available for a smoke test.

- Project testers verify that the application is performing as expected.

- SA and DBA watch respective systems for any problems during testing.

- If the application passes all Smoke Test criteria, application is deemed ready.

- Deploy application to Disaster Recovery (DR) environment.

- Project owner is notified.

- Users are notified that they can access the new PCMMR web application.

# Appendix B:  Reference Documents

The following list of documents can be found on the PCMMR SharePoint site (http://DNS  DNS       .DNS   /projects/pact/pcmm_reengineering/default.aspx).

- Integrated Master Schedule

- Training Plan

- Project Operation and Maintenance (OM) Plan

- Technical Implementation Plan

## Attachment A – Approval Signatures

This section is used to document the approval of the Patient-Centered Management Module ReHost/ReEngineering Deployment Plan during the Formal Review. The review should be ideally conducted face to face where signatures can be obtained ‘live’ during the review however the following forms of approval are acceptable:

- Digital signatures tied cryptographically to the signer (instructions for digital signature can be found in the Digital Signature Guide in ProPath http://DNS  oed.wss.DNS   /process/Library/digital_signature_guide.doc)

- Physical signatures obtained face to face or via fax

- /es/ in the signature block provided that a separate digitally signed e-mail indicating the signer’s approval is provided and kept with the document

The Chair of the governing Integrated Project Team (IPT), Business Sponsor, Information Technology (IT) Program Manager, and the Project Manager are required to sign. Please annotate signature blocks accordingly.