## Sched B CLINs
CLIN Nbr | Deliverable Description | Due Date /Frequency | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-01-01 | 2014-02-01
0001 | Project Management In Accordance With (IAW) Performance Work Statement (PWS) Paragraph 5.1 of the Task Order (TO) and all of its subparagraphs. This Firm-Fixed Price (FFP) Contract Line Item Number (CLIN) includes all labor, materials, project management and deliverables required for the successful completion of the services detailed in PWS Paragraph 5.1, inclusive of all subparagraphs. Period of Performance (POP) shall be August 8, 2014 through February 7, 2015. | Monthly | x | x
0001AA | Contractor Project Management Plan IAW PWS Paragraph 5.1.1. Due September 8, 2014 and updated monthly thereafter. Electronic submission to: VA Project Manager (PM), Contracting Officers Representative (COR), Contracting Officer (CO) | Monthly | x | x
0001AB | Contractor’s Progress, Status, and Management (CPSM) Report IAW TO PWS paragraph 4.4 and T4 PWS Paragraph 8.1.1. Monthly Progress, Status and Management Report shall be provided IAW TO PWS paragraphs 4.4 and Basic T4 Contract Section C, Performance Work Statement, Paragraph 8.1.1(A-E) and Section J Attachment 005. Due within fifteen (15) days after the completion of each calendar month throughout the POP. | Monthly | x | x
0001AC | Government Furnished Equipment Status Report IAW T4 PWS Paragraph 8.1.3. Government Furnished Equipment Status Report shall be provided in accordance with Basic T4 Contract Section C, PWS, Paragraph 8.1.3 (A-J) and Section J, Attachment 008. Due within fifteen (15) days after the completion of each calendar month throughout the POP. Electronic submission to: VA PM, COR, CO | Monthly | x | x
0001AD | Personnel Contractor Manpower Report IAW T4 PWS Paragraph 8.1.4. Personnel Contractor Manpower Report shall be provided in accordance with Basic T4 Contract Section C, PWS, Paragraph 8.1.4 (A-I) and Section J, Attachments 009 and 010. Due within fifteen (15) days after the completion of each calendar month throughout the POP. | Monthly | x | x
0001AE | Small Business Participation Report. Small Business Participation Report shall be provided in accordance with Basic T4 Contract Section H, clause H-2 Small Business Participation Requirements, and Section J, Attachment 011. Due Quarterly 10/15 (for the period ending 9/30), 1/15 (12/31 end), 4/15 (3/31 end) and 7/15 (6/30 end). | Quarterly | x | x
0002 | Collaborative Development Methodology IAW PWS Paragraph 5.2. This FFP CLIN includes all labor, materials, project management and deliverables required for the successful completion of the services detailed in PWS Paragraph 5.2. Period of Performance (POP) shall be August 8, 2014 through February 7, 2015. | Monthly | x | x
0002AA | Collaborative Deliverable Package IAW PWS Paragraph 5.2. Due Seven (7) days after each 30 day sprint cycle throughout the POP. | Monthly | x | x
0002AB | Internal VA Configuration File IAW PWS Paragraph 5.2. Due Seven (7) days after each 30 day sprint cycle throughout the POP. Electronic submission to: VA PM, COR, CO | Monthly | x | x
0003 | Grassroots Innovation Functional Requirements IAW PWS Paragraph 5.3, inclusive of all subparagraphs. This FFP CLIN includes all labor, materials, project management and deliverables required for the successful completion of the services detailed in PWS paragraph 5. 3, inclusive of all subparagraphs. Period of Performance (POP) shall be August 8, 2014 through February 7, 2015. | Monthly | x | x
0004 | Prototype Demonstration and Correction of Deficiencies IAW PWS Paragraph 5.4. This FFP CLIN includes all labor, materials, project management and deliverables required for the successful completion of the services detailed in PWS Paragraph 5.4. Period of Performance (POP) shall be August 8, 2014 through February 7, 2015. | Monthly | x | x
0004AA | Prototype Demonstration Report IAW PWS Paragraph 5.4. Due Seven (7) days after each 30 day sprint cycle throughout the POP. Electronic submission to: VA PM, COR, CO | Monthly | na | x
0005 | Project Close-Out IAW PWS Paragraph 5.6. This FFP CLIN includes all labor, materials, project management and deliverables required for the successful completion of the services detailed in PWS Paragraph 5.6. Period of Performance (POP) shall be August 8, 2014 through February 7, 2015. | Monthly | na | na
0005AA | Summary and Production Integration/Transition Report IAW PWS Paragraph 5.6. Due Six (6) months ARO Electronic submission to: VA PM, COR, CO | 2015-02-01 | na | na
0006 | External Certification Testing Support IAW PWS Paragraph 5.5. This FFP CLIN includes all labor, materials, project management and deliverables required for the successful completion of the services detailed in PWS paragraph 5.5. If Optional Task is exercised, POP shall be February 8, 2015 through May 7, 2015. | Yes | na | na
0006AA | Updated Github Repository, Internal VA Configuration File, and Collaborative Deliverable Package IAW PWS Paragraph 5.5. Due three (3) months after Optional Task Exercised Electronic submission to: VA PM, COR, CO | 2015-05-01 | na | na

## CDP
Collaborative Development Package Component | Owner | Inc/Exc | Notes | Sprint 1 | Sprint 2 | Sprint 3
a) Screenshot of Git repository development activity | Joy | Include | Screenshot of GitHub w/Patch DG_53_903.kid files | IEMHV_Sprint 1 GitHub Screenshot.docx
b) Source Code, Test Frameworks, Application Programming Interface (API) Frameworks, Third party | James | Include | For this enhancement, source code will be in DG_53_903.kid files | DG_53_903_V1.KID
c) Dependencies including URLs | James | Exclude | The only Increase MHV dependency is a current VistA environment, which is basically owned and maintained by the VA. No relevant dependencies to include. | na | na | na
d) Tests, test scripts and test data | James | Include | Documents developer unit test results (via attachmate emulator capture tool) | IEMHV_UNIT_TEST_CAPTURE_V1.doc
e) Test configuration file | Bill | Exclude | The configuration for the ‘application’ is VistA itself. BC documented that configuration not necessary for this innovation. 10/1 | na | na | na
f) Installation Guide | James | Include | Standard instructions for vista patch installation | IEMHV_INSTALL_GUIDE_V1.doc
g) System Administration Guide | James | Exclude | This enhancement is not a standalone or distinct system requiring administration; there are no system administration functions/instructions to provide. | na | na | na
h) Technical Manual | James | Include | Standalone doc, notate as additional content for existing VistA Registration Technical Manual => Pre-registration content | IEMHV_TECHNICAL_MANUAL_V1.doc
i) Testing Manual | Bill | Include | Test scenarios w/screen shots | IEMHV_Testing_Manual_v1.1.docx
j) Developer Guide | James | Include | Necessary to guide a developer in open source community in setting up the environment to compile, test, etc… It is very important to OSHERA certification. | IEMHV_DEVELOPER_GUIDE_V1.doc
k) User Manual | Bill | Include | Standalone doc, notate as CHANGE PAGES for existing VistA Registration User Manual => Pre-registration content | IEMHV_dg_5_3_p858_reg_um Change Pages v.1.doc
l) Release Notes including a detailed description of changes since the previous release, bug fixes, known issues | James | Include | Content of patch description; leverage past release notes | IEMHV_RELEASE_NOTES_V1.doc
m) and a manifest of remaining items to complete the project | Joy | Include |  | IEMHV_PROJECT_MANIFEST_V1.doc

## Product Backlog
User Story ID | User Story Name | User Story Description | User Story Statement | Type | Notes | Sprint | Status
IEMVH_Vista_MHV_Alert | Add/Display VistA alert for MHV enrollment | Provide an alert within VistA under certain conditions, reminding the User to populate MHV enrollment fields. | As a VistA user, during pre-registration of a Patient, under certain conditions I want an alert to display to remind me to capture the Patient's MHV enrollment status. | User Feature |  | 1 | Done
IEMVH_Vista_MHV_Soc_Question | Add/Display VistA MHV enrollment socialization question | Provide a field within VistA to capture whether or not the Patient has been socialized to enrolling in MyHealtheVet. | As a VistA user, during pre-registration of a Patient, I want to capture whether the Patient's Health Care provider has talked to them about enrolling in MHV and record any negative response to the question and the reason why. I want the information to be accessible the next time the Patient goes thru pre-registration. | User Feature |  | 1 | Done
Change location of the historical actions table to display right after the MHV alert | Add/Display VistA MHV enrollment socialization question |  |  | User Feature | Add on to Sprint 1 | 1 | Done
IEMVH_Vista_MHV_Enroll_Three_Fields | Add/Display VistA MHV Enrollment questions (3) | Provide fields within VistA to capture the Patient's responses for three MHV enrollment questions. | As a VistA user, during pre-registration of a Patient, I want to capture the Patient's responses for three MHV enrollment questions and make the responses accessible the next time the Patient goes thru the pre-registration process. | User Feature |  | 2 | Done
Add additional responses to the alert section depending if there is a pending socialization action from the previous pre-registration session. | Add/Display VistA alert for MHV enrollment |  |  | User Feature | Add on to Sprint 2 | 2 | Done
Add an additional patient response to the socialization question for no computer/internet access | Add/Display VistA MHV enrollment socialization question | Add response to socialization question: “ No - I don’t have a computer / internet access” |  | User Feature | Add on to Sprint 2 | 2 | Done
Add "We are strongly encouraging..." text to the MHV socialization scripts | Add/Display VistA MHV enrollment socialization question | In the MHV socialization question user story, when a patient responds with "No – I am not interested in enrolling" change text that clerk reads to say: “We are strongly encouraging patients to enroll in My HealtheVet. With My HealtheVet you can refill prescriptions and track their delivery, view lab results, and communicate securely with your Health Care teams." |  | User Feature | Add on to Sprint 2 | 2 | Done
IEMVH_Mod_DCC | Add MHV Data Consistency Check | Add MHV related fields to the Vista Data Consistency Check module | Modify Data Consistency Check to ensure newly added MHV related fields are populated as desired. | Validation Check |  | 3 | Not Started
Add Actions filter to only display relevant actions | Add/Display VistA MHV Enrollment questions (3) | Only Filter and display relevant actions for the MHV Socialization and Enrollment questions being asked instead of displaying all 13 for each question. |  | User Feature |  | 3 | Not Started

## Sprint1
Sprint Story: Provide an alert within VistA under certain conditions, reminding the User to populate MHV enrollment fields. Story Point: |  |  |  | Sprint Start/End = 9/08/2014 – 10/3/2014 | Sprint 1 Max Capacity | Estimated Work Hrs
Task Name | Hours Est | Hours Rem | Owner | Sprint Duration = 20 days | James = 140 hrs | 160
ANA: Create first draft of Alert user story | 0.5 | 0 | Kristen K | Max Sprint Capacity = 7hrs x 20 = 140 hrs | Bill = 140 x .25 = 35 hrs | 33
ANA: Schedule first working session | 0.5 | 0 | Kristen K |  | Kristen = 140 x .50 = 70 hrs | 4
ANA: Facilitate first working session | 1 | 0 | Kristen K |  | Joy = 35 hrs
ANA: Update user story after working sessions | 2 | 0 | Kristen K
ANA: Communications; emails, etc | 2 | 0 | Kristen K
6
Test: Create Test Plan | 3 |  | B. Frey
Test: Create Sprint Story Test Scripts | 2 |  | B. Frey
Test: Execute Sprint Story Tests | 8 |  | B. Frey
Test: Retest any code fixes required | 2 |  | B. Frey
Test: Update Test Plan with test results | 1 |  | B. Frey
Test: Prepare for Demo and Perform Demo at Sprint Review | 2 |  | B. Frey
18
DEV: Research existing VistA Alert Algorithms | 24 | 0 | JH
DEV: Design MHV Vista Alert | 8 | 0 | JH
DEV: Code MHVVistA Alert Enhancement | 16 | 0 | JH
DEV: Unit Test MHVVistA Alert Enhancement | 8 | 0 | JH
56
Sprint Story: Provide a field within VistA to capture whether or not the Patient has been socialized to enrolling in MyHealtheVet. Story Point:
Task Name | Hours Est | Hours Rem | Owner
ANA: Create first draft of user story | 1.5 | 0 | Kristen K
ANA: Schedule second working session | 0.5 | 0 | Kristen K
ANA: Facilitate second working session | 1 | 0 | Kristen K
ANA: Update user stories after working sessions | 6 | 0 | Kristen K
ANA: Communications; emails, etc | 2 | 0 | Kristen K
11
Test: Create Sprint Story Test Scripts | 2 |  | B. Frey
Test: Execute Sprint Story Tests | 8 |  | B. Frey
Test: Retest any code fixes required | 2 |  | B. Frey
Test: Update Test Plan with test results | 1 |  | B. Frey
Test: Prepare for Demo and Perform Demo at Sprint Review | 2 |  | B. Frey
15
DEV: Design 'Socialization' enhancement | 40 | 0 | JH
DEV: Code 'Socialization' enhancement | 32 | 0 | JH
DEV: Unit Test 'Socialization' enhancement | 32 | 0 | JH
104

## Sprint 2
Sprint Story: Provide fields within VistA to capture the Patient's responses for three MHV enrollment questions. |  |  |  | Sprint Start/End = 10/06/2014 – 10/31/2014 | Sprint 1 Max Capacity | Estimated Work Hrs
Task Name | Hours Est | Hours Rem on 10/17 | Owner | Sprint Duration = 19 days | James = 90 hrs | 90
SQA: Create Sprint Story Test Scripts | 2 | 2 | B. Frey | Max Sprint Capacity = 8hrs x 19 = 152 hrs | Bill = 152 x .25 = 38 hrs | 34
SQA: Execute Sprint Story Tests | 8 | 8 | B. Frey
SQA: Retest any code fixes required | 2 | 2 | B. Frey
SQA: Update Test Manual with test scripts for CDP | 2 | 2 | B. Frey
SQA: Prepare for Demo and Perform Demos during sprint | 2 | 2 | B. Frey
16
DEV: Technical Research | 24 | 0 | JH
DEV: Design MHV enrollment field enhancement | 24 | 8 | JH
DEV: Code MHV enrollment field enhancement | 24 | 8 | JH
DEV: Unit Test MHV enrollment field enhancement | 16 | 10 | JH
DEV: Update technical documents for CDP | 2 | 2 | JH
90
ANA: Update user story #3 and create final draft | 8 | 4 | B. Frey
ANA: Facilitate working sessions & SME collaborations | 8 | 2 | B. Frey
ANA: Update User Manual for CDP | 2 | 2 | B. Frey
18

## Sprint 3
Sprint Story: Add MHV related fields to the Vista Data Consistency Check module. Story Point: |  |  |  | Sprint Start/End = 11/03/2014 – 11/28/2014 | Sprint 1 Max Capacity | Estimated Work Hrs
Task Name | Hours Est | Hours Rem | Owner | Sprint Duration = 19 days | James = 90 hrs | 0
SQA: Create Sprint 3 user story Test Scripts |  |  |  | Max Sprint Capacity = 8hrs x 19 = 152 hrs | Bill = 152 x .25 = 38 hrs | #REF!
SQA: Execute Sprint 3 user story Tests
SQA: Retest any code fixes required
SQA: Update Test Manual with test scripts for CDP
SQA: Prepare for Demo and Perform Demos during sprint 3
DEV: Technical Research
DEV: Design MHV consistency checker
DEV: Code MHV consistency checker
DEV: Unit Test MHV consistency checker
DEV: Update technical documents for CDP
Sprint Story: Add Actions filter to only display relevant actions
SQA: Create Test Scripts
SQA: Execute user story Tests
SQA: Retest any code fixes required
SQA: Update Test Manual with test scripts for CDP
SQA: Prepare for Demo and Perform Demos during sprint 3
DEV: Technical Research
DEV: Design
DEV: Code
DEV: Unit Test
DEV: Update technical documents for CDP