Department of Veterans Affairs

Increase Enrollment in MHV

Contractor Project Management Plan (CPMP)

November 2014

Version 1.2

Revision History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| 9/8/2014 | 1.0 | Initial Draft | Joy Forester |
| 10/5/2014 | 1.1 | Updated project schedule for Sept 2014 | Joy Forester |
| 10/28/2014 | 1.2 | Updated project schedule for Oct 2014 | Joy Forester |
| 11/25/2014 | 1.2 | No changes for Nov 2014 | Joy Forester |

Table of Contents

1.	Introduction	4

1.1.	Project Overview	4

1.2.	Scope Statements	4

1.3.	Acronyms	4

1.3.1.	Acronyms	4

2.	Project Schedule	5

3.	Project Approach	5

3.1.	Project Management Approach	5

3.1.1.	Communication Plan	6

3.2.	Technical Approach	7

3.2.1.	Design and Development	7

3.2.2.	Quality Assurance	8

3.3.	Tools	8

4.	Deliverables	9

4.1.	Project Milestones and Key Deliverables	9

5.	Risk Planning	11

6.	Resources	13

6.1.	Resource Support	13

# Introduction

The Contractor Project Management Plan (CPMP) provides the approach, expected schedule, and tools to be used in managing the deliverables of the Increase Enrollment in My HealtheVet (MHV) innovation contract from beginning to end of the 6 month contract cycle.

## Project Overview

The Increase Enrollment in MHV project was born from the Veterans Administration (VA) Innovation Program.  Through this initiative, prospective projects submitted by VA employees scrutinize for benefit, funding, and development. Selected projects move to the first of two innovation phases, a prototype lowbar phase, where the requested functionality is developed outside the VA Network in a virtual cloud environment known as the Future Technology Lab (FTL).

Currently, the MyHealtheVet (MHV) web portal is a vastly under-utilized resource by Veterans. As a result of its underutilization, patients are left with long wait times when trying to reach a VHA employee to determine their appointment time, refill their prescriptions, or talk with their doctor. All of these problems could easily be mitigated with enrollment into the MHV web portal. Veterans are not consistently asked about their desire to enroll in MHV or what their current MHV status is. The one standardized process performed by all Clerks across the VHA is the pre-registration of patients when they arrive for their appointment. To streamline the education of patients on MHV, VA requires a prompt in the VistA pre-registration screen to indicate both the Veterans' desire to participate in the MHV program as well as their current MHV status.

This performance-based Task Order, “Increase Enrollment in MHV” is issued on a Firm-Fixed-Price (FFP) basis, in accordance with the terms and conditions of Contract VA118-11-D-1014 and modifications thereto. The TAC Number associated with this task is TAC-14-15832.  All work shall be performed in accordance with the T4 Performance Work Statement, entitled “Increase Enrollment in MHV” dated August 8, 2014 as set forth in Section C. The Task Order period of performance is August 8, 2014 through February 7, 2015.

## Scope Statements

The goal of this 6 month innovation project is to use Agile development practices to design, develop, test, and deliver a fully functional prototype in the Future Technology Lab (FTL) virtual cloud environment which modifies the Pre-registration Interface (PI) in the current VistA appointment management system package to include an alert and query/response line items that record the patient’s MHV Enrollment activity.  If the patient isn’t participating in MHV enrollment, VistA will provide a list of reason codes for to document why.  If the patient is participating, a series of 3 MHV Enrollment questions will be asked and the responses stored for future display.  VistA consistency checks in Pre-registration will be updated to include the new MHV Enrollment component.  This project does not include an actual integration into VA production or test environments running on the VA network within this contract.

## Acronyms

### Acronyms

| Term | Definition |
| --- | --- |
| API | Application Programming Interface |
| FFP | Firm-Fixed-Price |
| GFE | Government Furnished Equipment |
| HPES | Hewlett Packard Enterprise Services |
| OSEHRA | Open Source Electronic Health Record Agent |
| PM | Project Manager |
| PWS | Performance Work Statement |
| SME | Subject Matter Expert |
| SQA | Software Quality Assurance |
| TAC | Technical Acquisition Center |
| VAMC | VA Medical Center |
| VistA | Veterans Health Information Systems and Technology Architecture |

# Project Schedule

HPES will develop and maintain an integrated master project schedule that depicts project tasks, Performance Work Statement (PWS) deliverables, and milestones.   Task relationships and dependencies will be indicated within the schedule along with the resource assignments.  Task granularity will be enhanced as required; however, any task additions that appear to be scope creep will be brought to VA project management attention for validation.

The schedule has been broken down into smaller increments where logical tasks and deliverables are consolidated into a sprint.  The sprints are approximately 3-4 weeks in duration.  As each sprint concludes, HPES project team members perform a retrospective review to ensure that any lessons learned, including activities that went well, are addressed in the next sprint.

The Microsoft (MS) Project schedule contains the itemized task list, estimated duration, anticipated start and finish dates, predecessors, and resource assignments.  Although the project schedule is depicted as a linear progression, the agile nature of this project allows us to flex which tasks are incorporated into a sprint.  For instance, if a developer completes the design prior to the anticipated end date, they are able to initiate development without waiting for the next sprint to begin.  The project schedule should be considered a living document and will be updated incrementally with any changes through the duration of the Increase Enrollment in MHV project.  The baseline schedule is embedded.

# Project Approach

## Project Management Approach

HPES is focused on using sound project management methodology to deliver effective proof-of-concept solution consistent with this innovation in order to advance government Healthcare capabilities.  Our project management methodology is based on industry-accepted practices from the Project Management Institute, Inc. (PMI®) Project Management Body of Knowledge (PMBOK®).   Both the HPES Program Manager and Project Manager assigned to lead the development team are both PMI Project Management Professional (PMP) certified.

The project management approach for the Increase Enrollment in MHV project will incorporate a modified Agile and iterative software development techniques geared towards rapid prototyping.  The benefits to exercising this project management approach include:

- Delivery of Reliable Results - Engaging stakeholders in frequent interactions to set clear program direction, feature priorities, and integration strategies, thereby instilling a sense of shared product ownership.

- Risk Planning and Monitoring - Practicing risk avoidance and implement mitigation strategies

- Increased Performance - Engage group accountability for results and shared responsibility for team effectiveness.

### Communication Plan

To effectively manage this contract, we’ll establish controls and monitor performance to ensure all deliverables are completed on time and per the Performance Work Statement (PWS). In order to accomplish the deliverable requirements, a solid communication plan will be established and executed.  For this contract there will be three main sources of monitoring.

- Daily Project Scrum calls between the development team members to share status and obstacles

- Weekly Sprint Meetings between VA Innovations staff and HPES development team

- Any ad-hoc calls/meetings between HP and VA stakeholders

- Formal T4 Monthly Progress Report

The weekly sprint meetings will be used as a proactive checkpoint to identify and resolve problems early on, validate the progress of the deliverables against the scheduled completion date and capture any new risks.

The monthly T4 progress report will detail the actual delivery dates, schedule, critical items, accomplishments, risks, meetings and overall performance for the VA to review. The report will be used as a formal process for maintaining control of the project by being able to oversee the progress of the work being accomplished each month.

Additional details regarding project communication practices are outlined below in Table 3.1.1: Increase Enrollment in MHV Communication Plan.

Communication Type; Objective/Information; Method; Deliverables; Frequency; Audience; Responsibility. Kickoff Meeting; Introduction of the project and team members Review project objectives and deliverables; Virtual web meeting & conference line; - Agenda - Meeting Minutes; Once; - Project Leaders - Project Team - Stakeholders; - VA Project Manager - HPES Program Manager. Weekly Sprint Review Meeting; Review project status with the stakeholders and identify development requirements; Virtual web meeting & conference line; - Agenda - Meeting Minutes; Weekly; - Project Leaders - Project Team - Stakeholders; - HPES Program Manager. Daily Standup/Scrum Calls; Internal HPES meetings to assess progress, issues, and risks for communication to project leadership and stakeholders; Virtual web meeting & conference line; - N/A; Daily; - HPES Development Team; - HPES Development Key. Innovations Sandbox Tickets; Relay issues and questions associated to the VA FTL account install, setup, and applications; Innovations Sandbox Help Requests Web Ticketing System; - Written and/or verbal notification of ticket resolutions; Ad Hoc; - VA Sandbox Web Support Team; - HPES Development Team. Contractor Project Management Plan (CPMP); Conveys HPES project management and technical approach to meet goals; Document via email; - CPMP Document; Initial version 9/8/14; monthly afterward; - VA Project Leaders - Stakeholders; - HPES Program Manager. T4 Monthly Reports; Report the status to VA Management including activities, progress, issues, and planned work; Documents via Email; - Status Report - GFE Report - Manpower Report; 15th of each month; - VA Project Leaders; - HPES Program Manager. User Stories; Formally communicates the requirements provided by the stakeholders; Documents via Email; - Requirement Documents; as needed; - Project Team - Stakeholders; - HPES Requirements Analyst. Prototype Demonstration; Displays the final product for stakeholder review, feedback, and approval; Virtual web meeting & conference line; - Prototype Demonstration Report; 7 days after each 30 day sprint cycle; - Project Leaders - Project Team - Stakeholders; - HPES Program Manager - HPES Development Team. Project Close-out Meeting; Confirms all contract deliverable requirements are satisfied; convey lessons learned; Virtual web meeting & conference line; - Agenda - Meeting Minutes; Feb 2014; - Project Leaders - Project Team Stakeholders; - HPES Program Manager. Table 3.1.1: Increase Enrollment in MHV Project Management Plan Communication Plan

## Technical Approach

### Design and Development

The Technical Approach recognizes the need to modify the Pre-registration Interface of the VistA Appointment Scheduling System package. HPES recognizes the imperative role the MHV stakeholders will play in the success of this innovation project.  We will engage the MHV stakeholders at the first weekly sprint meeting to initiate requirements solicitation and begin discussing possible design options.   Moving quickly to involve key VA personnel at the project start will help ensure that the designed solution encompasses the required functionality and reduces the probability of re-work.  The developers will share their design approach with the team through continuous conversations during the Sprint cycles.  The functional features for each development sprint will be shared with the stakeholders at the end of each development sprint cycle.

Iterative documentation of the development effort will be created and maintained in a Collaborative Development Package (CDP) that contains sufficient information for VA and open source developers to review. The CDP will include the following items, if applicable:

- Screenshot of Git repository development activity

- Any applicable Source Code, Test Frameworks, Application Programming Interface (API) Frameworks, Third party, and dependencies including URLs

- Tests, test scripts and test data

- Test configuration file

- Installation Guide

- System Administration Guide

- Technical Manual

- Testing Manual

- Developer Guide

- User Manual

- Release Notes including a detailed description of changes since the previous release, bug fixes, known issues, and a manifest of remaining items to complete the project.

At the conclusion of each agile development cycle, the Collaborative Deliverable Package will be updated in the Git repository.

### Quality Assurance

HPES confirms the enhanced software meets VA stakeholder requirements through multiple rounds of software quality assurance (SQA) testing.  Prior to code delivery, developers practice unit testing of the features they code in order to minimize the likelihood of defect prior to delivery to the SQA tester.  The test cases are written directly from the software requirements and use cases.  HPES SQA will incorporate both functional and system testing prior to the initial prototype presentation.  During subsequent sprint development following the prototype demonstration, HPES will add regression testing to confirm that all features passed during the previous testing rounds continue to remain intact.  HPES will evaluate the effort and feasibility of adding Stakeholder Prototype User Functional Testing.

## Tools

The development team will utilize a variety of tools to accomplish their work.  The VA FTL web support team ticketing system will be used to coordinate staging and troubleshooting for the virtual cloud development environments.  Within the development environment, Cache will be used to perform the M coding changes for the Pre-registration interface routines.

Project management will operate using tools such as MS Project for schedule detail.  T4 Monthly status reports and issue logs will also be a mechanism for communicating the state of the project to VA leadership and TAC.

# Deliverables

## Project Milestones and Key Deliverables

The PWS has identified the key deliverable outcomes from the Increase Enrollment in MHV Project Management Plan project in the Schedule of Deliverables Section B.2.  The table below (Table 4-1) has been included to summarize the deliverables and due dates.

CLIN Nbr; Deliverable Description; Due Date /Frequency. 0001; Project Management In Accordance With (IAW) Performance Work Statement (PWS) Paragraph 5.1 of the Task Order (TO) and all of its subparagraphs. This Firm-Fixed Price (FFP) Contract Line Item Number (CLIN) includes all labor, materials, project management and deliverables required for the successful completion of the services detailed in PWS Paragraph 5.1, inclusive of all subparagraphs. Period of Performance (POP) shall be August 8, 2014 through February 7, 2015.; Monthly. 0001AA; Contractor Project Management Plan IAW PWS Paragraph 5.1.1. Due September 8, 2014 and updated monthly thereafter. Electronic submission to: VA Project Manager (PM), Contracting Officers Representative (COR), Contracting Officer (CO); Monthly. 0001AB; Contractor’s Progress, Status, and Management (CPSM) Report IAW TO PWS paragraph 4.4 and T4 PWS Paragraph 8.1.1. Monthly Progress, Status and Management Report shall be provided IAW TO PWS paragraphs 4.4 and Basic T4 Contract Section C, Performance Work Statement, Paragraph 8.1.1(A-E) and Section J Attachment 005. Due within fifteen (15) days after the completion of each calendar month throughout the POP. Electronic submission to: VA PM, COR, CO; Monthly. 0001AC; Government Furnished Equipment Status Report IAW T4 PWS Paragraph 8.1.3. Government Furnished Equipment Status Report shall be provided in accordance with Basic T4 Contract Section C, PWS, Paragraph 8.1.3 (A-J) and Section J, Attachment 008. Due within fifteen (15) days after the completion of each calendar month throughout the POP. Electronic submission to: VA PM, COR, CO; Monthly. 0001AD; Personnel Contractor Manpower Report IAW T4 PWS Paragraph 8.1.4. Personnel Contractor Manpower Report shall be provided in accordance with Basic T4 Contract Section C, PWS, Paragraph 8.1.4 (A-I) and Section J, Attachments 009 and 010. Due within fifteen (15) days after the completion of each calendar month throughout the POP. Electronic submission to: VA PM, COR, CO; Monthly. 0001AE; Small Business Participation Report. Small Business Participation Report shall be provided in accordance with Basic T4 Contract Section H, clause H-2 Small Business Participation Requirements, and Section J, Attachment 011. Due Quarterly 10/15 (for the period ending 9/30), 1/15 (12/31 end), 4/15 (3/31 end) and 7/15 (6/30 end). Electronic submission to: CO; Quarterly. 0002; Collaborative Development Methodology IAW PWS Paragraph 5.2. This FFP CLIN includes all labor, materials, project management and deliverables required for the successful completion of the services detailed in PWS Paragraph 5.2. Period of Performance (POP) shall be August 8, 2014 through February 7, 2015.; Monthly. 0002AA; Collaborative Deliverable Package IAW PWS Paragraph 5.2. Due Seven (7) days after each 30 day sprint cycle throughout the POP. Electronic submission to: VA PM, COR, CO; Monthly. 0002AB; Internal VA Configuration File IAW PWS Paragraph 5.2. Due Seven (7) days after each 30 day sprint cycle throughout the POP. Electronic submission to: VA PM, COR, CO; Monthly. 0003; Grassroots Innovation Functional Requirements IAW PWS Paragraph 5.3, inclusive of all subparagraphs. This FFP CLIN includes all labor, materials, project management and deliverables required for the successful completion of the services detailed in PWS paragraph 5. 3, inclusive of all subparagraphs. Period of Performance (POP) shall be August 8, 2014 through February 7, 2015.; Monthly. 0004; Prototype Demonstration and Correction of Deficiencies IAW PWS Paragraph 5.4. This FFP CLIN includes all labor, materials, project management and deliverables required for the successful completion of the services detailed in PWS Paragraph 5.4. Period of Performance (POP) shall be August 8, 2014 through February 7, 2015.; Monthly. 0004AA; Prototype Demonstration Report IAW PWS Paragraph 5.4. Due Seven (7) days after each 30 day sprint cycle throughout the POP. Electronic submission to: VA PM, COR, CO; Monthly. 0005; Project Close-Out IAW PWS Paragraph 5.6. This FFP CLIN includes all labor, materials, project management and deliverables required for the successful completion of the services detailed in PWS Paragraph 5.6. Period of Performance (POP) shall be August 8, 2014 through February 7, 2015.; Monthly. 0005AA; Summary and Production Integration/Transition Report IAW PWS Paragraph 5.6. Due Six (6) months ARO Electronic submission to: VA PM, COR, CO; Feb 2015. 0006; External Certification Testing Support IAW PWS Paragraph 5.5. This FFP CLIN includes all labor, materials, project management and deliverables required for the successful completion of the services detailed in PWS paragraph 5.5. If Optional Task is exercised, POP shall be February 8, 2015 through May 7, 2015.; Yes. 0006AA; Updated Github Repository, Internal VA Configuration File, and Collaborative Deliverable Package IAW PWS Paragraph 5.5. Due three (3) months after Optional Task Exercised Electronic submission to: VA PM, COR, CO; May 2015. Table 4-1: PWS Deliverables

# Risk Planning

Due to the short duration of the Increase Enrollment in MHV Project Management Plan project, HPES team recognizes the requirement to identify, monitor, track, and proactively respond to risks that may adversely affect project schedules.   The development team has been staffed with members that are seasoned in stakeholder interaction, requirements solicitation, M/Cache programming language, and testing but specifically with current VA environment and process knowledge to minimize the time it takes acclimate to the VA culture and project tasks.

All project risks, both threats and opportunities, will be relayed to VA Project Management immediately up on discovery.  In addition, project risks will be noted during the weekly sprint calls to validate our risk assessments and mitigation strategies are sound.

The Risk Summary table 5-1, notes initial team input regarding perceived risks on the Increase Enrollment in MHV project.  The CPMP will be updated as additional risks are identified during the project life-cycle.

| Risk | Probability | Impact | Comments |
| --- | --- | --- | --- |
| Hardware/Environments/Coding |  |  |  |
| Inability to connect to virtual Future Technology Lab (FTL) servers | Low | Med | In the event of a planned or unscheduled outage or challenges with remote connectivity to the FTL, the team will continue work on deliverables where access is not required (e.g. updating documentation). Extensive down-time (>5 days) may require re-evaluation of meeting deliverable deadlines or milestone targets. |
| Delays with establishing the VA FTL environments for DEV and TEST | Low | High | In the event of delays in establishing the DEV and TEST environments in FTL for the team, it may impact delivery schedule. HP will keep in close contact with the VA PM/COR on the environment set up progress and report any obstacles. |
| Requirements |  |  |  |
| Stakeholders cannot agree on feature functionality | Low | Med | VA PM/COR will be asked to mitigate so that development can progress |
| Key stakeholder(s) unavailable for input/approval | Low | Med | VA PM/COR will be asked to mitigate so that development can progress |
| Prototype |  |  |  |
| Stakeholders disagree on a requirement or alter a previous requirement decision | Low | Med | The development impact will need to be weighed and will require VA PM/COR to deliver a final decision |
| Stakeholders add new requirements not previously discussed | Low | Med | The development impact will need to be weighed and will require VA PM/COR to deliver a final decision on the scope change. |
| Project Management |  |  |  |
| Staff changes/turn-over | Low | Med | Schedule delays possible if new team members are brought in due to project acclimation, VA/FTL access, and ramp-up on project tasks |

Table 5 -1: Risk Summary Table

# Resources

## Resource Support

The resources required to support the Increase Enrollment in MHV project on the VA business side and in the field include VA Innovations Project staff, VA pre-registration end-users, VA MHV Stakeholders, and VA PM/COR to reinforce and coordinate these efforts.

| Name | Role | Organization |
| --- | --- | --- |
| Brian Stevenson | VA PM-COR | VHA OIA Innovations |
| Connie Calhoun | MHV Coordinator |  |
| Danielle Krakora | Lead Innovator | Cleveland VAMC |
| Dr. David Douglas | Co-Chair, MHV Advisory Board | Portland VAMC |
| Dennis Simms | TO Contract Specialist | Technology Acquisition Center (TAC) |
| James Wilson | MHV Coordinator | Cincinnati VAMC |
| Janet.Colyard | T4 Procurement Coord | Technology Acquisition Center (TAC) |
| Keven LeBlanc | COO | Liberty IT Solutions |
| Larry Foote |  |  |
| Matthew Ginty | T4 Contracting Officer | Technology Acquisition Center (TAC) |
| Meghan Mccloskey | T4 Contract Specialist | Technology Acquisition Center (TAC) |
| Summer Spalliero | TO Contracting Officer | Technology Acquisition Center (TAC) |
| Terri Ruggerie | MHV Coordinator | VISN 10 Ohio |
| Vince Pacasqua | MHV Coordinator | Columbus VAMC |

HPES development team members are staffed to fulfill the need for requirements elaboration, coding and design changes to the Pre-registration Interface, validation of those changes and ultimate prototype delivery.  This team includes members skilled in Business and Functional Analysis, VistA/M development, and Software Quality Assurance (SQA) testing.  The following HPES personnel have been identified as the development team for the Increase Enrollment in MHV innovations effort:

| Name | Role | Organization |
| --- | --- | --- |
| Bill Frey | Test Engineer | HP Enterprise Services |
| James Harris | M/VistA Developer | HP Enterprise Services |
| Kristen Kriwox | Sr Business Analyst | HP Enterprise Services |

Program Managers, Project Managers, Project Leads, and Contracting Officers provide guidance to the stakeholders and team members.  Project leaders also help to mitigate project risks and evaluate opportunities.  HPES Project leaders are responsible for ensuring that all project contract deliverables and activities are executed on-time and meet the quality expectations.  The VA and HPES Project leadership assigned to the Increase Enrollment in MHV effort are:

| Name | Role | Organization |
| --- | --- | --- |
| Mathew Ginty | VA T4 Contracting Officer | TAC |
| Meghan McCloskey | VA T4 Contracting Specialist | TAC |
| Janet Colyard | VA T4 Procurement Coordinator | TAC |
| Summer Spalliero | VA Contracting Officer | TAC |
| Dennis Simms | VA Contract Specialist | TAC |
| John Walsh | T4 Quality Manager | HP Vehicle Management Center (VMC) |
| Joy Forester | HPES Program Manager | HP Enterprise Services |
| Jay Heroux | HPES Client Sales Executive | HP Enterprise Services |
| Terrie Hohimer | HPES ePMO Security Clearance Lead | HP Enterprise Services |
| Brittanie Jackson | HP ePMO Project Lead | HP Enterprise Services |
| Barry Keiser | HP Account Executive | HP Enterprise Services |
| John Walsh | HP T4 PMO | HP Enterprise Services |
| Nicole Watt | HP MHVA ePMO Delivery Assurance Mgr | HP Enterprise Services |
| Maria Meleca | HP MHVA ePMO Leader | HP Enterprise Services |
| Margaret Pfeifle | HP Contracts Manager | HP Enterprise Services |
| Geff Garnhart | HP T4 Project Director | HP Enterprise Services |
| Greening | HP Account Manager | HP Enterprise Services |