## CY15 Q3 CIF Releases
EPS Project Name | Version | Build | Target Release Date
Medical ePayments Compliance |  | BPS*1*17, IB*2*511, PRCA*4.5*298 | 2015-07-13
Medical ePayments Compliance (Phase 2, Iteration 2) | 3 | IB*2*529 and PRCA*4.5*304 | 2015-07-07
ePharmacy Claims Compliance | 1 | PRCA*4.5*298, IB*2*511, BPS*1*17 | 2015-07-13
Health Data Repository (HDR) II | 3.1 | iteration 1 | CY15 Q3
Pharmacy Re-Engineering - PRE Medication Order Check Healthcare Application (MOCHA) | 2.1 | v7 and PSS*1*178 | 2015-08-27
Memorials First Notice of Death (FNOD) Enhancements | 1 |  | 2015-08-06
Memorials Eligibility Office Automation (EOA) Capability/Manual PreNeed | 1 |  | 2015-07-08
Breast Care Registry | 2.0.203.0 |  | 2015-08-18
CAPRI Enhancements and Platform Upgrade | DVBA*2.7*190 | patch 190 | 2015-07-22
Home Telehealth Reporting Enhancements (HTRE) | 7.5.0.003.01 | iteration 2 | 2015-08-27
VistA Scheduling Enhancements | 5.3 | SD*5.3*627 | CY15 Q3
VIA Enhancements | 1 | BRD, RSD, SDD | CY15 Q3
Multiple Sclerosis Surveillance Registry | 1 | RED | 2015-08-27
ICD-10 Patient Treatment File Modifications | v12 | ICD_10_PTF_MODIFICATIONS_V12.KID | CY15 Q3
VistA Evolution Radiology Package GUI |  | BRD | CY15 Q3
Mobile Health External Development (MHED)/Mobile Kidney | 1.0.0 |  | CY15 Q3
Mobile Health External Development (MHED)/Care4Caregiver | 1.0.0 |  | CY15 Q3
Mobile Health External Development (MHED)/FitHeart | 1.0.0 |  | CY15 Q3
Mobile Health External Development (MHED)/Ask a Pharmacist | 1.0.0 |  | CY15 Q3
Mobile Health External Development (MHED)/Skin Check | v1.0 |  | 2015-08-28
VistA Immunizations Enhancements (VIMM) | 2 | PX*1*209 | 2015-08-05
VistA Immunizations Enhancements (VIMM) | 2 | PX*1*206 | 2015-08-05
VistA Immunizations Enhancements (VIMM) | 2 | PX*1*210 | 2015-08-05
Camp Lejeune - Veterans | 1 | RSD, SDDs | CY15 Q3
CPRS | v31 | OR*3*377 T7 | CY15 Q3