## CY15 Q4 CIF Planned
EPS Project Name | Version | Build | Target Release Date
Memorials First Notice of Death (FNOD) Enhancements | 2 |  | 2015-10-01
Memorials Eligibility Office Automation (EOA) Capability/Manual PreNeed | 2 |  | 2015-10-08
CAPRI Enhancements and Platform Upgrade | VistA 192v11 GUI 192.02 | patch 192 | 2015-10-08
Home Telehealth Reporting Enhancements (HTRE) | 7.5 | 7.5.0.01201 | 2015-10-15
Patient Statement Enhancement | v1 | RSD, SDD | 2015-10-02
Mobile Health External Development (MHED)/Homeless Intake | 2 |  | 2015-10-13
Mobile Health External Development (MHED)/My Mobile Desktop | 1.1.0 |  | 2015-10-13
CPRS | v30.b | OR*3*350 T70 | 2015-10-13
CPRS | v32 | OR*3.0*405, PSS*1*187, PSO*7*441 | 2015-10-13
IAM Access Services (AcS) Phase 2 | 2.6.0.x | RSD | 2015-10-01
Pharmacy Re-Engineering - PRE Medication Order Check Healthcare Application (MOCHA) | ME2 | v24 | 2015-10-06
Enterprise Health Management Platform (eHMP) | 1.3.M1 | PSI8 | 2015-10-08
Telehealth Scheduling System (TSS) Integration Enhancements | Incr 2 | RSD, SDD | 2015-10-09
Billing Precertification for Fee Care | v0.1 | IB*2.0*554, FB*3.5*163 (Docs) | 2015-10-02
Billing Interface for Fee Care | v0.1 | IB*2.0*554, FB*3.5*163 (Docs) | 2015-10-02
Fee-Revenue Enhancements | v0.1 | IB*2.0*554, FB*3.5*163 (Docs) | 2015-10-02
Fee-Revenue Service Connected Condition Decision | v0.1 | FB*3.5*163 (Docs) | 2015-10-02
Copays on Hold - Medicare/No Insurance | v0.1 | IB*2.0*554, FB*3.5*163 (Docs) | 2015-10-02
Joint Legacy Viewer (JLV) Viewer Consolidation and Get the Data Back | v1 | Docs | 2015-10-09
Inpatient Medication Administration - Transdermal | UFT | PSB*3*83 v6, PSJ*3*315 v2, PSS*1*191 v7 | 2015-10-08
Meaningful Use - New VistA Data Elements |  | RSD, SDD | 2015-10-09
Pharmacy Interface Automation – Automated Dispensing Units | v5 & v1 | PSJ*5*317 & PSS*1*193 | 2015-10-09
Memorials Enterprise Letters | v1.0 | RSD | 2015-10-13
Caregivers - Title 1 Sections 101-104 | Incr 2 | RSD v1.4 | 2015-10-09
Health Data Repository (HDR) II | 3.11 |  | CY15 Q4
VistA Intake Program (VIP) | Intake 010 NSR 20141208 Display Recently Discontinued IV Orders | PSJ*5.0*325 | CY15 Q4
VistA Intake Program (VIP) | Intake 011 NSR 20100311 CPRS Laboratory Monitoring | OR*3.0*420 | CY15 Q4
VistA Intake Program (VIP) | Intake 012 NSR 20140505 Enhance Pt Inquiry to Add Personal Effects | DG*5.3*920 | CY15 Q4
VistA Intake Program (VIP) | Intake 013 NSR 20140712 Send Mail Message when VA Drug Class field is empty | GMRA*4.0*50 | CY15 Q4
VistA Intake Program (VIP) | Intake 014 NSR 20140715 Surgical Pathology Report Enhancements for Readability | LR*5.2*464 | CY15 Q4
VistA Intake Program (VIP) | Intake 015 NSR 20140713 Increase Selection from Auto Instrument File to 999 | LA*5.2*91 | CY15 Q4
VistA Intake Program (VIP) | Intake 016 NSR 20131108 Remove ListManager Restrictions on Mnemonics | OR*3.0*422 | CY15 Q4
VistA Intake Program (VIP) | Intake 017 NSR 20140714 Set Number of Labels in File 60 for Each Facility | LR*5.2*465 | CY15 Q4
Emergency Department Integration Software (EDIS) | V3 |  | CY15 Q4
Enrollment System Enhancements/Enrollment Customer Enhancements | v4.1 | DG*5.3*865, EAS*1*107 and EAS*1*111 and DG*5.3*891, DG*5.3*871, DG*5.3*890, DG*5.3*901, DG*5.3*904, DG*5.3*906, EAS*1*113 and IVM*2*160 | 2015-10-14
Beneficiary Travel Self-Service System |  |  | CY15 Q4
Camp Lejeune - Veterans |  |  | CY15 Q4
Claims Processing and Eligibility Enhancements |  |  | CY15 Q4
Customer Gateway Services (CGS) |  |  | CY15 Q4
Digits-to-Digits (D2D) |  |  | CY15 Q4
Military Service Data Sharing (MSDS) Phase II |  |  | CY15 Q4
Disability Exam and Assessment Program (DEAP) Enhancements Phase 1 |  |  | CY15 Q4
Fixed Medication Copayment Tiers |  |  | CY15 Q4
Implant Tracking Registry |  |  | CY15 Q4
Inpatient Medication Administration - Transdermal |  |  | CY15 Q4
Patient Safety Updates - Additive and IV Strength |  |  | CY15 Q4
Interagency Comprehensive Plan (ICP) Phase 1 |  |  | CY15 Q4
Multiple Sclerosis Surveillance Registry |  |  | CY15 Q4