## Core Functionality
RAPTOR User Acceptance Test Case
| Project Name / # | RAPTOR July to Jan 2015 UAT
| Test Site: | http://raptortest.vaftl.us/Rsite500/raptor/user/login?status=notauthenticated
Browser Version:
| Testing Start Date | 2014-07-14
| Testing End Date | 2015-01-23
Name of Tester(s):
| Issue Site: | http://www.room4me.com/raptortest1/bug_report_page.php
ID # | Description | March Worklist | June Functionality | August | September | November
1.1 | Contra-indications shall be clickable to go into details. | PASS
1.2 | Sort on work list by column. | PASS
1.3 | Radiation Dose shall be enhanced to calculate a moving average on each radiation dose episode to create a dose data set. |  |  |  |  | PASS
1.4 | RAPTOR shall be enhanced to add additional automatic pre-populated fields based on protocols to improve efficiency (e.g., have protocol contrast volumes pre-populate tech notes section; in that way tech does not need to enter data unless actual volume differed from planned). | PASS
1.5 | Improve the Refer Specialist concept. RAPTOR shall identify specialty role in addition to individuals. Use cases: For large VISN or VHA National Teleradiology Program NTP, the user does not know who is the specialist but wants to collaborate. The specialty role will assist in collaboration. |  | PASS
1.6 | Improve the reporting functionality to include measurements of department efficiency. |  | PASS
1.7 | Improve the reporting functionality to include the tracking of user actions to determine effectiveness. |  | PASS
1.8 | Improve the summary report concept such that details of medical decisions and actions for the examination protocol and execution are easily found within medical record. |  |  |  |  | PASS
1.9 | Auto-populate fields. (e.g., protocol contrast volumes default into tech notes page, then only need to do further entry if amount was different). | PASS
1.1O | Include facility/administrator configurability. | PASS
1.11 | Administrator shall be able to replace an order. | [5 empty] | PASS
1.12 | Enable/Improve search functionality on all information tabs. |  |  |  |  | PASS
1.13 | Notes and lab tabs should be brought up to original presentation concept (e.g. Notes default most recent progress or primary care note, then most recent d/c summary, then most recent h&p, then reverse chronological order. | PASS | PASS
1.14 | Improve medication tab to include reconciliation with outside medication list. |  | PASS
1.15 | Improve the allergies tab headings to reflect clinical data. |  | PASS
1.16 | Improve the Suspend ticket concept. In particular, suspension notifications and impact on other functionality shall be defined, designed, developed, tested and deployed. | PASS | PASS
1.17 | Add allergies thumbnail alert if risk is found. |  |  |  |  | PASS
1.18 | If RAPTOR discovers more than five pending imaging orders on a patient, the user is given the opportunity to click to reveal/display complete listing of pending imaging exams. |  |  |  |  | PASS
1.19 | Include protocol templates to improve workflow efficiency and dose reduction. Adding this functionality will improve user acceptance of RAPTOR. It will benefit quality locally by promoting sharing of templates between users and nationally by sharing between sites. | PASS
1.2o | Specify for Nuclear Medicine (NM) workflow. This functionality will improve user acceptance of RAPTOR. |  | PASS
1.21 | Allergy Contraindications: RAPTOR shall compare the patient's Allergy list against a set of user configurable key words to identify patients with a past history of adverse reaction to imaging contrast agents. |  |  |  |  | PASS
Default Key Words = Iodine, Iodinated, Contrast, Gadolinium, intravascular
1.22 | Allergy Contraindications: If RAPTOR identifies a match suggesting a patient with potential allergy contraindication, then RAPTOR shall flag with user configurable message that consent is required. |  |  |  |  | PASS
DEFAULT MESSAGE = "CONSENT FOR IV CONTRAST REQUIRED, POTENTIAL HISTORY OF IMAGING CONTRAST DYE ALLERGY"
This flag must be acknowledged by user.
1.23 | Allergy Contraindications: User can acknowledge and still elect to proceed without consent required radio button checked and has option to indicate a reason in the protocol notes free text area. |  |  |  |  | PASS
If flag for consent conditions are true, RAPTOR then also displays the following configurable default message text
"POTENTIAL HISTORY OF IMAGING CONTRAST DYE ALLERGY, CONSIDER PROPHYLACTIC PREMEDICATION PROTOCOL"
User does not have to acknowledge this message.
1.24 | RAPTOR shall have a failsafe against someone abandoning a workstation and someone else sitting down and performing orders under prior person’s identity. |  |  |  |  | PASS
Example includes having a signature code that is requested at time of 1st approval command of a session. Then, the signature request will not be requested at subsequent approvals within same session.
1.25 | RAPTOR desktop security shall assign an automatic time for the application to close if not used.
1.26 | Add the Scheduled State between Approved and Protocol Acknowledged states. Preferably interface with scheduling system, if feasible. |  | PASS
1.27 | Add a column of scheduled date/time to work list. | PASS
1.28 | Highlight the work list to ER, STAT & Inpatient orders using visual cues. | PASS
1.29 | Enhance the work list to include additional orders.
1.3o | Sort on work list by modality. This could be used to have a daily view into a modality type. | PASS
1.31 | Administrative function for facility personnel to manage user access and to provide audit trail. Include ability to add, modify, or delete protocols. |  | PASS
1.32 | Ability to protocol other modalities such as ultrasound or fluoro studies. |  | PASS
1.33 | Display allergies, medication (metformin) and creatinine/ Glomerular Filtration Rate (GFR) in one area for ease of viewing. |  | PASS
1.34 | Include API that allows link to CPRS (in case further review of a patient’s record is required) and PACS (to review prior images). Ideally, these links will not require additional sign on. |  | PASS
1.35 | The worklist can be manually updated with scheduling date. Once a patient is scheduled, the application can retain this information. | PASS
1.36 | Automatic time out when the application is not in use (refer to item 25). |  |  |  |  | PASS
1.37 | Display any additional pending radiology exams to facilitate scheduling coordination; I would not limit the number of pending exams (see item 18). |  |  |  |  | PASS
2.1 | Each facility may vary as to when a study is protocoled, some may protocol before scheduling, and others may do in reverse order. RAPTOR shall pull unscheduled orders as well as scheduled ones. Include scheduled date/time (See Item 27, above). For unscheduled orders, display “date desired”. | PASS
2.2 | Sort on work list | PASS
2.3 | Display recent exams of same modalities, avoid duplicate scanning within a short period of time, reduce unnecessary radiation exposure and waste of resources. |  | PASS
2.4 | Separate out studies by location (Emergency Department (ED), inpatients, outpatients) as well as urgency (Stat) (See Item 1.28, above). | PASS
2.5 | Sort on work list by modality (See Item 1.30, above). | PASS
2.6 | Filter work list by modality. | PASS
2.7 | Sort by date (date of exam and time), and sort by patient names. | PASS
2.8 | Add, “search” functionality with a box to type in patient’s name to quickly locate a patient’s order if there are a large number of orders. |  | PASS
2.9 | A work list filter for user to indicate the urgency of studies to be performed, (i.e. stat, urgent, or routine). | PASS
13 | A drop down menu for user to indicate the urgency of studies to be performed, i.e., stat, urgent, or routine. |  | PASS
1 | Sign-in and log out features, currently this is not included in the prototype as viewed in sandbox. |  | PASS | PASS
2 | Display all items on one page to minimize scrolling, use drop down menu for efficient use of screen space. |  | PASS
3 | Allow override or bypass a field except for contraindications where acknowledgement is required. | PASS

## Enhancements
RAPTOR User Acceptance Test Case
| Project Name / # | RAPTOR UAT
| Test Site: | http://raptortest.vaftl.us/Rsite500/raptor/user/login?status=notauthenticated
| Browser Version: | IE
Testing Start Date
Testing End Date
Name of Tester(s):
| Issue Site: | http://www.room4me.com/raptortest1/bug_report_page.php
ID # | Description | test
| Write-back RAPTOR information into VistA instead of a separate database | Testing under Sept tab | PASS
| Radiation Dose | Initial Dose in Workflow into QA tab | PASS
| Joint Commission Technologist Safety Checklist | Testing under Sept tab | PASS
| Replace existing order | Testing under Replace Order tabs (privledged and non-priv use cases) | PASS
| Cancel an order | Testing under Sept tab | PASS

## Login - Logout
UAT Testing | Seattle | Portand | Fresno | Tucson | Innovations
Scheduler | 4radiologist/radiology4!/RADIOLOGY4 | 8radiologist/radiology8!//RADIOLOGY8 | 10radiologist/radiology10!/RADIOLOGY10 | 9radiologist/radiology9!/RADIOLOGY9 | 13radiologist/radiology13!/RADIOLOGY13
Resident | 1radiologist/radiology1!/RADIOLOGY1 | 39radiologist/radiology39!/radiology39 | 25radiologist/radiology25!/RADIOLOGY25 | 40radiologist/radiology40!/RADIOLOGY40 | 14radiologist/radiology14!/RADIOLOGY14
Radiologist | 7radiologist/radiology7!//RADIOLOGY7 | 5radiologist/radiology5!/RADIOLOGY5 | 11radiologist/radiology11!/RADIOLOGY11 | 6radiologist/radiology6!/RADIOLOGY6 | 15radiologist/radiology15!/RADIOLOGY15
Technologist | 3radiologist/radiology3!//RADIOLOGY3 | 12radiologist/radiology12!//RADIOLOGY12 | 2radiologist/radiology2!/RADIOLOGY2 | 38radiologist/radiology38!/RADIOLOGY38 | 16radiologist/radiology16!/RADIOLOGY16
2nd Radiologist |  | 18radiologist/radiology18!/RADIOLOGY18
RAPTOR User Acceptance Test Case
| Project Name / # | RAPTOR 2014 - 2015 UAT
| Test Site: | http://raptortest.vaftl.us/Rsite500/raptor/user/login?status=notauthenticated
Browser Version:
Testing Start Date
Testing End Date
Name of Tester(s):
| Issue Site: | http://www.room4me.com/raptortest1/bug_report_page.php
| Description | Preconditions / Data | Steps To Execute | Expected Results | Pass/Fail | Fail | Retest Date | Defect/Comments
| Logon | http://raptortest.vaftl.us/Rsite500/raptor/user/login?status=notauthenticated (FROM INSIDE THE VA NETWORK) http://184.73.210.16/RSite500/raptor/user/login (FROM OUTSIDE THE VA NETWORK) | Log onto RAPTOR, by using valid username, password. (i.e. SEE ABOVE FOR ASSIGNED ACCESS/VERIFY/SIGNATURE CODES) | Integration with VA user authentication and the user's worklist is displayed.
| Logout | From worklist (or any other screen) http://184.73.210.16/RSite500/raptor/worklist | The user selects log out from the admin panel (upper right). | The user is returned to the logon page http://184.73.210.16/RSite500/raptor/raptor/kickout_timeout

## Worklist Functionality
RAPTOR User Acceptance Test Case
| Project Name / # | RAPTOR July 2014 UAT
| Test Site: | http://raptortest.vaftl.us/Rsite500/raptor/user/login?status=notauthenticated
Browser Version:
Testing Start Date
Testing End Date
Name of Tester(s):
| Issue Site: | http://www.room4me.com/raptortest1/bug_report_page.php
ID # | Description | Preconditions / Data | Steps To Execute | Expected Results | Pass | Fail
1.16 | Column Sort studies by location (inpatients, outpatients) as well as urgency (Stat). | cloud2 | Step 1 Worklist Columns, 2 Columns Sorting | On worklist, test that Patient Category/ location can be sorted by location. Test Data is either Inpatient/Outpatient. On worklist, Demonstrate that urgency can be sorted. Test Data is either STAT/Routine.
1.2 | Highlight the work list to STAT & Inpatient orders using visual cues. | cloud2 | Step 1 Worklist Columns, 2 Columns Sorting | On worklist, test that Urgency can be sorted. Visual cues included with Ranking Score.
1.27 | A work list for user to indicate the urgency of studies to be performed, (i.e. stat, urgent, or routine). | cloud2 | Step 1 Worklist Columns, 2 Columns Sorting | On worklist, test urgency column sorting. User then selects STAT order to protocol.
1.28 | The urgency of studies to be performed can be displayed, sorted and searched, i.e., stat or routine. | cloud2 | Step 1 Worklist Columns, 2 Columns Header 3. Select Protocol | On worklist, test urgency column sorting.
1.3 | Sort on work list by column. | cloud2 | Step 1 Worklist Columns, 2 Columns Sorting 3. Repeat sort for all columns. | On worklist, test sorting of each column.
1.35 | Sort on work list by modality. This could be used to have a daily view into a modality type. | cloud2 | Step 1 Worklist Columns, 2 Modality Columns Header 3. Select Protocol | On worklist, test Modality column sorting.
2 | Sort on work list | cloud2 | Step 1 Worklist Column Header, 2 Search for modality type, 3 Sorting 4 Personal worklist select | On worklist, test column sorting.
2.2 | Filter work list by modality. | cloud2 | Step 1 Worklist Columns, 2 Search Modality Type, 3 Sorting | On worklist, search by modality type and column sorting.
2.4 | Sort by date (date of exam and time), and sort by patient names. | cloud2 | Step 1 Worklist Columns, 2 Sort by date 3 Sort by name | On worklist, test date column and name column sorting.
2.6 | Display all items on one page to minimize scrolling, use drop down menu for efficient use of screen space. | cloud2 | Step 1 Manage Rows, Show Entries | On worklist, test per page (10, 25, 50, all) functionality. At the bottom of the page, nnShowing 1 to n of 693 entries (filtered from n total entries).
2.7 | Add a column of scheduled date/time to work list. | cloud2 | Step 1 Scheduled column is on far right of worklist. | On worklist, test scheduled column. On worklist, entry is updated from unknown to test data entered.
2.9 | The worklist can be manually updated with scheduling date. Once a patient is scheduled, the application can retain this information. |  | Step 1 If Scheduled Info is already provided, then review. 2. If Scheduled info is not provided, then select "Unknown". 3 Then Select, Room, Time, etc and Save. | On worklist, test scheduled column. On worklist, entry is updated from unknown to test data entered. Status message, Scheduled ID (Order) for Date, Time in RM
3 | Allow override or bypass a field except for contraindications where acknowledgement is required. |  | Step 6 Templates Concept Step 7 Auto Populate fields | On dashboard, Demonstrate template allows for auto-populated fields.
1.19 | Include protocol templates to improve workflow efficiency and dose reduction. Adding this functionality will improve user acceptance of RAPTOR. It will benefit quality locally by promoting sharing of templates between users and nationally by sharing between sites. |  | Step 6 Templates Concept Step 7 Auto Populate fields | On dashboard, Demonstrate template allows for auto-populated fields.
1.4 | RAPTOR shall be enhanced to add additional automatic pre-populated fields based on protocols to improve efficiency (e.g., have protocol contrast volumes pre-populate tech notes section; in that way tech does not need to enter data unless actual volume differed from planned). |  | Step 6 Templates Concept Step 7 Auto Populate fields | On dashboard, Demonstrate template allows for auto-populated fields.
1.9 | Auto-populate fields. (e.g., protocol contrast volumes default into tech notes page, then only need to do further entry if amount was different). |  | Step 6 Templates Concept Step 7 Auto Populate fields | On dashboard, Demonstrate template allows for auto-populated fields.
1.1 | Contra-indications shall be clickable to go into details. |  | Step 8. Contra-indications | On dashboard, Demonstrate contra-indications is clickable.
13 | Improve the Suspend ticket concept. In particular, suspension notifications and impact on other functionality shall be defined, designed, developed, tested and deployed. |  | Step 9 Suspend/ Reserve | On dashboard, demonstrate the reserve message. On dashboard, demonstrate that release back to worklist button takes you back to worklist.
1.16 | Improve the Suspend ticket concept. In particular, suspension notifications and impact on other functionality shall be defined, designed, developed, tested and deployed. |  | Step 9 Suspend/ Reserve | On dashboard, demonstrate the reserve message. On dashboard, demonstrate that suspend button takes you back to worklist.

## Protocol
RAPTOR User Acceptance Test Case
| Project Name / # | RAPTOR 2014 - 2015 UAT
| Test Site: | http://raptortest.vaftl.us/Rsite500/raptor/user/login?status=notauthenticated
Browser Version:
Testing Start Date
Testing End Date
Name of Tester(s):
| Issue Site: | http://www.room4me.com/raptortest1/bug_report_page.php
ID # | Description | Preconditions / Data | Steps To Execute | Expected Results | Pass Fail
1.5 | Improve the Refer Specialist concept. RAPTOR shall identify specialty role in addition to individuals. Use cases: For large VISN or VHA National Teleradiology Program NTP, the user does not know who is the specialist but wants to collaborate. The specialty role will assist in collaboration. | cloud2 | Set-up: Under administer, manage user, select collaboration profile settings (most to least significant). User provides and saves keyword values. Confirm settings in Protocol Collaborate Button. | Under Request Collabaration on protocol tab, Modality and Anatomy Specialties are displayed. User selects name and requests collabaration. On worklist, this protocol is assigned to the name.
1.6 | Improve the reporting functionality to include measurements of department efficiency. |  | In adminster, select manage reports. View Department Activity Report. | User can view department activity report.
1.7 | Improve the reporting functionality to include the tracking of user actions to determine effectiveness. |  | In adminster, select manage reports. View User Activity Report. | User can view user activity report.
1.1O | Include facility/administrator configurability. | cloud2 | Under Admin, User Management can configure profile, contraindications, protocols, lists, reports | On worklist, test User Management can configure profile, contraindications, protocols, lists, reports
1.13 | Notes and lab tabs should be brought up to original presentation concept (e.g. Notes default most recent progress or primary care note, then most recent d/c summary, then most recent h&p, then reverse chronological order. | cloud2 | Notes tab displays selected notes and rest of notes in sections of descending chronological order. | User can search and sort on notes and lab tabs.
1.14 | Improve medication tab to include reconciliation with outside medication list. | cloud2 | Under administer, Manage lists. Select the Edit At Risk Medications list. User has ability to add, delete, or change medications list. | Under Medication tab, updated medications is displayed.
1.15 | Improve the allergies tab headings to reflect clinical data. | cloud2 | Allergies tab displays date, item, causitive agent and Observed/Historical information. | Allergies tab displays date, item, causitive agent and Observed/Historical information.
1.16 | Improve the Suspend ticket concept. In particular, suspension notifications and impact on other functionality shall be defined, designed, developed, tested and deployed. |  | Suspend/ Reserve | On dashboard, demonstrate the reserve message. On dashboard, demonstrate that suspend button takes you back to worklist. Status message and workflow status showing assignment.
1.2O | Specify for Nuclear Medicine (NM) workflow. This functionality will improve user acceptance of RAPTOR. | cloud2 | Under protocol tab, Radioisotope panel. | Radioisotope information can be saved and displayed.
1.31 | Administrative function for facility personnel to manage user access and to provide audit trail. Include ability to add, modify, or delete protocols. |  | In adminster, select edit profile to manage access. Select manage protocol to add, edit delete protocols. | User uploads protocol. User provides correct protocol matching values. Naming convention. Index values. User provides correct administrative metadata values. Title
1.34 | Include API that allows link to CPRS (in case further review of a patient’s record is required) and PACS (to review prior images). Ideally, these links will not require additional sign on. |  | Under Rad Reports tab, RAPTOR displays either image thumbnail or no images available status message | Image displayed in frame (see 2005 example)
2.3 | Display recent exams of same modalities, avoid duplicate scanning within a short period of time, and reduce unnecessary radiation exposure and waste of resources. |  | Radiology reports display recent completed exams' reports. | When clicking on link, reports details are displayed
2.6 | Filter work list by modality. |  | On Worklist. 1. Select Modality column. 2. Check off modality to sort. 3. Refresh worklist.
2.8 | Add, “search” functionality with a box to type in patient’s name to quickly locate a patient’s order if there are a large number of orders. |  | On Worklist search box. 1. Type in item to search. | Worklist is refreshed. Status message, Showing filtered worklist entries from total entries.
2.11 | Display recent exams of same modalities to avoid duplicate scanning within a short period of time, reduce unnecessary radiation exposure and waste of resources. |  | Radiology Reports tab
3.1 | Integration with VA user authentication |  | RAPTOR role = VistA User Name | Authenticated user only. Non-authenticated user is rejected. In user management, select administer then add users
4.1 | Sign-in and log out features. |  | User Access login and logout screen and error messages are displayed. | Authenticated user only. Non-authenticated user is rejected. In user management, select administer then add users
4.2 | Display all work list items on one page to minimize scrolling, use drop down menu for efficient use of screen space. |  | Step 1 Manage Rows, Show Entries | On worklist, test per page (10, 25, 50, all) functionality. At the bottom of the page, nnShowing 1 to n of 693 entries (filtered from n total entries).
cloud2

## Initial Workflow Script
| Project Name / # | RAPTOR 2014 - 2015 UAT
| Test Site: | http://raptortest.vaftl.us/Rsite500/raptor/user/login?status=notauthenticated
Browser Version:
Testing Start Date
Testing End Date
Name of Tester(s):
| Issue Site: | http://www.room4me.com/raptortest1/bug_report_page.php
Role | Description | Preconditions / Data | Steps To Execute | Expected Results | Pass Fail
Scheduler | Workflow Scenario |  | Scheduler will logon, review filtered worklist for highest priority CT orders. Scheduler will use RAPTOR to assign and add notes for two different studies to Resident. Scheduler accidentally double books room and error message is displayed. Patient communications are captured. The Scheduler cancels another exam, based on patient request. Scheduler logs off. | Order assigned.
Resident |  | Scheduler steps | Resident will log on and reviews worklist and sees assignment. Resident selects these two for personal list, so one item follows the other. For each, Resident reviews scheduler notes. Two studies assigned are reviewed and protocoled and prepped for the Radiologist to review and sign. Resident selects request approval. Writes note (example using using mass marker note) Technologist, please ask patient where mass is and then bracket mass with skin surface. markers prior to scanning. Resident logs off. | Order protocoled but not signed.
Radiologist |  | Scheduler, Resident steps | Radiologist logs on and reviews worklist and sees collaboration. Radiologist selects these two for personal list, so one item follows the other. For each, Radiologist reviews scheduler notes. Two studies assigned are reviewed and protocoled. Radiologist makes changes and writes note. Radiologist signs protocols and logs off. | Protocol signed.
Technologist |  | Scheduler, Resident,Radiologist steps | Technologist logs on and reviews worklist and sees approved items. Technologist reviews work and acknowledges. | Protocol acknowledged.

## Library Template Scenario
| Project Name / # | RAPTOR 2014 2015 UAT
| Test Site: | http://raptortest.vaftl.us/Rsite500/raptor/user/login?status=notauthenticated
Browser Version:
Testing Start Date
Testing End Date
Name of Tester(s):
| Issue Site: | http://www.room4me.com/raptortest1/bug_report_page.php
Role | Description | Preconditions / Data | Steps To Execute | Expected Results | Pass Fail
Radiologist, Resident, Technologist | Update Template Library Scenario |  | Authorized User will logon, selects Manage Protocols. User will then search and select to edit a protocol. | Edit Protocol in Library is displayed.
Radiologist, Resident, Technologist |  |  | User updates the values of the protocol; for example name, keywords, default protocol values and notes. User saves protocol updates. | Status message of saved changes to protocol.
Radiologist, Resident, Technologist |  |  | User then selects an applicable order. On the protocol page, under protocol name, the user selects the protocol just updated. The user confirms that the updates to the template are displayed. | Tempate updated.
Radiologist, Resident, Technologist |  |  | User selects library tab and confirms updates are displayed. | Library updated.

## Contraindication Scenario
| Project Name / # | RAPTOR 2014 - 2015 UAT
| Test Site: | http://raptortest.vaftl.us/Rsite500/raptor/user/login?status=notauthenticated
Browser Version:
Testing Start Date
Testing End Date
Name of Tester(s):
| Issue Site: | http://www.room4me.com/raptortest1/bug_report_page.php
Role | Description | Preconditions / Data | Steps To Execute | Expected Results | Pass Fail
Radiologist, Resident, Technologist | Contraindication Scenario |  | Authorized User will logon to administer rules, selects Manage Contraindications. User will then search and select to edit a contraindication. | Manage contraindications in admin is displayed.
Radiologist, Resident, Technologist |  |  | User updates the values of the contraindication rule; for example name, explanation, require acknowledgement, active. User saves contraindication rule updates. User closes admin panel. | After save, time stamp of rule is updated on admin screen.
Radiologist, Resident, Technologist |  |  | User then selects an applicable order from worklist. On the protocol page, user confirms data applies to rule. Rules that apply to data are displayed in yellow rectangle at the top of the tabs. For example, if the rule was age > 60, then confirm patient age is over 60. If the rule does not apply due to data, it is not displayed, and select another patient until data applies to rule. | Protocol selected.
Radiologist, Resident, Technologist |  |  | User selects protocol tab, user selects protocol panel information, for example, contrast, hydration, etc. If the rule update was to text, select text at acknowledgement (at the bottom of the page) to display the updated text. | User confirms that Contraindication rule was updated.

## Workflow into QA
| Project Name / # | RAPTOR 2014 - 2015 UAT
| Test Site: | http://raptortest.vaftl.us/Rsite500/raptor/user/login?status=notauthenticated
Browser Version:
Testing Start Date
Testing End Date
Name of Tester(s):
| Issue Site: | http://www.room4me.com/raptortest1/bug_report_page.php
Role | Description | Preconditions / Data | Steps To Execute | Expected Results | Pass Fail
Scheduler | Workflow Scenario |  | Scheduler will logon, review filtered worklist for highest priority CT orders. Scheduler will use RAPTOR to assign and add notes for two different studies to Resident. Scheduler accidentally double books room and error message is displayed. Patient communications are captured. The Scheduler cancels another exam, based on patient request. Scheduler logs off. | Order assigned.
Resident |  | Scheduler steps | Resident will log on and reviews worklist and sees assignment. Resident selects these two for personal list, so one item follows the other. For each, Resident reviews scheduler notes. Two studies assigned are reviewed and protocoled and prepped for the Radiologist to review and sign. Resident selects request approval. Writes note (example using using mass marker note) Technologist, please ask patient where mass is and then bracket mass with skin surface. markers prior to scanning. Resident logs off. | Order protocoled but not signed.
Radiologist |  | Scheduler, Resident steps | Radiologist logs on and reviews worklist and sees collaboration. Radiologist selects these two for personal list, so one item follows the other. For each, Radiologist reviews scheduler notes. Two studies assigned are reviewed and protocoled. Radiologist makes changes and writes note. Radiologist acknowledges contraindications (if applicable) and signs protocols and logs off. | Protocol signed.
Technologist |  | Scheduler, Resident,Radiologist steps | Technologist logs on and reviews worklist and sees approved items. Technologist answers safety checklist questions. Technologist reviews work and acknowledges contraindications (if applicable) and protocol. | Protocol acknowledged.
Technologist |  | Scheduler, Resident,Radiologist steps | In the Ready for Examination, Protocol acknowledged mode, Technologist updates the examination notes with actual values. The technologist answers consent was received. The technologist writes notes and selects exam completed. Technologist logs off. | Exam completed.
Radiologist |  | Scheduler, Resident,Radiologist, Techologist steps | Radiologist logs on and reviews worklist in Interpretation mode and selects exam completed from worklist. Radiologist reviews exam while interpretation results. Radiologist selects interpetation completed. | Interpetation completed.
Radiologist |  | Scheduler, Resident,Radiologist, Techologist steps | Radiologist reviews worklist in QA mode and selects QA completed from worklist. Radiologist reviews exam while QA results. Radiologist selects QA completed. | Interpetation completed.

## Sept Use Cases
| Project Name / # | RAPTOR 2014 2015 UAT
| Test Site: | http://raptortest.vaftl.us/Rsite500/raptor/user/login?status=notauthenticated
Browser Version:
Testing Start Date
Testing End Date
Name of Tester(s):
| Issue Site: | http://www.room4me.com/raptortest1/bug_report_page.php
Role | Description | Preconditions / Data | Steps To Execute | Expected Results | Pass Fail
Any User | Enable search functionality on all information tabs. | Table must contain searchable data. | From any RAPTOR tab (except, Protocol & Dx), the right hand corner above the table contains the search area. | Queries provide instantanous search results
Any User | Display any additional pending radiology exams to facilitate scheduling coordination |  | From the worklist, #P (pending orders), provides a numeric showing the matches for each row. Clicking on the number, drills down to patient (name in search box) and lists orders pending for patient. Select refrech worklist to return to default worklist. | Queries provide instantanous search results
Any User | If RAPTOR discovers more than five pending imaging orders on a patient, the user is given the opportunity to click to reveal/display complete listing of pending imaging exams. |  | From the worklist, #P (pending orders), provides a numeric showing the matches for each row. Clicking on the number, drills down to patient (name in search box) and lists orders pending for patient. Select refrech worklist to return to default worklist. | Selecting the number provides instantanous pending orders search results. All number of pending orders are displayed, more than 5 are visually highlighted.
Any User | Allergy Contraindications: RAPTOR shall compare the patient's Allergy list against a set of user configurable key words to identify patients with a past history of adverse reaction to imaging contrast agents. Default Key Words = Iodine, Iodinated, Contrast, Gadolinium, intravascular | In Admin, Manage Lists, Edit Allergy Contrast List. Enter test allergen that matches patient's allergies. | From the ready for examination worklist, select the id that matches a patient's allergies with an imaging event. | CONTRAINDICATIONS REQUIRING ACKNOWLEDGEMENT, Allergy Risks are displayed.
User who can approve | Allergy Contraindications: If RAPTOR identifies a match suggesting a patient with potential allergy contraindication, then RAPTOR shall flag with user configurable message that consent is required. DEFAULT MESSAGE is CONSENT FOR IV CONTRAST REQUIRED, POTENTIAL HISTORY OF IMAGING CONTRAST DYE ALLERGY. This flag must be acknowledged by user. | In Admin, Manage Lists, Edit Allergy Contrast List. Enter test allergen that matches patient's allergies. | From ready for examination worklist, Approve the protocol, and then view the Allergy Contraindications | Contraindication "CONSENT FOR IV CONTRAST REQUIRED, POTENTIAL HISTORY OF IMAGING CONTRAST DYE ALLERGY" is displayed and acknowledged.
Any User authorized to view,edit contraindication rules. | Allergy Contraindications: User can acknowledge and still elect to proceed without consent required radio button checked and has option to indicate a reason in the protocol notes free text area. If flag for consent conditions are true, RAPTOR then also displays the following configurable default message text. POTENTIAL HISTORY OF IMAGING CONTRAST DYE ALLERGY, CONSIDER PROPHYLACTIC PREMEDICATION PROTOCOL. User does not have to acknowledge this message. | See contraindication rule PROPHYLACTIC_ALLERGY_PREMEDICATION. Requires Acknowledgment is set to no. | From ready for examination worklist, Approve the protocol, and then view the Allergy Contraindications | Contraindication "POTENTIAL HISTORY OF IMAGING CONTRAST DYE ALLERGY, CONSIDER PROPHYLACTIC PREMEDICATION PROTOCOL." is displayed.
Any User | Display any additional pending radiology exams to facilitate scheduling coordination |  | From the worklist, #P (pending orders), provides a numeric showing the matches for each row. Clicking on the number, drills down to patient (name in search box) and lists orders pending for patient. Select refrech worklist to return to default worklist. | Queries provide instantanous search results
Users who have electronic signature rights | Safety Checklist Note Writeback | Complete protocol workflow to exam completed, including Safety Checklist. | In the interpretation mode, select interpretation complete & commit details to VistA. | To confirm, for this patient, review the notes tab to display to RAPTOR safety notes.

## Replace Order (privledged)
| Project Name / # | RAPTOR 2014 - 2015 UAT
| Test Site: | http://raptortest.vaftl.us/Rsite500/raptor/user/login?status=notauthenticated
Browser Version:
Testing Start Date
Testing End Date
Name of Tester(s):
| Issue Site: | http://www.room4me.com/raptortest1/bug_report_page.php
Role | Description | Preconditions / Data | Steps To Execute | Expected Results | Pass Fail
Privledged User (User who is holds the ORES or OREMAS CPRS Key) | Replace Order Scenario |  | Radiologist will logon, review filtered worklist for orders that need to be replaced. Radiologist selects an order to protocol. Write the RAPTOR tracking ID# ____. | Write the Tracking ID# ____ (displayed in left column of worklist & last four digits of upper left of header).
Privledged User (User who is holds the ORES or OREMAS CPRS Key) |  |  | After reviewing the information on the protocol tab, the user selects the replace order button at the bottom of the page. | After reviewing the information on the protocol tab, the user selects the replace order button at the bottom of the page.
Privledged User (User who is holds the ORES or OREMAS CPRS Key) | Step 1 of 3 of the Replace Order |  | Step 1 of 3 Replacement Reason * PER ERROR Select reason for canceling the existing order. Imaging Type * Select Imaging Type CT SCAN for the new order. | Step 1 of 3 Replacement Reason * PER ERROR Select reason for canceling the existing order. Imaging Type * Select Imaging Type CT SCAN for the new order.
Privledged User (User who is holds the ORES or OREMAS CPRS Key) | Step 2 of 3 of the Replace Order |  | Step 2 of 3 of the Replace Order Ordering Location * Select location Orderable Item * CT ABDOMEN W/O Contrast Select orderable item (imaging procedure) | Step 2 of 3 of the Replace Order Ordering Location * Select location 2-INTERMED Orderable Item * CT ABDOMEN W/O Contrast Select orderable item (imaging procedure)
Privledged User (User who is holds the ORES or OREMAS CPRS Key) | Step 2 of 3 of the Replace Order (continued) |  | Step 2 of 3, Select Modifiers, Urgency, Transports, Category, Isolation, Pregnancy Status from drop down menus. | Step 2 of 3, Select Modifiers, Urgency, Transports, Category, Isolation, Pregnancy Status selected from drop down menus.
Privledged User (User who is holds the ORES or OREMAS CPRS Key) | Step 2 of 3 of the Replace Order (continued) |  | Step 2 of 3, Reason for Study and Clinical History. | Step 2 of 3, Free Text Type in Reason for Study and Clinical History.
Privledged User (User who is holds the ORES or OREMAS CPRS Key) | Step 2 of 3 of the Replace Order (continued) |  | Step 2 of 3, Desired Exam Time *, PreOp Scheduled *, Preop Time * in the correct format. | Step 2 of 3, Desired Exam Time *, PreOp Scheduled *, Preop Time *
Privledged User (User who is holds the ORES or OREMAS CPRS Key) | Step 2 of 3 of the Replace Order (continued) |  | Step 2 of 3, Press Next button. | All fields are shown entered and the electronic signature field is highlighted.
Privledged User (User who is holds the ORES or OREMAS CPRS Key) | Step 3 of 3 of the Replace Order |  | Step 2 of 3, Electronic Signature is added. | The user is returned to worklist with status message displaying tracking ID# ____ is updated. Fields updated in step 2 are displayed in header.

## Replace Order (without priv)
| Project Name / # | RAPTOR 2014 - 2015 UAT
| Test Site: | http://raptortest.vaftl.us/Rsite500/raptor/user/login?status=notauthenticated
Browser Version:
Testing Start Date
Testing End Date
Name of Tester(s):
| Issue Site: | http://www.room4me.com/raptortest1/bug_report_page.php
Role | Description | Preconditions / Data | Steps To Execute | Expected Results | Pass Fail
Non-privledged user | Replace Order Scenario |  | Radiologist will logon, review filtered worklist for orders that need to be replaced. Radiologist selects an order to protocol. Write the RAPTOR tracking ID# ____. | Write the Tracking ID# ____ (displayed in left column of worklist & last four digits of upper left of header).
Non-privledged user |  |  | After reviewing the information on the protocol tab, the user selects the replace order button at the bottom of the page. | After reviewing the information on the protocol tab, the user selects the replace order button at the bottom of the page.
Non-privledged user |  |  | The user sees the following displayed, "Your account does not have sufficient VISTA privilege to replace CPRS orders Relevant VISTA keys are the following... PROVIDER key allows an account to create orders OREMAS key allows an account to use Signature on File feature Your account has neither of these keys." | The user selects exit with no changes.

## Cancel Order
| Project Name / # | RAPTOR 2014 - 2015 UAT
| Test Site: | http://raptortest.vaftl.us/Rsite500/raptor/user/login?status=notauthenticated
Browser Version:
Testing Start Date
Testing End Date
Name of Tester(s):
| Issue Site: | http://www.room4me.com/raptortest1/bug_report_page.php
Role | Description | Preconditions / Data | Steps To Execute | Expected Results | Pass Fail
Non-privledged user | Cancel Order Scenario #1 |  | Radiologist will logon, review filtered worklist for orders that need to be replaced. Radiologist selects an order to protocol. Write the RAPTOR tracking ID# ____. | Write the Tracking ID# ____ (displayed in left column of worklist & last four digits of upper left of header).
Non-privledged user 01vehu |  |  | After reviewing the information on the protocol tab, the user selects the cancel order button at the bottom of the page. | After reviewing the information on the protocol tab, the user selects the replace order button at the bottom of the page.
Non-privledged user | Step |  | The user sees the following displayed, "Your account does not have sufficient VISTA privilege to cancel CPRS orders Relevant VISTA keys are the following... PROVIDER key allows an account to create orders OREMAS key allows an account to use Signature on File feature Your account has neither of these keys." | The user selects exit with no changes.
Provider | Cancel Order Scenario #2 |  | Radiologist will logon, review filtered worklist for orders that need to be replaced. Radiologist selects an order to protocol. Write the RAPTOR tracking ID# ____. | Write the Tracking ID# ____ (displayed in left column of worklist & last four digits of upper left of header).
Provider |  |  | This order may continue to show up in the worklist until the original order provider signs the discontinuation action.
Provider |  | Reason for Cancel | Select the Reason for Cancel
Provider |  | Select Cancel this Imaging Order | Status Message Order is Canceled.
OREMAS KEY Holder | Cancel Order Scenario #3 |  | Clerk will logon, review filtered worklist for orders that need to be replaced. Radiologist selects an order to protocol. Write the RAPTOR tracking ID# ____. | Write the Tracking ID# ____ (displayed in left column of worklist & last four digits of upper left of header).
|  | Select Cancel this Imaging Order | Your account has the priviledge to fully cancel using OREMAS key by providing the electronic signature.
|  | Select the Reason for Cancel. Enter electronic signature | Status Message Order is Canceled.

## Fresno (hidden)
<VhaSite name="Test500 Raptor" ID="500" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.38.144" status="active" port="9300"/>
</VhaSite>
<VhaSite name="Test970 Fresno570, CA" ID="970" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.2" status="active" port="19002"/>
</VhaSite>
<VhaSite name="Test948 Portland648, OR" ID="948" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.11" status="active" port="19011"/>
</VhaSite>
<VhaSite name="Test978 Tuscon678, AZ" ID="978" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.31" status="active" port="19031"/>
</VhaSite>
<VhaSite name="Test963 Puget Sound (Seattle)663, WA" ID="963" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.12" status="active" port="19012"/>
</VhaSite>
The URLs are as follows...
PUGET SOUND (SEATTLE)
http://10.184.38.146/rsite963/raptor/start
FRESNO
http://10.184.38.146/rsite970/raptor/start
TUSCON
http://10.184.38.146/rsite978/raptor/start
PORTLAND
http://10.184.38.146/rsite948/raptor/start

## Tucson (hidden)
<VhaSite name="Test500 Raptor" ID="500" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.38.144" status="active" port="9300"/>
</VhaSite>
<VhaSite name="Test970 Fresno570, CA" ID="970" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.2" status="active" port="19002"/>
</VhaSite>
<VhaSite name="Test948 Portland648, OR" ID="948" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.11" status="active" port="19011"/>
</VhaSite>
<VhaSite name="Test978 Tuscon678, AZ" ID="978" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.31" status="active" port="19031"/>
</VhaSite>
<VhaSite name="Test963 Puget Sound (Seattle)663, WA" ID="963" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.12" status="active" port="19012"/>
</VhaSite>
The test URLs are as follows...
PUGET SOUND (SEATTLE)
http://10.184.38.146/rsite963/raptor/start
FRESNO
http://10.184.38.146/rsite970/raptor/start
TUSCON
http://10.184.38.146/rsite978/raptor/start
PORTLAND
http://10.184.38.146/rsite948/raptor/start

## Portland (hidden)
<VhaSite name="Test500 Raptor" ID="500" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.38.144" status="active" port="9300"/>
</VhaSite>
<VhaSite name="Test970 Fresno570, CA" ID="970" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.2" status="active" port="19002"/>
</VhaSite>
<VhaSite name="Test948 Portland648, OR" ID="948" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.11" status="active" port="19011"/>
</VhaSite>
<VhaSite name="Test978 Tuscon678, AZ" ID="978" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.31" status="active" port="19031"/>
</VhaSite>
<VhaSite name="Test963 Puget Sound (Seattle)663, WA" ID="963" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.12" status="active" port="19012"/>
</VhaSite>
The test URLs are as follows...
PUGET SOUND (SEATTLE)
http://10.184.38.146/rsite963/raptor/start
FRESNO
http://10.184.38.146/rsite970/raptor/start
TUSCON
http://10.184.38.146/rsite978/raptor/start
PORTLAND
http://10.184.38.146/rsite948/raptor/start

## Seattle (hidden)
<VhaSite name="Test500 Raptor" ID="500" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.38.144" status="active" port="9300"/>
</VhaSite>
<VhaSite name="Test970 Fresno570, CA" ID="970" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.2" status="active" port="19002"/>
</VhaSite>
<VhaSite name="Test948 Portland648, OR" ID="948" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.11" status="active" port="19011"/>
</VhaSite>
<VhaSite name="Test978 Tuscon678, AZ" ID="978" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.31" status="active" port="19031"/>
</VhaSite>
<VhaSite name="Test963 Puget Sound (Seattle)663, WA" ID="963" moniker="CPM">
<DataSource modality="HIS" protocol="VISTA" source="10.184.72.12" status="active" port="19012"/>
</VhaSite>
The test URLs are as follows...
PUGET SOUND (SEATTLE)
http://10.184.38.146/rsite963/raptor/start
FRESNO
http://10.184.38.146/rsite970/raptor/start
TUSCON
http://10.184.38.146/rsite978/raptor/start
PORTLAND
http://10.184.38.146/rsite948/raptor/start

## URLs
The test URLs are as follows...
PUGET SOUND (SEATTLE)
http://10.184.38.146/rsite963/raptor/start
FRESNO
http://10.184.38.146/rsite970/raptor/start
TUSCON
http://10.184.38.146/rsite978/raptor/start
PORTLAND
http://10.184.38.146/rsite948/raptor/start