## CY16 Q1 CIF Planned
EPS Project Name | Version | Build | Target Release Date
Enterprise Health Management Platform (eHMP) | 2 | PSI10 | CY16 Q1
VistA Intake Program (VIP) | Intake 012 NSR 20140505 Enhance Pt Inquiry to Add Personal Effects | DG*5.3*920 | 2016-01-12
VistA Intake Program (VIP) | Intake 013 NSR 20140712 Send Mail Message when VA Drug Class field is empty | GMRA*4.0*50 | CY16 Q1
VistA Intake Program (VIP) | Intake 014 NSR 20140715 Surgical Pathology Report Enhancements for Readability | LR*5.2*464 | CY16 Q1
VistA Intake Program (VIP) | Intake 015 NSR 20140713 Increase Selection from Auto Instrument File to 999 | LA*5.2*91 | 2016-01-13
VistA Intake Program (VIP) | Intake 016 NSR 20131108 Remove ListManager Restrictions on Mnemonics | OR*3.0*422 | CY16 Q1
VistA Intake Program (VIP) | Intake 017 NSR 20140714 Set Number of Labels in File 60 for Each Facility | LR*5.2*465 | CY16 Q1
Emergency Department Integration Software (EDIS) | V3 | v2.1.3-IOC-T4, EDP*2*8 | 2016-01-11
Beneficiary Travel Self-Service System | v1.0 | RSD, SDD | CY16 Q1
Disability Exam and Assessment Program (DEAP) Enhancements Phase 1 | v1.0 |  | CY16 Q1
Multiple Sclerosis Surveillance Registry |  |  | CY16 Q1
Healthcare Claims 837 Compliance - Phase 2, Iteration 1 |  | iteration 2 | CY16 Q1
Medical Care Collections Fund (MCCF) eBilling Compliance Phase 3 |  |  | CY16 Q1
Medical Care Collections Fund (MCCF) ePharmacy Compliance Phase 3 |  |  | CY16 Q1
Medical Care Collections Fund (MCCF) eInsurance Compliance Phase 3 |  |  | CY16 Q1
Pharmacy Re-engineering (PRE) Inbound ePrescribing | 1 | BRD, RSD | 2016-01-06
Health Data Repository (HDR) II | v3.11 | Iteration 2 | 2016-01-08
Health Data Repository (HDR) II | v3.12 | Iteration 1 | 2016-01-12
Airborne Hazards and Open Burn Pit Registry (AHOBPR) |  |  | CY16 Q1
Posttraumatic Stress Disorder Checklist 5 (PCL-5) and Mental Health Assistant Stabilization | v5.0.1 | YS*5.01*119 | CY16 Q1
Meaningful Use - New VistA Data Elements | 5.3 | DG*5.3*918 | 2016-01-11
Bed Management Solution v2 | 2 | iteration 1 RSD, SDD | 2016-01-12
Direct Secure Messaging Enhancements | 1.6.0 | 1.6.0.14 | 2016-01-21
Converged Registries Solutions Enhancements | 1 | RSD, SDD | CY16 Q1
VistA Blood Establishment Computer Software (VBECS) – Safety & Quality Updates | 2.1.0 | build 3 | CY16 Q1
VistA Immunizations Enhancements (VIMM) | 2 | PXRM*2.0*66 | 2016-01-12
Pharmacy Interface Automation - Automated Dispensing Units | 2 | PSJ*5*317 and PSS*1*193 | CY16 Q1
Joint Legacy Viewer (JLV) - Get The Data Back (GTDB) | 2.3.1 | iteration 1 | CY16 Q1
Telehealth Scheduling System (TSS) Integration Enhancements | v2.2 |  | CY16 Q1
VistA Services Assembler - Phase 2 |  |  | CY16 Q1
Enterprise Messaging Infrastructure Veterans Interoperability Infrastructure | 1 | SIDDs | CY16 Q1
Inpatient Medication Administration - Transdermal |  | PSS*1*191, PSJ*5*315, PSB*3*83, OR*3*417, and PSB*3*87 Docs | CY16 Q1
Pharmacy Safety Updates - Additive and IV Strength |  |  | CY16 Q1
Resident Assessment Instrument/Minimum Data Set (RAI/MDS) Modernization |  | DRG patch | CY16 Q1
Memorials Eligibility Office Automation (EOA) Capability/Manual PreNeed | 9.5 EOAS and 3.3 BOSS/AMAS | SRRv5.5 | CY16 Q1
Memorials First Notice of Death (FNOD) Enhancements | 9.7 | SRRv5.3 | CY16 Q1
Memorials First Notice of Death (FNOD) Enhancements | 6.3 | Cemetery Burial Schedules (CBS) | CY16 Q1
Presidential Memorial Certificate (PMC) Processing Capability | 10 | SRRv6.7 | CY16 Q1
Voluntary Service System (VSS) Enhancements |  |  | CY16 Q1
Fixed Medication Copayment Tiers |  |  | CY16 Q1
Memorial Enterprise Letters |  |  | CY16 Q1
Interagency Comprehensive Plan (ICP) - Phase 1 |  |  | CY16 Q1