## CY16 Q2 CIF Planned
EPS Project Name | Version | Build | Target Release Date
Enterprise Health Management Platform (eHMP) | r2.0.m1 | PSI10 | CY16 Q2
Enterprise Health Management Platform (eHMP) | 2 | PSI11 | CY16 Q2
Existing Program Intake Program (EPIP) | Intake 016 NSR 20131108 Remove ListManager Restrictions on Mnemonics | OR*3.0*422 | CY16 Q2
Existing Program Intake Program (EPIP) | Intake 017 NSR 20140714 Set Number of Labels in File 60 for Each Facility | LR*5.2*465 | CY16 Q2
Existing Program Intake Program (EPIP) | Intake 011 NSR 20100311 CPRS Laboratory Monitoring | OR*3.0*420 | CY16 Q2
Existing Program Intake Program (EPIP) | Intake 004 NSR 20140205 Provide Orders Mgmt. | OR*3.0*425 | CY16 Q2
Healthcare Claims 837 Compliance - Phase 2, Iteration 1 | EDI Web Viewer |  | CY16 Q2
Medical Care Collections Fund (MCCF) eBilling Compliance Phase 3 |  | IB*2.0*547 | CY16 Q2
Medical Care Collections Fund (MCCF) eInsurance Compliance Phase 3 |  | IB*2.0*549, DG*5.3*916 | CY16 Q2
Fixed Medication Copayment Tiers |  |  | CY16 Q2
Memorial Enterprise Letters |  |  | CY16 Q2
Interagency Comprehensive Plan (ICP) - Phase 1 | FCMT v3.2 |  | CY16 Q2
VistA Scheduling Enhancements | v5.3 | SD*5.3*627, SD*5.3*628, SD*5.3*642, SD*5.3*643, SD*5.3*645, GMRC*3.0*83 | CY16 Q2
Claims Attachments Compliance |  |  | CY16 Q2
Health Eligibility Center (HEC) | Pilot | RSD, SDD | CY16 Q2
eHealth Exchange | 6.7.0.17 | build 17 | CY16 Q2
State Prescription Monitoring Program Enhancements | 1 | PSO*7*451 v1 | CY16 Q2
VistA Services Assembler - Phase 2 |  |  | CY16 Q2
CPRS | v31 |  | CY16 Q2
CPRS | v32 |  | CY16 Q2
IAM Access Services (AcS) Phase 2 |  |  | CY16 Q2
VistA Immunizations Enhancements (VIMM) | v2.0 |  | CY16 Q2
Customer Gateway Services (CGS) |  | Increment 1 | CY16 Q2
Digits-to-Digits (D2D) |  | Increment 2 | CY16 Q2
VistA Integration Adapter (VIA) Enhancements | 2.0.21.0 | sprint 21 | CY16 Q2
Bed Management Solution Version 2 |  |  | CY16 Q2
eHealth Exchange |  |  | CY16 Q2
VistA Blood Establishment Computer Software (VBECS) – Safety & Quality Updates | v2.2.0 |  | CY16 Q2
Beneficiary Travel Self-Service System |  |  | CY16 Q2
Patient Statement Enhancement |  |  | CY16 Q2
Health Data Repository (HDR) II | 3.14 |  | CY16 Q2
Pharmacy Re-Engineering - PRE Inbound ePrescribing |  |  | CY16 Q2
Pharmacy Re-Engineering - PRE Medication Order Check Healthcare Application (MOCHA) | ME2 v26 | combined build | CY16 Q2
Pharmacy Re-Engineering - PRE Pharmacy Enterprise Customization System (PECS) | 6 |  | CY16 Q2
Pharmacy Re-Engineering - PRE Pharmacy Product System National (PPS-N) | 3 | PSN*4*396 v18, PSS*1*195 v5, build #283 | CY16 Q2
Pharmacy Re-Engineering - PRE DATUP | 3 |  | CY16 Q2
Direct Secure Messaging Enhancements |  | Increment 2 | CY16 Q2
Joint Legacy Viewer (JLV) - Get The Data Back (GTDB) |  |  | CY16 Q2
Inpatient Medication Administration - Transdermal |  |  | CY16 Q2
State Prescription Monitoring Program Enhancement |  |  | CY16 Q2
Converged Registries Solutions Enhancements |  |  | CY16 Q2
Medical Appointment Scheduling System (MASS) |  |  | CY16 Q2
Fileman 22.2E |  |  | CY16 Q2
Fileman 23 |  |  | CY16 Q2
Meaningful Use - New VistA Data Elements |  |  | CY16 Q2
Healthcare Reform/Affordable Care Act |  |  | CY16 Q2
MHV Veteran-Facing Enhancements Phase 2 |  |  | CY16 Q2
MHV Infrastructure and Interface Enhancements Phase 2 |  |  | CY16 Q2
VistA Fee - Separation of Duties | 5 | FB*3.5*165, Build 7 | CY16 Q2
Mobile Health External Development (MHED) Phase 2 | 4.4.0 | Authorization Services | CY16 Q2
Mobile Health External Development (MHED) Phase 2 | 3.4.2 | Health Adapter | CY16 Q2
Mobile Health External Development (MHED) Phase 2 | 1.1.0 | Metrics | CY16 Q2
Mobile Health External Development (MHED) Phase 2 | 2.3.2 | PVS | CY16 Q2
Mobile Development (MD) Phase 2 | 1.0.0 | DS Logon | CY16 Q2