## ROM for HMP Extensions Support
FY15 ROM: Extension of HDR Services to Support Fix The Phone (FtP) Requirements (Estimate Includes Releasing all the way to production including PMAS)
Assumptions: 1. FtP will use SOAP interfaces provided by HDR Service 2. FtP will accept payload in XML format from HDR Service - 4 different payloads each matching a highlevel business need 3. FtP and HDR teams will collaborate to determine the data source from which to obtain the data elements as needed - HDR is currently unable to locate data for 3.3.6 and 3.3.7 in VistA 4. FtP will use IAM/ESR services directly for data related to identity and eligibility 5. FtP requires the HDR services supporting their requirements to be ready for integration testing by June 2015 6. FtP requires HDR services supporting FtP requirements to be deployed to production by July 2015 7. For Requirement 3.5.13 - HDR services will support only 'Advance Directives', 'Clinical Warnings' and 'Restricted/Sensitive record warnings' 8. For Requirement 6.2.2 - FtP will send an authenticated token that can be used by HDR services to obtain an appropriate DUZ to update VistA 9. Integration with MHV for MHV specific data will depend on MHV service availability and approvals (impacts 3.1.7, 3.18 and 3.1.20) - Assuming we can integrate with MHV services for now; this may change if MHV does not have the required interfaces for integration
Activity | Resources | Notes | FTEs | Hous per Week | Weeks | Addtl. Comments
Project Management (VA) |  |  | 0.125 | 5 | 9
Project Management (Contract) |  |  | 0.125 | 5 | 9
Project Planning (Contract) |  |  | 0.125 | 5 | 9
Program Analyst (Contract) |  |  | 0.125 | 5 | 9
Program Facilitation/Admin Analyst (Contract) |  |  | 0.125 | 5 | 9
Architectural Management (Contract) |  |  | 0.25 | 10 | 9
Requirements Management (Contract) |  |  | 1 | 40 | 9
SW Development (Contract) - Service extensions for specific data elements |  |  | 2 | 80 | 9 | To deliver: 3.1.11, 3.1.13, 3.1.15 3.3.1, 3.3.2, 3.3.8, 3.3.9, 3.3.10 3.5.13 If possible: 3.3.6 and 3.3.7
Java Development |  |  | 1 | 40 | 9
Cache Development |  |  | 1 | 40 | 9
SW Development (Contract) - Service extensions for VistA updates |  |  | 2 | 80 | 6 | To deliver: 6.2.2
Java Development |  |  | 1 | 40 | 6
Cache Development |  |  | 1 | 40 | 6
SW Development (Contract) - Integration with MHV Java Oracle Mumps Cache NoSQL |  | Java | 1 | 40 | 6 | To deliver: 3.1.7, 3.1.8, 3.1.20
DBA Support (deployments to DBs in ICL and their verification) (Contract) |  |  | 0.125 | 5 | 3
DBA Development -- release package development, data modeling (Contract) |  |  | 0 | 0 | 0
Configuration Management & Release Deployment (Contract) |  |  | 0.5 | 20 | 3
Load/Perforamnce Test (Contract) |  |  | 1 | 40 | 4
SQA Testing (VA/Contract) - Service extensions for specific data elements |  |  | 2 | 80 | 9 | To test: 3.1.11, 3.1.13, 3.1.15 3.3.1, 3.3.2, 3.3.8, 3.3.9, 3.3.10 3.5.13 If developed, test: 3.3.6 and 3.3.7
SQA Testing (VA/Contract) - Service extensions for VistA updates |  |  | 1 | 40 | 3 | To test: 6.2.2
SQA Testing (VA/Contract) - Integration with MHV |  |  | 1 | 40 | 6 | To test: 3.1.7, 3.1.8, 3.1.20
Technical Services (TSG) (Contract) System Administation (ranging from Oracle upgrade, patching, OS upgrade, backup & recovery, capacity planning, application load testing support) |  |  | 0.25 | 10 | 3
Tech Writing/PMAS/ORR Documentation, Meeting coordination/scribing, documents updates on TSPR and HDR SharePoint (Contract) |  |  | 1 | 40 | 9
TOTAL
SIGNATURE: DATE: