VATS 3.0.x - Information for Deployment/Install/Back out/Rollback

# Dependencies

The following services are required for deployment as part of the entire release package.

| Deployable Artifact Name | Release Number | Build Number | Installation Instructions |
| --- | --- | --- | --- |
| VATS Web | 3.0 |  | Error! Hyperlink reference not valid. Error! Hyperlink reference not valid. Error! Hyperlink reference not valid. |
| VATS Resources | 3.0 |  | Error! Hyperlink reference not valid. Error! Hyperlink reference not valid. |

Note that the Error! Hyperlink reference not valid. references several other dependencies, however, the ones referenced above are the only ones being deployed with VATS 2.2.0

# Timeline

## VATS 3.0 - Next Gen

The deployment and installation is scheduled to run for 3 days, as depicted in the master deployment schedule.

| Task Name | Duration | Start | Finish |
| --- | --- | --- | --- |
| VAOS 4.3.x, SM 2.3.x, VATS 2.2.x | 25 days | Fri 5/11/18 | Fri 6/15/18 |
| Development & Local Testing | 12 days | Fri 5/11/18 | Tue 5/29/18 |
| Integrated VistA Continuous Delivery Sprint | 10 days | Tue 5/15/18 | Tue 5/29/18 |
| Community Care Continuous Delivery Sprint | 10 days | Tue 5/15/18 | Tue 5/29/18 |
| Build Plan Deliverable | 1 day | Fri 5/11/18 | Fri 5/11/18 |
| Sprint Plan Deliverable | 1 day | Tue 5/15/18 | Tue 5/15/18 |
| CD2 Prep |  |  |  |
| Documentation Finalization (CCB Ticket submitted) | 0.5 days | Mon 6/4/18 | Mon 6/4/18 |
| Build Acceptance Form Deliverable | 1 day | Mon 6/4/18 | Tue 6/5/18 |
| PMO upload into Rational | 5 days | Mon 6/4/18 | Mon 6/11/18 |
| Release Readiness Review of Artifacts | 5 days | Mon 6/4/18 | Mon 6/11/18 |
| Installations (007) | 0.63 days | Mon 6/4/18 | Mon 6/4/18 |
| ECE Deploy | 0.5 days | Mon 6/4/18 | Mon 6/4/18 |
| Dev-Int, SQA (NextGen -- VAR) | 1 hr | Mon 6/4/18 | Mon 6/4/18 |
| SQA (PS -- SM) | 1 hr | Mon 6/4/18 | Mon 6/4/18 |
| Formal VA Testing | 9.5 days | Mon 6/4/18 | Fri 6/15/18 |
| SQA testing (high level smoke testing | 2 hrs | Mon 6/4/18 | Mon 6/4/18 |
| SQA testing (running through scripts | 5 days | Mon 6/4/18 | Mon 6/11/18 |
| Production Deployment | 0.13 days | Mon 6/4/18 | Mon 6/4/18 |
| VAR deployment | 1 hr | Mon 6/4/18 | Mon 6/4/18 |
| SM and VATS deployment | 1 hr | Mon 6/4/18 | Mon 6/4/18 |
| Field Testing | 6 days | Tue 6/5/18 | Tue 6/12/18 |

| VAR, SM, VATS | 1 day | Tue 6/5/18 | Tue 6/5/18 |
| --- | --- | --- | --- |
| Defect Log Deliverable | 5 days | Wed 6/6/18 | Tue 6/12/18 |
| Defect Resolution Plan Deliverable | 5 days | Wed 6/6/18 | Tue 6/12/18 |
| Hot Fix #1 | 4 days | Wed 6/6/18 | Mon 6/11/18 |
| Development/ testing | 2 days | Wed 6/6/18 | Thu 6/7/18 |
| Documentation, CCB ticket, Deploy to ECE, Dev-int, SQA | 6 hrs | Fri 6/8/18 | Fri 6/8/18 |
| SQA testing | 1 hr | Fri 6/8/18 | Fri 6/8/18 |
| Beta Deploy | 1 hr | Fri 6/8/18 | Fri 6/8/18 |
| Prod Validation Testing | 1 day | Mon 6/11/18 | Mon 6/11/18 |
| Hot Fix #2 | 4 days | Tue 6/12/18 | Fri 6/15/18 |
| Development/ testing | 2 days | Tue 6/12/18 | Wed 6/13/18 |
| Documentation, CCB ticket, Deploy to ECE, Dev-int, SQA | 6 hrs | Thu 6/14/18 | Thu 6/14/18 |
| SQA testing | 1 hr | Thu 6/14/18 | Thu 6/14/18 |
| Beta Deploy | 1 hr | Thu 6/14/18 | Thu 6/14/18 |
| Prod Validation Testing | 1 day | Fri 6/15/18 | Fri 6/15/18 |
| National Release | 1 day | Fri 6/15/18 | Fri 6/15/18 |

The Site Readiness Assessment section of this document must be completed for all deployments. The PM should tailor these paragraphs according to the characteristics of the project, to answer the following:Site Readiness Assessment

Where is this deployment happening?

In the next gen Environment in MAE

What product, site, or object is the physical recipient of this deployment?

Its a veteran facing mobile application hosted in the MAE Terremark.

Is it happening at physical locations?

NO device or physical location action occurring/required. Its deployed in a shared hosted environment.

Is it happening to devices? Is it happening to desktops? Is it happening to mainframe systems Its being deployed in the MAE

Is there a site readiness checklist available that can be completed prior to installation?

The VAR release team manages and maintains a SharePoint site with training materials, user guide and faqs.

This section discusses the locations that will receive the VAR deployment.

There is a supported facility collection stored in MongoDB, that maintains list of all facilities that can actively use VAR. An export can be obtained to get a most recent list of active facilities.

# Site Preparation

All deployments are handled by the MIS deployment team and are done in the VAMF cloud. There are no action items required by sites for the upgraded version of release package.

The following table describes preparation required by the site prior to deployment.

Table 2: Site Preparation

| Site/Other | Problem/Change Needed | Features to Adapt/Modify to New Product | Actions/Steps | Owner |
| --- | --- | --- | --- | --- |
| N/A |  |  |  |  |

# Resources

All deployments are handled by the MIS deployment team. Technical POC from development team will be available for any required troubleshooting. Coordination occurs through DNS  S CCB ticketing process after required approvals are completed and installation date/time has been scheduled.

Please refer to CCB submission process: Error! Hyperlink reference not valid.

## Technical POC from development team:

| Developer Name/ Point of Contact | Email Address | Phone Number |
| --- | --- | --- |
| Mohamed Khader | Mohamed.Khader@ablevets.com | 703-851-9037 |

Stored Data Backout

For any database backout required in the VAMF Production environment, a DNS  CCB ticket is required to be entered for approvals. Development team will provide DB script tailored to remove the data necessary. Once proper approvals have occurred by the CCB, ticket will be assigned to the Database Team for execution. Please refer to CCB submission process: Error! Hyperlink reference not valid.

Error! Hyperlink reference not valid.Be the first to like this