Community Care Electronic Data Interchange (CCEDI) Teams 4, 5, 6, 7, 8, and 9

Build 3 Plan

CLIN 0008AC (includes

CLIN 0008AF Build Release Planning Package and

CLIN 0008AG Sprint Plan) Department of Veterans Affairs (VA)

Office of Information and Technology (OIT)

September 2017

Version 0.2

Document Version History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| 9/22/2017 | 0.2 | Technical Edits | Loretta Woltz |
| 9/21/2017 | 0.1 | Initial Draft | Lori Spencer and Sam Bridges |

Note: The revision history cycle begins once changes or enhancements are requested after the document has been baselined.

Table of Contents

1.	Introduction ........................................................................................ 1

2.	Build Execution .................................................................................. 1

3.	Scrum Teams ..................................................................................... 2

3.1.  Velocity ............................................................................................................. 2

3.2.  Capacity vs. Plan ............................................................................................. 3

3.3.  Organization Chart........................................................................................... 5

4.	Epics, Sub-Epics and User Stories................................................... 5

5.	User Stories/Backlog ....................................................................... 19

Team 4 HAC Documentation Backlog ............................................................... 19

FPPS Backlog ...................................................................................................... 19

6.	Testing Responsibilities .................................................................. 20

7.	Acceptance Criteria ......................................................................... 20

8.	Schedule ........................................................................................... 21

8.1.  Build 3 Sprint 1............................................................................................... 21

8.2.  Build 3 Sprint 2............................................................................................... 22

8.3.  Build 3 Sprint 3............................................................................................... 23

8.4.  Build 3 Sprint 4............................................................................................... 23

8.5.  Build 3 Sprint 5............................................................................................... 24

8.6.  Build 3 Sprint 6............................................................................................... 25

8.7.  Sprint Ceremonies ......................................................................................... 25

8.8.  Build 4 Planning............................................................................................. 26

9.	Dependencies................................................................................... 26

10. Risks and Issues .............................................................................. 27

10.1.Identified Risks .............................................................................................. 27

10.2.Identified Issues............................................................................................. 27

11. Constraints ....................................................................................... 27

12. Assumptions .................................................................................... 27

13. Definition of Done ............................................................................ 28

13.1.Build 3 Deliverables ....................................................................................... 28

CCEDI Build 3 Plan Approval Signatures.............................................. 29

1.	Introduction

This Build Plan outlines the high-level strategy to be implemented by Favor TechConsulting, LLC (FTC) to successfully manage Community Care (CC) Electronic Data Interchange (EDI) Build 3. This is the third installment of the Fee Payment Processing System (FPPS) Upgrade development, ultimately resulting in the first incremental release of the new FPPS application.

The goal of Build 3 is to complete the first incremental release of the upgraded FPPS application, implement Other Health Insurance (OHI) functionality that is new to FPPS, and complete the functionality that a Read-Only user will be able to utilize. The functionality implemented will expand upon the architecture that was implemented in Build 1 & 2. End-to-End integration will include the frontend and backend servers with a database that is populated with the minimum amount of mock data needed to demonstrate completion of the development effort, until the

actual test or production FPPS database is provided by the Department of Veteran Affairs (VA).

Given the replacement of foundational frameworks and the related requirements for Security, Performance, 508 Compliance, Testing and Reporting, the CCEDI effort is essentially the creation of new enterprise-level claims processing software. This solution will be modern, scalable and extensible. A solid application base will allow more rapid development and deployment of end user screens.

2.	Build Execution

The CCEDI Build 3 Plan runs from September 28, 2017 through December 19, 2017 and includes six (6) sprints of approximately two (2) weeks each. During the build, scrum teams will elaborate, analyze, program, validate, test and build user stories in support of the business owner’s priorities. The prioritization of items in the backlog is captured in the Rational product backlog.

Sprint Teams collaborate to produce and deliver code to the VA for Quality Assurance (QA) and User Acceptance Testing (UAT). Defects found during sprints will be evaluated immediately by the scrum team. Defects that can be resolved within the sprint will be tasked and resolved. FTC will call defects “bugs”.

Defects that cannot be resolved within the sprint will be placed on the Build Backlog to be resolved based upon the business priorities. These defects will be evaluated by the scrum team and estimates will be listed in Rational, then prioritized, and approved by the business. At the end of the two (2) weeks sprint, a build is created and demonstrated. Stories with High and Very High defects will not be considered complete and will not be demonstrated at the end of a sprint. Stories without defects and stories with Low or Medium defects will be demonstrated for acceptance.

During the two-week sprint period, FTC is preparing for building and demonstrating the product. FTC has continuous deployment jobs that help sustain our builds, packaging fixes, and

promoting the code from one environment to the next. FTC keeps control of its versioning and configurations, including preparing test data for testing and fixes.

A retrospective ceremony is used to review and approve the work product completed during the two-week sprint.

3.	Scrum Teams

FTC will accomplish sprint planning based on the following velocity and capacity. Velocity is based upon the team average over previous sprints and will adjust based upon that average throughout the build. Capacity is determined by the team members assigned and their availability during the sprint to accomplish tasks. The final sprint in the build will be for defect repair and hardening.

3.1.  Velocity

The following table illustrates the total number of points completed by each team during Build 2 and the average points per sprint. The velocity from Build 2 is used to plan for Build 3.

| Team | Build 2 Completed Points | Average Per Sprint Points |
| --- | --- | --- |
| Team 4 | 138 | 34.5 |
| Team 5 | 115 | 28.75 |
| Team 6 | 105 | 26.25 |
| Team 7 | 181 | 45.25 |
| Team 8 | 189 | 47.25 |
| Team 9 | 143 | 35.75 |

Figure 1: Build 2 Velocity

3.2.  Capacity vs. Plan

The following table represents the full team capacity (in hours) vs. the planned work per sprint/per team (in hours). Level of Effort (LOE) roles, such as Project Manager and Business Analyst, are spread evenly per user story.

| Sprint 1 (8 days) | Team 4 | Team 5 | Team 6 | Team 7 | Team 8 | Team 9 |
| --- | --- | --- | --- | --- | --- | --- |
| Total Team Capacity | 274 | 292 | 283 | 277 | 277 | 331 |
| Total Rational Capacity | 217 | 208 | 208 | 211 | 211 | 265 |
| Sprint 2 (10 days) | Team 4 | Team 5 | Team 6 | Team 7 | Team 8 | Team 9 |
| Total Team Capacity | 274 | 292 | 283 | 277 | 277 | 331 |
| Total Rational Capacity | 217 | 208 | 208 | 211 | 211 | 265 |

| Sprint 3 (10 days) | Team 4 | Team 5 | Team 6 | Team 7 | Team 8 | Team 9 |
| --- | --- | --- | --- | --- | --- | --- |
| Total Team Capacity | 274 | 292 | 283 | 277 | 277 | 331 |
| Total Rational Capacity | 217 | 208 | 208 | 211 | 211 | 265 |
| Sprint 4 (9 days) | Team 4 | Team 5 | Team 6 | Team 7 | Team 8 | Team 9 |
| Total Team Capacity | 274 | 292 | 283 | 277 | 277 | 331 |
| Total Rational Capacity | 217 | 208 | 208 | 211 | 211 | 265 |
| Sprint 5 (9 days) | Team 4 | Team 5 | Team 6 | Team 7 | Team 8 | Team 9 |
| Total Team Capacity | 274 | 292 | 283 | 277 | 277 | 331 |
| Total Rational Capacity | 217 | 208 | 208 | 211 | 211 | 265 |
| Sprint 6 (10 days) | Team 4 | Team 5 | Team 6 | Team 7 | Team 8 | Team 9 |
| Total Team Capacity | 274 | 292 | 283 | 277 | 277 | 331 |
| Total Rational Capacity | 217 | 208 | 208 | 211 | 211 | 265 |

3.3.  Organization Chart

4.	Epics, Sub-Epics and User Stories

Epic 002 of PCSI Business Requirements Document (BRD) 1.1.4:  As Veteran Health Administration Office of Community Care (VHA CC), I want to upgrade FPPS to meet current security requirements while maintaining existing functionality so that I can continue to use current processes in the system.

Sub-epic 001 of PCSI Technical Reference Model (TRM): “As the VHA CC, I need FPPS to utilize TRM-compliant technologies, so that I can achieve ATO.”

Sub-epic 002 of PCSI TRM: “As the VHA CC, I need FPPS to maintain existing end-user functionality, so that there is no loss in business continuity due to end-user retraining.”

| Epic | Story | RM# | Description | Build | Sprint |
| --- | --- | --- | --- | --- | --- |
| 001 | n/a |  | As a HAC system developer, I need to create technical documentation so that I can understand how the system works. | Epic | Epic |
| 001 | Sub Epic | 937824 | As a MUMPS developer I need to update the CP&E MUMPS Routine Matrix to describe HAC system MUMPS routines so that I can develop code against the as-is state | Sub Epic | Sub Epic |
| 001 | 001.01.14 | 938143 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFADR*documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.15 | 938144 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA001-CHMFA019 documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.16 | 938145 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA01A - CHMFA01K documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.17 | 938147 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA020 - CHMFA029 and CHMFA02* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.18 | 938149 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA030-CHMFA036 documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.19 | 938150 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA050 - CHMFA059 and CHMFA05A- CHMFA05E documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.20 | 938151 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA070 - CHMFA079 and CHMFA07A- | B3 | S1 |

| Epic | Story | RM# | Description | Build | Sprint |
| --- | --- | --- | --- | --- | --- |
|  |  |  | CHMFA07E documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. |  |  |
| 001 | 001.01.21 | 938152 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA100-CHMFA137 documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.22 | 938154 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA140 - CHMFA149 documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.23 | 938155 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA14A - CHMFA14G, CHMFA14M- CHMFA14V documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.24 | 938156 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA150 - CHMFA159 documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.25 | 938158 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA160 - CHMFA167 documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.26 | 938159 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA17* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.27 | 938160 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA18* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.28 | 938161 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA19* documented in the CP&E | B3 | S1 |

| Epic | Story | RM# | Description | Build | Sprint |
| --- | --- | --- | --- | --- | --- |
|  |  |  | MUMPS Routine Matrix so that I can develop code against the as-is state. |  |  |
| 001 | 001.01.29 | 938162 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA200 - CHMFA209 documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.30 | 938164 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA210 - CHMFA219 documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.31 | 938165 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA22* and CHMFA30* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.32 | 938166 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA40* and CHMFA50* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.33 | 938167 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA60* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.34 | 938169 | As a MUMPS developer I need the In Processing/EDI routines prefixed with CHMFA70* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S1 |
| 001 | 001.01.35 | 938171 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHMFA8* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.36 | 938173 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCPU1, CHGCPU, and CHGCU100- CHGCU109 documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |

| Epic | Story | RM# | Description | Build | Sprint |
| --- | --- | --- | --- | --- | --- |
| 001 | 001.01.37 | 938174 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCU11* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.38 | 938175 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCU12* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.39 | 938176 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCU13* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.40 | 938177 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCU14* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.41 | 938179 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCU15* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.42 | 938180 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCU16* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.43 | 938181 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCU17* and CHGCU18* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.44 | 938182 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCU1MS and CHGCU2* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.45 | 938183 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCU3* documented in the CP&E | B3 | S2 |

| Epic | Story | RM# | Description | Build | Sprint |
| --- | --- | --- | --- | --- | --- |
|  |  |  | MUMPS Routine Matrix so that I can develop code against the as-is state. |  |  |
| 001 | 001.01.46 | 938184 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCU4* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.47 | 938185 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCU5* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.48 | 938186 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCU60* and CHGU61* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.49 | 938190 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCU62* and CHGU7* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.50 | 938191 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCU8* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.51 | 938192 | As a MUMPS developer I need the Claim Edit - Queue routines prefixed with CHGCUSHW and CHGCUU* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.52 | 938193 | As a MUMPS developer I need the Claim Sort routines prefixed with CHMFSORT and CMFSR0* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.53 | 938194 | As a MUMPS developer I need the Claim Sort routines prefixed with CHMFSR1* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |

| Epic | Story | RM# | Description | Build | Sprint |
| --- | --- | --- | --- | --- | --- |
| 001 | 001.01.54 | 938195 | As a MUMPS developer I need the Claim Sort routines prefixed with CHMFSR2* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.55 | 938196 | As a MUMPS developer I need the Claim Sort routines prefixed with CHMFSR2N* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.56 | 938197 | As a MUMPS developer I need the Claim Sort routines prefixed with CHMFSRR* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.57 | 938198 | As a MUMPS developer I need the Claim Sort routines prefixed with CHMFSRT* documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.58 | 938199 | As a MUMPS developer I need the Check Data routines prefixed with CHFCD001- CHFCD010 documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.59 | 938200 | As a MUMPS developer I need the Check Data routines prefixed with CHFCD011- CHFCD021 documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.60 | 938201 | As a MUMPS developer I need the Check Data routines prefixed with CHFCD100 - CHFCD133 documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.61 | 938202 | As a MUMPS developer I need the Check Data routines prefixed with CHFCD2*, CHFCDDRV and CHFCDUTL documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | S2 |
| 001 | 001.01.70 | 938203 | As a MUMPS developer I need Claim Queues/Claim Edit routines documented in | B3 | Future |

| Epic | Story | RM# | Description | Build | Sprint |
| --- | --- | --- | --- | --- | --- |
|  |  |  | the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. |  |  |
| 001 | 001.01.100 | 938204 | As a MUMPS developer I need Business Rules routines documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | Future |
| 001 | 001.01.200 | 938205 | As a MUMPS developer I need Benefit/Payment Calc routines documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | Future |
| 001 | 001.01.300 |  | As a MUMPS developer I need Business Rules routines documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | Future |
| 001 | 001.01.400 | 938206 | As a MUMPS developer I need Payment/Batch Processing routines documented in the CP&E MUMPS Routine Matrix so that I can develop code against the as-is state. | B3 | Future |
| 001 | 001.02 Sub Epic | 937763 | As a HAC system developer, I need Interface Control Documents (ICDs) between HAC systems so that I can understand interface requirements between systems in the HAC. | Sub Epic | Sub Epic |
| 001 | 001.02.01 | 936674 | As a MUMPS developer I need a CP&E 837 File ICD so that I can understand the interface requirements for the inbound 837 file into CP&E. | Sub Epic | Sub Epic |
| 001 | 001.02.02 | 938208 | As a MUMPS developer I need a CP&E 835 File ICD so that I can understand the interface requirements for the outbound 835 file from CP&E. | B3 | S2 |
| 001 | 001.02.03 | 938209 | As a MUMPS developer I need a CP&E H(v) File ICD so that I can understand the interface requirements for the outbound H(v) file from CP&E to FMS. | B3 | Future |
| 001 | 001.04 Sub Epic | 936506 | As a HAC system developer, I need to create or update high level HAC system workflow diagrams so that I can develop code against the as-is state. | Sub Epic | Sub Epic |
| 001 | 001.04.01 | 936507 | As a HAC system developer, I need to update the high level CP&E Claims Process | B3 | S2 |

| Epic | Story | RM# | Description | Build | Sprint |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Workflow Document so I can develop code against the as-is state. |  |  |
| 005 | Sub Epic | 931023 | As an FPPS Claims Processor I need to have OHI Data available for review within the FPPS application so that I can make accurate decisions on claim adjudication. | Sub Epic | Sub Epic |
| 005 | 005.1 | 931024 | As an FPPS Claims Processor, I need to have an OHI Tab on the Claims Detail View with an indication of OHI Data so that I know when a claim has associated OHI Data. | B3 | S1 |
| 005 | 005.2 | 931025 | As an FPPS Claims Processor, I need to be able to choose the primary payer with a payer ID so that I can review OHI data on a per payer basis. | B3 | S1 |
| 005 | 005.3 | 931026 | As an FPPS Claims Processor, I need to be able to choose the secondary payer with a payer ID so that I can review OHI data on a per payer basis. | B3 | S1 |
| 005 | 005.4 | 931027 | As an FPPS Claims Processor, I need to be able to choose the tertiary payer with a payer ID so that I can review OHI data on a per payer basis. | B3 | S1 |
| 005 | 005.5 | 931029 | As an FPPS Claims Processor, I need to be able to choose the quaternary payer with a payer ID so that I can review OHI data on a per payer basis. | B3 | S1 |
| 005 | 005.6 | 931030 | As an FPPS Claims Processor, I need to be able to see a prior payers name so that I can review the payer's high level claim information at a glance. | B3 | S2 |
| 005 | 005.7 | 936716 | As an FPPS Claims Processor, I need to be able to see a prior payers group name so that I can review the payer's high level claim information at a glance. | B3 | S2 |
| 005 | 005.8 | 936717 | As an FPPS Claims Processor, I need to be able to see the subscriber name of the | B3 | S2 |

| Epic | Story | RM# | Description | Build | Sprint |
| --- | --- | --- | --- | --- | --- |
|  |  |  | veteran based on prior payer information so that I can review the payer's high level claim information at a glance. |  |  |
| 005 | 005.9 | 936718 | As an FPPS Claims Processor, I need to be able to see the subscriber id of the veteran based on prior payer information so that I can review the payer's high level claim information at a glance. | B3 | S2 |
| 005 | 005.10 | 936719 | As an FPPS Claims Processor, I need to be able to see the secondary subscriber id of the veteran based on prior payer information so that I can review the payer's high level claim information at a glance. | B3 | S2 |
| 033 | Sub Epic | 909736 | As an FPPS Admin, I need a Claim Disapproval page, so I that I can disapprove claims. | Sub Epic | Sub Epic |
| 033 | 033.6 | 911630 | As an FPPS Admin, I need to be able to select a Reason code (RARC) for the Claim Disapproval so that the reason for the claim disapproval can be communicated to the provider. | B3 | S1 |
| 033 | 033.7 | 911631 | As an FPPS Admin, I need to have a button that initiates a claim reroute so that I can execute a claim reroute on the Claim Reroute Page. | B3 | S1 |
| 033 | 033.8 | 911632 | As an FPPS Admin, I need to see a claim reroute history for a selected claim so that I can be aware of prior rerouting of a claim. | B3 | S1 |
| 043 | Sub Epic | 911031 | As an FPPS Admin, I need a Station Maintenance - Add Page, so I that I can add station information. | Sub Epic | Sub Epic |
| 043 | 043.8 | 911082 | As a FPPS Admin, I need to be able to Allow Rerouting for the station so that I can add a station to a VISN. | B3 | S1 |
| 043 | 043.9 | 911106 | As a FPPS Admin, I need to be able to save the station that has been entered on the form so that I can add a station to a VISN. | B3 | S1 |

| Epic | Story | RM# | Description | Build | Sprint |
| --- | --- | --- | --- | --- | --- |
| 043 | 043.10 | 911107 | As a FPPS Admin, I need to be able to cancel the station that has been entered on the form so that I can avoid adding a station to a VISN. | B3 | S1 |
| 044 | Sub Epic | 911112 | As an FPPS Admin, I need a Station Maintenance - Edit Page, so I that I can edit station information. | Sub Epic | Sub Epic |
| 044 | 044.1 | 911113 | As a FPPS Admin, I need to be able to edit a Station so that I can edit a station. | B3 | S1 |
| 044 | 044.2 | 911140 | As a FPPS Admin, I need to be able to select an existing VISN so that I can edit a station. | B3 | S1 |
| 044 | 044.3 | 911141 | As a FPPS Admin, I need to be able to select a Type from the following list so that I can edit a station: OMNH - OUTPATIENT CLINIC/NURSING HOME OM - OUTPATIENT CLINIC RO - REGIONAL OFFICE CEM - CEMETERY HOSP - HOSPITAL CTR - VET CENTER CLIN - CLINIC FAC - VA FACILITY (Stations) FACS - Facility (Other) VISNOF - VISN Operations Office | B3 | S1 |
| 044 | 044.4 | 911142 | As a FPPS Admin, I need to be able to edit a Short Name for the station so that I can edit a station. | B3 | S2 |
| 044 | 044.5 | 911144 | As a FPPS Admin, I need to be able to edit a Name for the station so that I can edit a station. | B3 | S2 |
| 044 | 044.6 | 911170 | As a FPPS Admin, I need to be able to edit an Aged Definition for the station so that I can edit a station. | B3 | S2 |

| Epic | Story | RM# | Description | Build | Sprint |
| --- | --- | --- | --- | --- | --- |
| 044 | 044.7 | 911171 | As a FPPS Admin, I need to be able to edit a Patent Station to the station so that I can edit a station. | B3 | S2 |
| 044 | 044.8 | 911172 | As a FPPS Admin, I need to be able to Allow Rerouting for the station so that I can edit a station. | B3 | S2 |
| 045 | Sub Epic | 911182 | As an FPPS Admin, I need a Station Maintenance - View Page, so I that I can view station information. | Sub Epic | Sub Epic |
| 045 | 045.1 | 911183 | As a FPPS Admin, I need to be able to view a Station number so that I can view pertinent station information. | B3 | S2 |
| 045 | 045.2 | 911184 | As a FPPS Admin, I need to be able to view an existing VISN so that I can view pertinent station information. | B3 | S2 |
| 045 | 045.3 | 911185 | As a FPPS Admin, I need to be able to view a station Type so that I can view pertinent station information. | B3 | S2 |
| 045 | 045.4 | 911186 | As a FPPS Admin, I need to be able to view a Short Name for the station so that I can view pertinent station information. | B3 | S2 |
| 045 | 045.5 | 911188 | As a FPPS Admin, I need to be able to view a Name for the station so that I can view pertinent station information. | B3 | S2 |
| 045 | 045.6 | 911190 | As a FPPS Admin, I need to be able to view an Aged Definition for the station so that I can view pertinent station information. | B3 | S2 |
| 045 | 045.7 | 911191 | As a FPPS Admin, I need to be able to add a Parent Station to the station so that I can view pertinent station information. | B3 | S2 |
| 047 | Sub Epic | 911235 | As an FPPS Admin, I need an Add Zip Code Page, so I that I can add a zip code to a station. | Sub Epic | Sub Epic |
| 047 | 047.1 | 911236 | As a FPPS Admin, I need to be able to add a zip code so that I can add a zip code to a station. | B3 | S1 |

| Epic | Story | RM# | Description | Build | Sprint |
| --- | --- | --- | --- | --- | --- |
| 047 | 047.2 | 911237 | As a FPPS Admin, I need to be able to indicate whether a zip code is active or inactive so that I can add a zip code to a station. | B3 | S2 |
| 047 | 047.3 | 911238 | As a FPPS Admin, I need to be able to add a FIPS County Code so that I can add a zip code to a station. | B3 | S2 |
| 047 | 047.4 | 911239 | As a FPPS Admin, I need to be able to add a FIPS State Code so that I can add a zip code to a station. | B3 | S2 |
| 047 | 047.5 | 911240 | As a FPPS Admin, I need to be able to add an Urban Indicator so that I can add a zip code to a station. | B3 | S2 |
| 047 | 047.6 | 911242 | As a FPPS Admin, I need to be able to save the form so that I can add a zip code to a station. | B3 | S2 |
| 047 | 047.7 | 911244 | As a FPPS Admin, I need to be able to cancel the form so that I can cancel adding a zip code to a station. | B3 | S2 |
| 058.10 | Sub Epic | 933162 | As a FPPS Admin, I need to have a Read Only User Role so that FPPS users have minimum appropriate permissions. | Sub Epic | Sub Epic |
| 058.10 | 058.10.1 | 933164 | As a Read Only User, I need the ability to access the Home Page, so that I review claim counts of my assigned station. | B3 | S1 |
| 058.10 | 058.10.3 | 936761 | As a Read Only User, I need the ability to access the Search Claims Page, so that I can Search Claims. | B3 | S1 |
| 058.10 | 058.10.4 | 936766 | As a Read Only User, I need to have a claim navigation menu with an option for Search Claims so that I can access the claims pages allowed by my role | B3 | S1 |
| 058.10 | 058.10.5 | 936767 | As a Read Only User, I need to have a reports navigation menu with an option for claim reports so that I can access reports allowed by my account role. | B3 | S1 |

| Epic | Story | RM# | Description | Build | Sprint |
| --- | --- | --- | --- | --- | --- |
| 058.10 | 058.10.6 | 934654 | As a Read Only User, I need the ability to access the Claim Detail Page, so that I can View Claim Details. | B3 | S1 |
| 058.10 | 058.10.7 | 936768 | As a Read Only User, I need to have a tools navigation menu with an option for medical and diagnosis code lookup tools so that I can access tools allowed by my account role. | B3 | S2 |
| 058.10 | 058.10.8 | 934656 | As a Read Only User, I need the ability to Print claims, so that I can review a claims printed form. | B3 | S2 |
| 058.10 | 058.10.9 | 934657 | As a Read Only User, I need the ability to access the Diagnosis Code Lookup, so that I can lookup Diagnosis Codes. | B3 | S2 |
| 058.10 | 058.10.10 | 934659 | As a Read Only User, I need the ability to access the Medical Code Lookup, so that I can lookup Medical Codes. | B3 | S2 |
| 058.10 | 058.10.11 | 934661 | As a Read Only User, I need the ability to access the Claims Completed Report, so that I can review the Claims Completed Report. | B3 | S2 |
| 063 | Sub Epic | 929698 | As an FPPS Admin, I need a Manual Reconciliation - Out of System Payment Page, so that I can apply payments to claim line items when manually reconciling claims. | Sub Epic | Sub Epic |
| 063 | 063.7 | 929706 | As an FPPS Admin, I need to be able to select a group code for a selected adjustment so that I can apply claim adjustments to a claim. | B3 | S1 |
| 063 | 063.8 | 929707 | As an FPPS Admin, I need to be able to select a Claim Adjustment Reason Code (CARC) for a selected adjustment so that I can apply claim adjustments to a claim. | B3 | S1 |
| 063 | 063.9 | 929708 | As an FPPS Admin, I need to be able to select up to 2 Remittance Advice Remark Codes (RARC) for a selected adjustment so that I can apply claim adjustments to a claim. | B3 | S1 |

| Epic | Story | RM# | Description | Build | Sprint |
| --- | --- | --- | --- | --- | --- |
| 063 | 063.10 | 929793 | As an FPPS Admin, I need to be able to clear the RARC Selection for a selected adjustment so that I can make a new RARC selection and apply claim adjustments to a claim. | B3 | S1 |
| 063 | 063.11 | 929794 | As an FPPS Admin, I need to be able to see a selection summary of selected claim adjustment information so that I can ensure accuracy of claim adjustments prior to application to a claim. | B3 | S2 |
| 063 | 063.12 | 929795 | As an FPPS Admin, I need to be able to submit payment info so that I can apply a claim payment and claim adjustments to a claim. | B3 | S2 |
| 063 | 063.13 | 929796 | As an FPPS Admin, I need to be able to cancel claim payment and claim adjustment entry so that I can avoid erroneous data entry on a claim. | B3 | S2 |

5.	User Stories/Backlog

The Rational Product backlogs contain all prioritized and accepted user stories. Backlog items can be reprioritized by the VA at any time. The current backlog is maintained and available within Rational.

Team 4 HAC Documentation Backlog

FPPS Backlog

6.	Testing Responsibilities

| FTC (Developer) | Party Responsible |
| --- | --- |
| Unit/Product/Component Testing | FTC System Quality Assurance (SQA) |
| Build Verification Testing | FTC SQA |
| Functional Testing | FTC SQA |
| Performance/Load Testing | FTC SQA |
| Integration/System Testing | FTC SQA |
| Regression Testing | FTC SQA |
| Section 508 Compliance Testing | FTC SQA |
| Security Testing | FTC SQA |
| HAC SQA | Party Responsible |
| Installation Testing/Build Verification | Health Administration Center (HAC) Quality Assurance (QA) |
| Security Testing | HAC QA |
| Performance/Load Testing | HAC QA |
| User Acceptance Testing (UAT) | HAC QA |
| User Functional Testing (UFT) | VHA CC |

7.	Acceptance Criteria

•	Final Development Code Files, Compiled Code and supporting documentation are

checked into the project’s Rational repository.

•	100% traceability in Rational

•	Updated Requirements Traceability Matrix (RTM) and executed test scripts as per plan in Rational

•	508 Compliant Checklists

8.	Schedule

The Build schedule is described in the sections below. Story Points are estimated prior to elaboration using standard Agile principals and may not reflect actual hours estimated during sprint planning.

8.1.	Build 3 Sprint 1

| CCEDI Build 3 |  | 56 Days |  | Thur 9/28/17 |  |  | Tue 12/19/17 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Task Name |  | Duration |  | Start |  |  | Finish |
| Build 3 Sprint 1 |  | 8 Days |  | Wed 9/28/17 |  |  | Tue 10/10/17 |
| Team | Description | Epic | Sub Epic |  | User Story | Story Points | Hours |
| Team 4 | CP&E MUMPS Routine Matrix: 837 routines: Stories 001.01 938143, 938144, 938145, 938147, 938149, 938150, 938151, 938152, 938154, 938156, 938158, 938159, 938160, 938161, 938162, 938164, 938165, 835 ICD: Story 001.02 938166 Claims Process Flow: Story 001.04 938169 |  |  |  |  | 39 8 8 | 217 |
| Team 5 | Add Station Page: Stories 043.8, 043.9, 043.10 Modify Station Page: Stories 044.1, 044.2, 044.3 |  |  |  |  | 16 21 | 208 |
| Team 6 | OHI Data: Stories 005.1, 005.2, 005.3, 005.4, 005.5 |  |  |  |  | 40 | 208 |
| Team 7 | Read-Only User Role: Stories 058.10.1, 058.10.3, 058.10.4, 058.10.5, 058.10.6 |  |  |  |  | 40 | 211 |
| Team 8 | Out of System Payment Page: Stories 063.7, 063.8, 063.9, 063.10 |  |  |  |  | 36 | 211 |
| Team 9 | Reroute Page: Stories 033.6, 033.7, 033.8 Station Add Zip Code Page: Story 047.1 |  |  |  |  | 23 8 | 265 |

| D: Sprint Plan | Fri 9/8/17 |  |  |
| --- | --- | --- | --- |
| Sprint Milestone/Ceremony | Hours |  | Date |
| Sprint Kickoff/Planning (All Teams) | 4-6 Hrs |  | 9/28/17 |
| Sprint 1 Backlog Grooming (All Teams) | 1 Hr |  | 10/4/17 |
| Sprint 1 Sprint Review (All Teams) | 1 Hr |  | 10/10/17 |

8.2.	Build 3 Sprint 2

Build 3 Sprint 2	10 Days	Wed 10/11/17	Tue 10/24/17

Team	Description	Epic	Sub

Epic

Team 4	CP&E MUMPS Routine Matrix: IP/EDI Screens: Stories 001.01 938171,

938173, 938174, 938175, 938176

938177, 938179, 938180, 938181,

938182, 938183, 938184, 938185

938186, 938190, 938191, 938192,

938193, 938194, 938195, 938196,

938198, 938199, 938200, 938201

938202

835 ICD: Story 001.01 936674

User Story	Story

Points

41

8

Hours

217

Claims Process Workflow: Story

001.04 936507

Team 5	Modify Station Page:  Stories 44.4,

44.5, 44.6, 44.7, 44.8

8

31

208

Team 6	OHI Data:  Stories 005.6, 005.7, 005.8,

005.9, 005.10

40	208

Team 7	Read-Only User Role:  Stories

058.10.7, 058.10.8, 058.10.9,

058.10.10, 058.10.11

40	211

Team 8	Out of System Payment Page:  Stories

063.11, 063.12, 063.13

View Station Page:  Stories 045.1,

045.2, 045.3, 045.4, 045.5, 045.6,

045.7

13	211

21

Team 9	Station Add Zip Code Page:   Stories

047.2, 047.3, 047.4, 047.5, 047.6,

047.7

29	265

Build 3 Sprint 2	10 Days	Wed 10/11/17	Tue 10/24/17

Team	Description	Epic	Sub

Epic

User Story	Story

Points

Hours

Total:

D: Sprint Plan	Fri 9/22/17

Sprint Milestone/Ceremony	Hours	Date

Sprint Kickoff/Planning (All Teams)	4-6 Hrs	10/11/17

Sprint 2 Backlog Grooming (All Teams)	1 Hr	10/18/17

Sprint 2 Sprint Review (All Teams)	1 Hr	10/24/17

8.3.	Build 3 Sprint 3

| Build 3 Sprint 3 |  | 10 Days |  | Wed 10/25/17 |  |  | Tue 11/7/17 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Team | Description | Epic | Sub Epic |  | User Story | Story Points | Hours |
| Team 4 |  |  |  |  |  | 57 | 217 |
| Team 5 |  |  |  |  |  | 32 | 208 |
| Team 6 |  |  |  |  |  | 32 | 208 |
| Team 7 |  |  |  |  |  | 32 | 211 |
| Team 8 |  |  |  |  |  | 32 | 211 |
| Team 9 |  |  |  |  |  | 32 | 265 |
| D: Sprint Plan |  | Fri 10/6/17 |  |  |  |  |  |
| Sprint Milestone/Ceremony |  | Hours |  |  |  |  | Date |
| Sprint Kickoff/Planning (All Teams) |  | 4-6 Hrs |  |  |  |  | 10/25/17 |
| Sprint 3 Backlog Grooming (All Teams) |  | 1 Hr |  |  |  |  | 11/1/17 |
| Sprint 3 Sprint Review (All Teams) |  | 1 Hr |  |  |  |  | 11/7/17 |

8.4.	Build 3 Sprint 4

| Build 3 Sprint 4 | 9 Days | Wed 11/8/17 | Tue 11/21/17 |
| --- | --- | --- | --- |

| Team | Description | Epic | Sub Epic |  | User Story | Story Points | Hours |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Team 4 |  |  |  |  |  | 57 | 217 |
| Team 5 |  |  |  |  |  | 32 | 208 |
| Team 6 |  |  |  |  |  | 32 | 208 |
| Team 7 |  |  |  |  |  | 32 | 211 |
| Team 8 |  |  |  |  |  | 32 | 211 |
| Team 9 |  |  |  |  |  | 32 | 265 |
| D: Sprint Plan |  | Fri 10/20/17 |  |  |  |  |  |
| Sprint Milestone/Ceremony |  | Hours |  |  |  |  | Date |
| Sprint Kickoff/Planning (All Teams) |  | 4-6 Hrs |  |  |  |  | 11/8/17 |
| Sprint 4 Backlog Grooming (All Teams) |  | 1 Hr |  |  |  |  | 11/15/17 |
| Sprint 4 Sprint Review (All Teams) |  | 1 Hr |  |  |  |  | 11/21/17 |

8.5.	Build 3 Sprint 5

| Build 3 Sprint 5 |  | 9 Days |  | Wed 11/22/17 |  |  | Tue 12/5/17 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Team | Description | Epic | Sub Epic |  | User Story | Story Points | Hours |
| Team 4 |  |  |  |  |  | 57 | 217 |
| Team 5 |  |  |  |  |  | 32 | 208 |
| Team 6 |  |  |  |  |  | 32 | 208 |
| Team 7 |  |  |  |  |  | 32 | 211 |
| Team 8 |  |  |  |  |  | 32 | 211 |
| Team 9 |  |  |  |  |  | 32 | 265 |
| D: Sprint Plan |  | Fri 11/4/17 |  |  |  |  |  |
| Sprint Milestone/Ceremony |  | Hours |  |  |  |  | Date |
| Sprint Kickoff/Planning (All Teams) |  | 4-6 Hrs |  |  |  |  | 11/22/17 |
| Sprint 5 Backlog Grooming (All Teams) |  | 1 Hr |  |  |  |  | 11/29/17 |

| Sprint 5 Sprint Review (All Teams) | 1 Hr |  | 12/5/17 |
| --- | --- | --- | --- |

8.6.	Build 3 Sprint 6

Build 3 Sprint 6	10 Days	Wed 12/6/17	Tue 12/19/17

Team	Description	Epic	Sub

Epic

User

Story

Story

Points

Hours

Team 4	57	217

Team 5	208

Team 6	208

Team 7	211

Team 8	211

Team 9	265

D: Sprint Plan	Fri 11/18/17

Sprint Milestone/Ceremony	Hours	Date

Sprint Kickoff/Planning (All Teams)	4-6 Hrs	12/6/17

Sprint 6 Backlog Grooming (All Teams)	1 Hr	12/13/17

Sprint 6 Sprint Review (All Teams)	1 Hr	12/19/17

8.7.	Sprint Ceremonies

| Meeting Name | Date | Time | Duration | Attendees |
| --- | --- | --- | --- | --- |
| Standing Sprint Ceremonies/Meetings |  |  |  |  |
| Sprint Kickoff Veteran-focused Integration Process (VIP) Sprint Planning | First Day of Sprint | Various (Wed) | 1 Hr per Team | FTC Team Reps VA PM VA PO VA BA |
| Daily Scrum | Daily | Mornings | 10 Mins | FTC Team Members VA Representatives Welcome |
| Scrum of Scrums | Daily | 11:30 | 30 Mins | FTC Team Reps VA PM VA PO VA BA |

| Meeting Name | Date | Time | Duration | Attendees |
| --- | --- | --- | --- | --- |
| Sprint Backlog Grooming/Planning | Bi-Weekly | 3:00 Wednes- day | 1 Hr | FTC Team Reps VA PM VA PO VA BA |
| Sprint Review/Demo | At Sprint End | 2:00 Tuesday | 1 Hr | FTC Team Reps VA PM VA PO VA BA |

8.8.	Build 4 Planning

| Standing Build Planning Sessions/Meetings/Deliverables |  |  |  |  |
| --- | --- | --- | --- | --- |
| Build 4 Planning | Timeframe | Date | Duration | Attendees |
| Build Plan 4 Backlog Review | Within 3 Weeks Prior to Build Start | 12/13/17 | 1 Hr | FTC Team Reps VA PM VA PO VA BA |
| Build Plan 4 Planning Session | Within 3 Weeks Prior to Build Start | 12/13/17 | 1 Hr | FTC Team Reps VA PM VA PO VA BA |
| Build Plan 4 Review | Within 2 Weeks Prior to Build Start | 12/20/17 | 1 Hr | FTC Team Reps VA PM VA PO VA BA |
| Build Plan 4 Architecture Review | Within 2 Weeks Prior to Build Start | 12/20/17 | 1 Hr | FTC Team Reps VA PM VA PO VA BA |

9.	Dependencies

•	HAC Full Time Employee (FTE) resource will be required to answer specific technical questions regarding HAC idiosyncrasies and specific implementation issues.

10.	Risks and Issues

10.1.	Identified Risks

•	IF SQA resources knowledgeable of the HAC systems and processes are not assigned at the Program level THEN the Program and Projects under the Program run the risk of not being able to support the systems owned under the Help Administration Product Enhancement (HAPE) portfolio in a timely manner to ensure claims for veterans and their dependents are processed. POC: Jim Reich

10.2.	Identified Issues

•	SINCE: a Fee Payment Processing System (FPPS) development database has not been provided due to lack of resources, a connection cannot be established between the application running on the Enterprise Development Environment (EDE) web servers and the database, THEN: requests for individual access to the database cannot be submitted, the project schedule will slip and contractor resources will need to be reassigned. POC: Eric Hickam

•	SINCE: there currently is no clear plan on how to keep the EPMO resources that are required for the project, which has led to sudden and unprepared reassignments of essential personnel without a knowledge transfer, THEN: this will cause significant delays, hindering the project from moving forward due to the lack of key personnel. POC: Jim Reich

11.	Constraints

•	The application must be 508 compliant.

•	TRM compliant framework(s) must be used.

•	All fundamental functionality and page-flow must be maintained.

•	User Interface (UI)/User eXperience (UX) page structure/visual layout will be maintained, but will use a modern, 508 compliant UI framework.

12.	Assumptions

•	FPPS must be secure, scalable and extensible so that it aligns with modern enterprise architectures. This will accommodate an increase in throughput (~100% increase), as well as provide a platform for an expansion in functionality.

•	FPPS is currently operating under a temporary ATO, with tools not on the TRM; the new

FPPS will require a new ATO.

•	Approved security infrastructure will be implemented throughout application and its layers.

13.	Definition of Done

Below is an enumeration of items to be agreed upon as the definition of Done for Purchased Care

(PC) System Integrity Build 2. Sprint work product deliverables are listed above.

•	Final Development Code Files, Compiled Code and supporting documentation are

checked into the project’s Rational repository (0008AM).

•	100% traceability in Rational

•	Creation of all the iterative Release Package (008AP) documentation associated with Build 3 required for a future release to production (e.g. Installation Guide and User Manual)

•	Updated RTM and executed test scripts as per plan in Rational

•	In following the Agile process defects found during a sprint that cannot be resolved within the sprint are placed in the build backlog and will be worked in the next sprint and the technical reasons why the User Story with defects could not be finished within the sprint will be explained during the sprint retrospective.

13.1.	Build 3 Deliverables

•	All completed Sprint work product deliverables are checked into the project’s Rational

repository to be updated and maintained as project moves forward.

•	Build 3 Interconnection Security Agreement/Memorandum of Understanding

(ISA/MOU) (0008AD)

•	Build 3 Release Planning Package (0008AF)

•	Build 3 Sprint Plans (0008AG)

•	Build 3 Sprint Burn down and Velocity charts (0008AH)

•	Build 3 508 Certification (0008AK)

•	Build 3 Acceptance Form (0008AN)

•	Build 3 Release Package (0008AP)

CCEDI Build 3 Plan Approval Signatures

Title: Community Care Electronic Data Interchange Build 3 Plan with Sprints 1 and 2 detail.

Signed: Derek Creary, Project Manager	Date:

Signed: James Reich, Project Manager	Date:

Signed: Brian Matthews, Product Owner	Date:

Signed: Terry Tanner, Product Owner	Date:

9/22/17

Signed: Lori Spencer, Product Lead	Date: