## Kidney Build 3 - Build Plan
Id | Summary | Group | Work Item Type | Implements Requirement | Related Test Case | Status
362383 | Accommodate unique Kidney data in the registry Database. | Kidney Build 3 - Sprint 13 | Epic | Accommodate unique Kidney data in the registry Database. |  | In Progress
362385 | Accommodate unique data requirements in Kidney Disease Registry. | Kidney Build 3 - Sprint 13 | Epic | Accommodate unique data requirements in Dialysis Registry. |  | In Progress
362409 | As the Kidney Disease Registry, I want to provide lab test information defined as routine or emergency so that the information can be used for analysis. | Kidney Build 3 - Sprint 13 | Story | As the Dialysis Registry, I want to provide lab test information defined as routine or emergency so that the information can be used for analysis. | 165955: VIRP - KD - As the Dialysis Registry, I want to provide lab test information defined as routine or emergency so that the information can be used for analysis. | Done
371489 | Create a User Interface to access and manage Kidney Disease Registry Data. | Kidney Build 3 - Sprint 13 | Epic |  |  | In Progress
361959 | Develop within the GUI tools to capture disparity in renal care delivery. | Kidney Build 3 - Sprint 13 | Epic | Develop within the GUI tools to capture disparity in renal care delivery. |  | Ready for Review
361969 | As the Kidney Disease Registry, I want to provide data elements on disparity of renal care delivery across all facilities so that I can carry out an adequate analysis. | Kidney Build 3 - Sprint 13 | Story | As the Dialysis Registry, I want to provide data elements on disparity of renal care delivery across all facilities so that I can carry out an adequate analysis. |  | In Progress
361963 | As a User, I want to be able to report on data related to renal care delivery at multiple VA sites, so that I can Identify the differences in disease identification and care given. | Kidney Build 3 - Sprint 13 | Story | As a User, I want to be able to report on data related to renal care delivery at multiple VA sites, so that I can Identify the differences in disease identification and care given. |  | In Progress
362284 | Track Veterans with Kidney Disease through the care process. | Kidney Build 3 - Sprint 13 | Epic | Track Veterans with Kidney Disease through the care process. |  | Ready for Review
362327 | As a User, I need to track patient's kidney function chronologically through the care process so that I can better understand patient outcomes. | Kidney Build 3 - Sprint 13 | Story | As a User, I need to track patient's kidney function chronologically through the care process so that I can better understand patient outcomes. | 165999: VIRP - KD - As a User, I need to track patient's kidney function chronologically through the care process so that I can better understand patient outcomes | Done
362328 | As a User, I need to track patient's proteinuria chronologically through the care process so that I can better understand patient outcomes. | Kidney Build 3 - Sprint 13 | Story | As a User, I need to track patient's proteinuria chronologically through the care process so that I can better understand patient outcomes. | 165998: VIRP - KD - As a User, I need to track patient's proteinuria chronologically through the care process so that I can better understand patient outcomes | Done
362325 | As a User, I need to track patient outcomes chronologically through the care process so that I can better understand patient outcomes. | Kidney Build 3 - Sprint 13 | Story | As a User, I need to track patient outcomes chronologically through the care process so that I can better understand patient outcomes. | 166000: VIRP - KD - As a User, I need to track patient outcomes chronologically through the care process so that I can better understand patient outcomes | Done
362383 | Accommodate unique Kidney data in the registry Database. | Kidney Build 3 - Sprint 14 | Epic | Accommodate unique Kidney data in the registry Database. |  | In Progress
362386 | Develop back-end database system for kidney disease. | Kidney Build 3 - Sprint 14 | Epic | Develop back-end database system for kidney disease. |  | Ready for Review
362389 | As the System Administrator, I want to create a kidney disease database/registry using the VIRP wizard so that the unique kidney disease data requirements can be accommodated. | Kidney Build 3 - Sprint 14 | Story | As the System Administrator, I want to create a kidney dialysis database/registry using the CRSe wizard so that the unique kidney disease data requirements can be accommodated. | 165962: VIRP - KD - As the System Administrator, I want to create a kidney dialysis database/registry using the CRSe wizard so that the unique kidney disease data requirements can be accommodated. | Done
362385 | Accommodate unique data requirements in Kidney Disease Registry. | Kidney Build 3 - Sprint 14 | Epic | Accommodate unique data requirements in Dialysis Registry. |  | In Progress
362400 | As the Kidney Disease Registry, I want to limit the ICD and CPT codes received from a source to those identifying dialysis, ESRD, transplant, and other kidney related procedures so that the database only contains kidney related data. | Kidney Build 3 - Sprint 14 | Story | As the Dialysis Registry, I want to limit the ICD and CPT codes received from a source to those identifying dialysis, ESRD, transplant, and other kidney related procedures so that the database only contains kidney related data. | 165958: VIRP - KD - As the Dialysis Registry, I want to limit the ICD and CPT codes received from a source to those identifying dialysis, ESRD, transplant, and other kidney related procedures so that the database only contains kidney related data. | Ready for Review
646693 | Add LOINC as Cohort Filter Criteria | Kidney Build 3 - Sprint 14 | Task |  |  | Ready for Review
646695 | Add Stop Code as Cohort Filter Criteria | Kidney Build 3 - Sprint 14 | Task |  |  | Ready for Review
362403 | As the Kidney Disease Registry, I want to provide comorbid diagnosis and procedure codes so that the information can be used for analysis. | Kidney Build 3 - Sprint 14 | Story | As the Dialysis Registry, I want to provide comorbid diagnosis and procedure codes so that the information can be used for analysis. | 165957: VIRP - KD - As the Dialysis Registry, I want to provide comorbid diagnosis and procedure codes so that the information can be used for analysis. | Done
362397 | NF - As the Kidney Disease Registry, I want to identify dialysis procedures provided in inpatient and outpatient settings for both VA facility and fee-based provider types so that unique data is provided about a patient. | Kidney Build 3 - Sprint 14 | Story | As the Dialysis Registry, I want to identify dialysis procedures provided in inpatient and outpatient settings for both VA facility and fee-based provider types so that unique data is provided about a patient. | 165959: VIRP - KD - As the Dialysis Registry, I want to identify dialysis procedures provided in inpatient and outpatient settings for both VA facility and fee-based provider types so that unique data is provided about a patient. | Ready for Review
362396 | As the Kidney Disease Registry, I want a multiracial indicator to denote where more than one race is indicated so that ethnicity data can be evaluated and consolidated into one value. | Kidney Build 3 - Sprint 14 | Story | As the Dialysis Registry, I want a multiracial indicator to denote where more than one race is indicated so that ethnicity data can be evaluated and consolidated into one value. | 165960: VIRP - KD - As the Dialysis Registry, I want a multiracial indicator to denote where more than one race is indicated so that ethnicity data can be evaluated and consolidated into one value. | Done
362391 | As the Kidney Disease Registry I want to identify ESRD diagnoses provided in inpatient and outpatient settings for both VA facility and fee-based provider types so that unique data is provided related to a patient. | Kidney Build 3 - Sprint 14 | Story | As the Dialysis Registry I want to identify ESRD diagnoses provided in inpatient and outpatient settings for both VA facility and fee-based provider types so that unique data is provided related to a patient. | 165961: VIRP - KD - As the Dialysis Registry I want to identify ESRD diagnoses provided in inpatient and outpatient settings for both VA facility and fee-based provider types so that unique data is provided related to a patient. | Done
362409 | As the Kidney Disease Registry, I want to provide lab test information defined as routine or emergency so that the information can be used for analysis. | Kidney Build 3 - Sprint 14 | Story | As the Dialysis Registry, I want to provide lab test information defined as routine or emergency so that the information can be used for analysis. | 165955: VIRP - KD - As the Dialysis Registry, I want to provide lab test information defined as routine or emergency so that the information can be used for analysis. | Done
362406 | NF - As the Kidney Disease Registry, I want to provide information related to Emergency Room (ER) visits so that the information can be used for analysis. | Kidney Build 3 - Sprint 14 | Story | As the Dialysis Registry, I want to provide information related to Emergency Room (ER) visits so that the information can be used for analysis. | 165956: VIRP - KD - As the Dialysis Registry, I want to provide information related to Emergency Room (ER) visits so that the information can be used for analysis. | Ready for Review
646710 | Include requested KDR data in VIRP framework | Kidney Build 3 - Sprint 14 | Task |  |  | Ready for Review
362214 | Create a National/Enterprise Level VHA Kidney Disease Registry | Kidney Build 3 - Sprint 14 | Epic | Create a National/Enterprise Level VHA Dialysis Registry |  | In Progress
362221 | Positive patient ID/Authentication using the VA authoritative source (MVI) | Kidney Build 3 - Sprint 14 | Epic | Positive patient ID/Authentication using the VA authoritative source (MVI) |  | Ready for Review
362269 | NF - As the Kidney Disease Registry, I want to combine all records for the same patient into one record, so that I can view and report on all data for the patient. | Kidney Build 3 - Sprint 14 | Story | As the Dialysis Registry, I want to combine all records for the same patient into one record, so that I can view and report on all data for the patient. | 166010: VIRP - KDR - As the Dialysis Registry, I want to combine all records for the same patient into one record, so that I can view and report on all data for the patient | Ready for Review
362266 | NF - As a User, I want patients to be positively identified by VA Identity Management so that I have confidence that incoming data is mapped to the correct patient. | Kidney Build 3 - Sprint 14 | Story | As a User, I want patients to be positively identified by VA Identity Management so that I have confidence that incoming data is mapped to the correct patient. | 166011: VIRP - KDR - As a User, I want patients to be positively identified by VA Identity Management so that I have confidence that incoming data is mapped to the correct patient | Ready for Review
362216 | Automated feeds from VA sources. | Kidney Build 3 - Sprint 14 | Epic | Automated feeds from other sources. |  | Ready for Review
362252 | As the Kidney Disease Registry, I want other data from the Corporate Data Warehouse (CDW) so that the Veteran health care record data is accurate and complete in the Kidney Disease Registry. | Kidney Build 3 - Sprint 14 | Story | As the Dialysis Registry, I want other data from the Corporate Data Warehouse (CDW) so that the Veteran health care record data is accurate and complete in the Dialysis Registry. |  | Done
362253 | As the Kidney Disease Registry, I want other data from VistA so that the Veteran health care record data is accurate and complete in the Kidney Disease Registry. | Kidney Build 3 - Sprint 14 | Story | As the Dialysis Registry, I want other data from VistA so that the Veteran health care record data is accurate and complete in the Dialysis Registry. | 166027: VIRP - KDR - As the Dialysis Registry, I want other data from VistA so that the Veteran health care record data is accurate and complete in the Dialysis Registry | Done
362249 | As the Dialysis Registry, I want data from the patient's electronic health record contained in CDW and Vista, so that the Veteran health care record data is accurate and complete in the Dialysis Registry. | Kidney Build 3 - Sprint 14 | Story | As the Dialysis Registry, I want data from the patient's electronic health record contained in CDW and Vista, so that the Veteran health care record data is accurate and complete in the Dialysis Registry. | 166254: VIRP - KDR - As the Dialysis Registry, I want data from the patient's electronic health record contained in CDW and Vista, so that the Veteran health care record data is accurate and complete in the Dialysis Registry | Done
362279 | Include Diagnostic Procedures and treatments related to kidney disease in the registry data. | Kidney Build 3 - Sprint 14 | Epic | Include Diagnostic Procedures and treatments related to kidney disease in the dialysis registry data. |  | Ready for Review
362336 | As a User, I want to view data by diagnostic procedure and treatments related to a patient so that I can analyze the data. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to view data by diagnostic procedure and treatments related to a patient so that I can analyze the data. | 165990: VIRP - KD - As a User, I want to view data by diagnostic procedure and treatments related to a patient so that I can analyze the data. | Done
362335 | As a User, I want to report on data by diagnostic procedure and treatments related to a patient so that I can analyze the data. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to report on data by diagnostic procedure and treatments related to a patient so that I can analyze the data. | 165992: VIRP - KD - As a User, I want to report on data by diagnostic procedure and treatments related to a patient so that I can analyze the data. | Done
362344 | Hemodialysis data in the Kidney Disease Registry. | Kidney Build 3 - Sprint 14 | Epic | Hemodialysis data in the Dialysis Registry. |  | Ready for Review
362351 | NF - As a User, I want hemodialysis data from all available sources to be available in the Kidney Disease Registry so that I can provide better statistical analysis. | Kidney Build 3 - Sprint 14 | Story | As a User, I want hemodialysis data from all available sources to be available in the Dialysis Registry so that I can provide better statistical analysis. | 165974: VIRP - KD - As a User, I want hemodialysis data from all available sources to be available in the Dialysis Registry so that I can provide better statistical analysis. | Ready for Review
362350 | As a User, I need to track data related to hemodialysis by series for a patient so that I can better monitor outcomes. | Kidney Build 3 - Sprint 14 | Story | As a User, I need to track data related to hemodialysis by series for a patient so that I can better monitor outcomes. | 165975: VIRP - KD - As a User, I need to track data related to hemodialysis by series for a patient so that I can better monitor outcomes. | Ready for Review
362349 | Peritoneal dialysis data in the Kidney Disease Registry. | Kidney Build 3 - Sprint 14 | Epic | Peritoneal dialysis data in the Dialysis Registry. |  | Ready for Review
362354 | As a User, I want Peritoneal Dialysis data from all available sources to be available in the Kidney Disease Registry so that I can provide better statistical analysis. | Kidney Build 3 - Sprint 14 | Story | As a User, I want Peritoneal Dialysis data from all available sources to be available in the Dialysis Registry so that I can provide better statistical analysis. | 165972: VIRP - KD - As a User, I want Peritoneal Dialysis data from all available sources to be available in the Dialysis Registry so that I can provide better statistical analysis. | Done
362353 | NF - As a User, I need to track data related to Peritoneal Dialysis chronologically by patient so that I can better monitor outcomes. | Kidney Build 3 - Sprint 14 | Story | As a User, I need to track data related to Peritoneal Dialysis chronologically by patient so that I can better monitor outcomes. | 165973: VIRP - KD - As a User, I need to track data related to Peritoneal Dialysis chronologically by patient so that I can better monitor outcomes. | Ready for Review
362280 | Incorporate mortality and morbidity data from all other VIRP Registries in the Kidney Disease Registry data. | Kidney Build 3 - Sprint 14 | Epic | Incorporate mortality and morbidity data from all other CRSe Registries in the Dialysis Registry data. |  | In Progress
362324 | As a User, I want to view mortality and morbidity data from other VIRP registries from within the Kidney Disease Registry so that I produce accurate statistics based on the data collected. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to view mortality and morbidity data from other CRSe registries from within the Dialysis Registry so that I produce accurate statistics based on the data collected. | 166001: VIRP - KD - As a User, I want to view mortality and morbidity data from other CRSe registries from within the Dialysis Registry so that I produce accurate statistics based on the data collected. | In Progress
362322 | As a User, I want to report on mortality and morbidity data from all VIRP registries so that I can determine if there is a link to Kidney disease. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to report on mortality and morbidity data from all CRSe registries so that I can determine if there is a link to Kidney disease. | 166002: VIRP - KDR - As a User, I want to report on mortality and morbidity data from all CRSe registries so that I can determine if there is a link to Kidney disease. | In Progress
362287 | Transplant data in the Kidney Disease Registry. | Kidney Build 3 - Sprint 14 | Epic | Transplant data in the Dialysis Registry. |  | Ready for Review
362338 | As a User, I want transplant data from available sources to be available in the Kidney Disease Registry so that I can provide better statistical analysis. | Kidney Build 3 - Sprint 14 | Story | As a User, I want transplant data from available sources to be available in the Dialysis Registry so that I can provide better statistical analysis. | 165976: VIRP - KD - As a User, I want transplant data from available sources to be available in the Dialysis Registry so that I can provide better statistical analysis. | Ready for Review
362337 | As a User, I need to track data related to transplants chronologically by patient so that I better monitor outcomes. | Kidney Build 3 - Sprint 14 | Story | As a User, I need to track data related to transplants chronologically by patient so that I better monitor outcomes. | 165989: VIRP - KD - As a User, I need to track data related to transplants chronologically by patient so that I better monitor outcomes. | Ready for Review
361880 | Support nationally recognized references and terminology standards in Kidney Disease Registry data. | Kidney Build 3 - Sprint 14 | Epic | Support nationally recognized references and terminology standards in Dialysis Registry data. |  | Ready for Review
361891 | As a User, I want all data fields (clinical and non-clinical) that have national standards to display a patient s information using standard data when associated to the patient so that more consistent health statistics can be viewed. | Kidney Build 3 - Sprint 14 | Story | As a User, I want all data fields (clinical and non-clinical) that have national standards to display a patient s information using standard data when associated to the patient so that more consistent health statistics can be viewed. |  | Ready for Review
361890 | As a User, I want all reports that contain data fields (clinical and non-clinical) with national standards to provide a patients information using the appropriate standard data when associated to the patient record so that more consistent health statistics are available. | Kidney Build 3 - Sprint 14 | Story | As a User, I want all reports that contain data fields (clinical and non-clinical) with national standards to provide a patients information using the appropriate standard data when associated to the patient record so that more consistent health s... |  | Ready for Review
361927 | Contain report data for creating specialized reports. | Kidney Build 3 - Sprint 14 | Epic | Contain report data for creating specialized reports. |  | Ready for Review
361929 | As a User, I want to report on timelines when the data has defined dates and data points so that I can better monitor a patient s status. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to report on timelines when the data has defined dates and data points so that I can better monitor a patient s status. |  | Done
361933 | As a User, I want to report on a patient s treatment when data points exist so that I can better monitor a patient s status. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to report on a patient s treatment when data points exist so that I can better monitor a patient s status. |  | Done
361930 | As a User, I want to report on a patients follow up care when data points exist so that I can better monitor a patient s status. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to report on a patients follow up care when data points exist so that I can better monitor a patient s status. |  | Done
361931 | As a User, I want to report on patient outcomes when data points exist so that I can better monitor a patient s care. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to report on patient outcomes when data points exist so that I can better monitor a patient s care. |  | Done
362347 | Incorporate other VIRP registries data into the Kidney Disease Registry. | Kidney Build 3 - Sprint 14 | Epic | Incorporate other CRSe registries data into the Dialysis Registry. |  | Ready for Review
362375 | As a User, I want to view and report on kidney disease related data captured by other VIRP registries so that I have all information available for analysis. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to view and report on kidney disease related data captured by other CRSe registries so that I have all information available for analysis. | 165965: VIRP - KD - As a User, I want to view and report on kidney disease related data captured by other CRSe registries so that I have all information available for analysis. | Ready for Review
362217 | Automated process metric data Feeds | Kidney Build 3 - Sprint 14 | Epic | Automated process metric data Feeds |  | Ready for Review
362255 | As an administrator, I want to view process metrics captured by VIRP related to Dialysis from all data sources, so that I can monitor data reliability. | Kidney Build 3 - Sprint 14 | Story | As an administrator, I want to view process metrics captured by CRSe related to Dialysis from all data sources, so that I can monitor data reliability. | 166026: VIRP - KDR - As an administrator, I want to view process metrics captured by CRSe related to Dialysis from all data sources, so that I can monitor data reliability | Done
362223 | Receive data from VHA Kidney Disease Centers | Kidney Build 3 - Sprint 14 | Epic | Receive data from VHA Dialysis Centers |  | In Progress
362259 | As the Kidney Disease Registry, I want to include data from VHA Dialysis Centers in the Kidney Disease Registry so that I have a complete picture of the patient s current treatment. | Kidney Build 3 - Sprint 14 | Story | As the Dialysis Registry, I want to include data from VHA Dialysis Centers in the Dialysis Registry so that I have a complete picture of the patient s current treatment. | 166012: VIRP - KDR - As the Dialysis Registry, I want to include data from VHA Dialysis Centers in the Dialysis Registry so that I have a complete picture of the patient s current treatment | In Progress
709264 | Verify access to CDW DOEX schema and Dialysis Dashboard tables | Kidney Build 3 - Sprint 14 | Task |  |  | New
362258 | As a user, I want to incorporate data from VHA Dialysis Centers in reports so that the reports have the most up to date treatment information. | Kidney Build 3 - Sprint 14 | Story | As a user, I want to incorporate data from VHA Dialysis Centers in reports so that the reports have the most up to date treatment information. | 166025: VIRP - KDR - As a user, I want to incorporate data from VHA Dialysis Centers in reports so that the reports have the most up to date treatment information | In Progress
362277 | Collect scheduling and follow up action information from available sources. | Kidney Build 3 - Sprint 14 | Epic | Collect scheduling and follow up action information from available sources. |  | Ready for Review
362331 | As a User I want to view both past appointments and scheduled future appointments related to kidney disease so that I can better monitor the care given to patients. | Kidney Build 3 - Sprint 14 | Story | As a User I want to view both past appointments and scheduled future appointments related to kidney disease so that I can better monitor the care given to patients. | 165996: VIRP - KD - As a User I want to view both past appointments and scheduled future appointments related to kidney disease so that I can better monitor the care given to patients. | Ready for Review
362333 | As a User, I want to be able to identify when an appointment was missed, so that I can better track a patient status. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to be able to identify when an appointment was missed, so that I can better track a patient status. | 165994: VIRP - KD - As a User, I want to be able to identify when an appointment was missed, so that I can better track a patient status. | Ready for Review
362332 | As a user I want to view follow up related data so that I can better monitor the care given to patients. | Kidney Build 3 - Sprint 14 | Story | As a user I want to view follow up related data so that I can better monitor the care given to patients. | 165995: VIRP - KD - As a user I want to view follow up related data so that I can better monitor the care given to patients. | Ready for Review
371489 | Create a User Interface to access and manage Kidney Disease Registry Data. | Kidney Build 3 - Sprint 14 | Epic |  |  | In Progress
361905 | Develop a user interface to display and analyze data. | Kidney Build 3 - Sprint 14 | Epic | Develop a user interface to display and analyze data. |  | Ready for Review
361910 | As a User, I want an interface where data is displayed so that I can see patient data from the registry | Kidney Build 3 - Sprint 14 | Story | As a User, I want an interface where data is displayed so that I can see patient data from the registry |  | Done
361907 | As a User, I want to be able to extract patient data so that I can use the relevant data for analysis | Kidney Build 3 - Sprint 14 | Story | As a User, I want to be able to extract patient data so that I can use the relevant data for analysis |  | Done
361912 | As a User, I want to be able to export reports so that can see relevant data for analysis. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to be able to export reports so that can see relevant data for analysis. |  | Done
361959 | Develop within the GUI tools to capture disparity in renal care delivery. | Kidney Build 3 - Sprint 14 | Epic | Develop within the GUI tools to capture disparity in renal care delivery. |  | Ready for Review
361969 | As the Kidney Disease Registry, I want to provide data elements on disparity of renal care delivery across all facilities so that I can carry out an adequate analysis. | Kidney Build 3 - Sprint 14 | Story | As the Dialysis Registry, I want to provide data elements on disparity of renal care delivery across all facilities so that I can carry out an adequate analysis. |  | In Progress
361963 | As a User, I want to be able to report on data related to renal care delivery at multiple VA sites, so that I can Identify the differences in disease identification and care given. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to be able to report on data related to renal care delivery at multiple VA sites, so that I can Identify the differences in disease identification and care given. |  | In Progress
362058 | Provide Sort and Filter capability when viewing report in the GUI. | Kidney Build 3 - Sprint 14 | Epic | Provide Sort and Filter capability when viewing report in the GUI. |  | In Progress
362101 | As a User, I want to sort a view a report in the GUI either ascending or descending so that I can view the data I need. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to sort a view a report in the GUI either ascending or descending so that I can view the data I need. |  | Done
362064 | As a User, I want to filter a view of reports in the GUI so that I can view the data I need. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to filter a view of reports in the GUI so that I can view the data I need. |  | In Progress
362092 | As a User, I want to export data in a format that can be used by statistical software so that I can provide more detailed statistical information when needed. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to export data in a format that can be used by statistical software so that I can provide more detailed statistical information when needed. |  | In Progress
362110 | As a User, I want to view national results organized by Zip Code so that I can view data by geographic location. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to view national results organized by Zip Code so that I can view data by geographic location. |  | Ready for Review
362105 | As a User, I want to view national results organized by City so that I can view data by geographic location. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to view national results organized by City so that I can view data by geographic location. |  | Ready for Review
362108 | As a User, I want to view national results organized by State so that I can see data nationally. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to view national results organized by State so that I can see data nationally. |  | Ready for Review
362098 | As a User, I want to report on utilization of services so that I can better identify improvement opportunities. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to report on utilization of services so that I can better identify improvement opportunities. |  | Done
362107 | As a User, I want to view national results organized by Region so that I can see data nationally. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to view national results organized by Region so that I can see data nationally. |  | Ready for Review
362095 | As a User, I want to report on services provided to one or more patients so that I can track continuity of care. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to report on services provided to one or more patients so that I can track continuity of care. |  | Done
362079 | As a user, I want to able to identify if the treatment facility was a VA facility or a Care in the Community facility | Kidney Build 3 - Sprint 14 | Story | As a user, I want to able to identify if the treatment facility was a VA facility or a Care in the Community facility |  | New
362283 | Record tracking data via the user interface. | Kidney Build 3 - Sprint 14 | Epic | Record tracking data via the user interface. |  | Ready for Review
362330 | As a Read/Write User, I want to enter tracking data for a patient so that a more completed picture of the patients care is available. | Kidney Build 3 - Sprint 14 | Story | As a Read/Write User, I want to enter tracking data for a patient so that a more completed picture of the patients care is available. | 165997: VIRP - KD - As a Read/Write User, I want to enter tracking data for a patient so that a more completed picture of the patients care is available. | Done
362284 | Track Veterans with Kidney Disease through the care process. | Kidney Build 3 - Sprint 14 | Epic | Track Veterans with Kidney Disease through the care process. |  | Ready for Review
362327 | As a User, I need to track patient's kidney function chronologically through the care process so that I can better understand patient outcomes. | Kidney Build 3 - Sprint 14 | Story | As a User, I need to track patient's kidney function chronologically through the care process so that I can better understand patient outcomes. | 165999: VIRP - KD - As a User, I need to track patient's kidney function chronologically through the care process so that I can better understand patient outcomes | Done
362328 | As a User, I need to track patient's proteinuria chronologically through the care process so that I can better understand patient outcomes. | Kidney Build 3 - Sprint 14 | Story | As a User, I need to track patient's proteinuria chronologically through the care process so that I can better understand patient outcomes. | 165998: VIRP - KD - As a User, I need to track patient's proteinuria chronologically through the care process so that I can better understand patient outcomes | Done
362325 | As a User, I need to track patient outcomes chronologically through the care process so that I can better understand patient outcomes. | Kidney Build 3 - Sprint 14 | Story | As a User, I need to track patient outcomes chronologically through the care process so that I can better understand patient outcomes. | 166000: VIRP - KD - As a User, I need to track patient outcomes chronologically through the care process so that I can better understand patient outcomes | Done
362371 | Track veterans that have been screened for kidney disease. | Kidney Build 3 - Sprint 14 | Epic | Track veterans that have been screened for kidney disease. |  | Ready for Review
362363 | As a User, I want to view the date veterans were screened for kidney disease. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to view the date veterans were screened for kidney disease. | 165968: VIRP - KD - As a User, I want to view the date veterans were screened for kidney disease. | Done
362365 | As a User, I want to view the results of a veteran s kidney disease screening. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to view the results of a veteran s kidney disease screening. | 165966: VIRP - KD - As a User, I want to view the results of a veteran s kidney disease screening. | Done
362362 | As a User, I want to report kidney disease screenings so that the continuity of care can be managed more efficiently. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to report kidney disease screenings so that the continuity of care can be managed more efficiently. | 165969: VIRP - KD - As a User, I want to report kidney disease screenings so that the continuity of care can be managed more efficiently. | Done
362202 | Create end user tools to share with other users. | Kidney Build 3 - Sprint 14 | Epic | Create end user tools to share with other users. |  | Ready for Review
362200 | As a User, I want to be able to create customized views of data that can be shared with other users so that data is presented in a more usable format. | Kidney Build 3 - Sprint 14 | Story | As a User, I want to be able to create customized views of data that can be shared with other users so that data is presented in a more usable format. | 166278: VIRP - KDR - As a User, I want to be able to create customized views of data that can be shared with other users so that data is presented in a more usable format | Ready for Review