## Transplant Build 3 - Build Plan
Id | Summary | Plan Parent ID | Group
316380 | 1.0 The system shall provide the ability to manage data elements/fields throughout the registry |  | Transplant Build 3 - Sprint 13
315276 | 1.10 As NSO staff, I need to be notified about potential transplant patients that need to | 316380 | Transplant Build 3 - Sprint 13
629955 | US025.01.01 NSO staff members must be notified when patient information indicates that the patient may have had a transplant outside the VHA that is not already represented in the Registry. | 315276 | Transplant Build 3 - Sprint 13
315283 | 1.5 As a VHA provider, I want to be notified via email if my patient does not appear in registry | 316380 | Transplant Build 3 - Sprint 13
629950 | US005.01.01 User will need access to email in order to receive notifications and user should also have an administrative capability to determine if an email is undeliverable or repeated emails go unread so that follow-up outside the registry can occur to determine alternate means of contact regarding the potential candidate. | 315283 | Transplant Build 3 - Sprint 13
315285 | 1.3 As a VHA provider, I need to be able to view, create, and update transplant records so the registry has accurate and up-to-date information. | 316380 | Transplant Build 3 - Sprint 13
315592 | 1.4 As a VHA provider, I need to be able to view and edit transplant registry records. | 316380 | Transplant Build 3 - Sprint 13
316385 | 3.0 The system shall allow interface with other systems. |  | Transplant Build 3 - Sprint 13
315594 | 3.5 As a VHA provider, I need the transplant registry to be updated with (graft failure) | 316385 | Transplant Build 3 - Sprint 13
629963 | US014.01.01 When the patient outcome information of (graft failure) is updated in TRACER, the transplant registry must be updated to ensure accurate information. | 315594 | Transplant Build 3 - Sprint 13
315601 | 3.2 As a VHA provider, I need the transplant registry to be updated with the accurate information | 316385 | Transplant Build 3 - Sprint 13
629960 | US011.01.01 When the transplant occurrence information is updated in TRACER the transplant registry must be updated in order to view accurate information. | 315601 | Transplant Build 3 - Sprint 13
316380 | 1.0 The system shall provide the ability to manage data elements/fields throughout the registry |  | Transplant Build 3 - Sprint 14
315273 | 1.7 As a VHA provider, I want to be able to perform a nightly task that searches for | 316380 | Transplant Build 3 - Sprint 14
629952 | US007.01.01 User must be able to perform a nightly task search for potential transplant registry candidates based on provided criteria to trigger notification alerts. | 315273 | Transplant Build 3 - Sprint 14
315283 | 1.5 As a VHA provider, I want to be notified via email if my patient does not appear in registry | 316380 | Transplant Build 3 - Sprint 14
315289 | 1.8 As a VHA provider, I need to be able to search and filter the dashboard results by various | 316380 | Transplant Build 3 - Sprint 14
315592 | 1.4 As a VHA provider, I need to be able to view and edit transplant registry records. | 316380 | Transplant Build 3 - Sprint 14
315635 | 1.2 As a VHA provider, I need to access transplant registry from CPRS and update the registry | 316380 | Transplant Build 3 - Sprint 14
629949 | US002.01.01 Ability to launch the Transplant registry from within CPRS through a link or tools menu option (to be determined). | 315635 | Transplant Build 3 - Sprint 14
316385 | 3.0 The system shall allow interface with other systems. |  | Transplant Build 3 - Sprint 14
315594 | 3.5 As a VHA provider, I need the transplant registry to be updated with (graft failure) | 316385 | Transplant Build 3 - Sprint 14
629963 | US014.01.01 When the patient outcome information of (graft failure) is updated in TRACER, the transplant registry must be updated to ensure accurate information. | 315594 | Transplant Build 3 - Sprint 14