## VIRP Build 3 - Build Plan
Id | Summary | Group | Work Item Type | Implements Requirement | Related Test Case | Status
635435 | VIRP_SQA Test Environment is extremely slow resulting with a error message | VIRP Build 3 | Task |  |  | Invalid
635442 | VIRP_Build 2_SQA Test Environment_ All CRS References should now state VIRP | VIRP Build 3 | Task |  |  | Invalid
635457 | VIRP_Build_2_SQA Test Environment- Requesting VIRP Name to be Conspicuous on the Home Page (Heading) | VIRP Build 3 | Task |  |  | Invalid
635493 | VIRP_Build_2_SQA Test Environment _Increase the number of patients listed/view in Patients table | VIRP Build 3 | Task |  |  | Invalid
645721 | VIRP Framework Data - Mouse over code to display data definition | VIRP Build 3 | Task |  |  | New
656558 | Providers (SStaff_SStaff) are not loading | VIRP Build 3 | Task |  |  | Done
659241 | WASA Vulnerability 6 - Server Side Requet Forgery | VIRP Build 3 | Task |  |  | New
659242 | WASA Vulnerability 7 - Web Application is Vulnerable to Cross-Site Request Forgery (CSRF) | VIRP Build 3 | Task |  |  | New
659244 | WASA Vulnerability 8 - Web Application uses known Weak Transport Layer Security | VIRP Build 3 | Task |  |  | New
667161 | Install Visual Studio 2015.3 on DEV/SQA DB servers | VIRP Build 3 | Task |  |  | New
724322 | VIRP - KDR - Report>KDR>Patient Lab Information - View Report button does not load anything on the first click | VIRP Build 3 | Defect |  | 170083: VIRP-KDR-As a User I want to filter a view of reports in the GUI so that I can view the data I need... | New
724370 | VIRP - KDR - Export - Report>KDR>Patient Lab Information - CSV export column names are different | VIRP Build 3 | Defect |  | 170065: VIRP-KDR-As a User I want to export data in a format that can be used by statistical software so that I can provide more detailed statistical information when needed... | New
574586 | Non Functional Requirements | VIRP Build 3 | Epic | 919118: Non Functional Requirements |  | In Progress
574919 | P-010: Defining Performance Metrics | VIRP Build 3 | Story | 638259: P-010: Defining Performance Metrics | 161559: VIRP_NF_Defining Performance Metrics | New
574920 | P-020: Transaction Processing Performance | VIRP Build 3 | Story | 638262: P-020: Transaction Processing Performance | 161534: VIRP_NF_Transaction Processing Performance | New
574921 | P-030: Concurrent User Capacity | VIRP Build 3 | Story | 638263: P-030: Concurrent User Capacity | 161581: VIRP_NF_Concurrent User Capacity | New
574922 | P-040: Scalability and Maintaining Required Performance | VIRP Build 3 | Story | 638266: P-040: Scalability and Maintaining Required Performance | 161505: VIRP_NF_Scalablity and Maintaining Required Performance | New
574923 | P-050: Scalability and Supporting Additional Registries | VIRP Build 3 | Story | 638269: P-050: Scalability and Supporting Additional Registries |  | Implemented
574924 | P-060: Scalability to Increase Transactions, Concurrent Users, and ETLs | VIRP Build 3 | Story | 638271: P-060: Scalability to Increase Transactions, Concurrent Users, and ETLs |  | New
574925 | P-070: User Response Time | VIRP Build 3 | Story | 638272: P-070: User Response Time | 162655: VIRP - User Response Time | New
574926 | P-080: ETL Execution Time | VIRP Build 3 | Story | 638273: P-080: ETL Execution Time | 161517: VIRP - NF - ETL Execution Time | Done
574880 | DST-040: Production Database Upload | VIRP Build 3 | Story | 638370: REP-040: Graphical Report Creation | 163006: VIRP NF_Production Database Upload | Done
574882 | DST-060: Individual Patient ETL Execution | VIRP Build 3 | Story | 638222: DST-060: Individual Patient ETL Execution |  | Done
574881 | DST-050: Data-staging Environment Usage | VIRP Build 3 | Story | 638219: DST-050: Data-staging Environment Usage | 161775: VIRP_NF_Data Staging Environment Usage | Done
574883 | ERR-010: Error Handling and Logging | VIRP Build 3 | Story | 638223: ERR-010: Error Handling and Logging | 161771: VIRP_NF_Error Handling and Logging | Done
574884 | ERR-020: Distinguishing Between Errors and Tracing Events | VIRP Build 3 | Story | 638224: ERR-020: Distinguishing Between Errors and Tracing Events | 162613: VIRP_NF_Distinguishing Between Errors and Tracing Events | Done
574885 | ETL-010: Maximized Use of Common ETLs | VIRP Build 3 | Story | 638225: ETL-010: Maximized Use of Common ETLs | 160258: VIRP Default ETL Schedule | Done
574887 | ETL-030: ETL Error Handling | VIRP Build 3 | Story | 638227: ETL-030: ETL Error Handling | 162579: VIRP_NF_ETL Error Handling | Done
574886 | ETL-020: Consolidating ETL Processes | VIRP Build 3 | Story | 638226: ETL-020: Consolidating ETL Processes | 161747: VIRP_NF_Consolidating ETL Processes | Done
574888 | ETL-040: ETL Logging, Tracking, and Monitoring | VIRP Build 3 | Story | 638228: ETL-040: ETL Logging, Tracking, and Monitoring | 161767: VIRP_NF_ETL Logging Tracking and Monitoring | Done
574889 | ETL-050: ETL Status Notification Capability | VIRP Build 3 | Story | 638229: ETL-050: ETL Status Notification Capability | 160258: VIRP Default ETL Schedule | Done
574890 | ETL-060: ETL Status Notification List | VIRP Build 3 | Story | 638230: ETL-060: ETL Status Notification List | 160145: VIRP - ETL Status Notification List | Done
574891 | ETL-070: ETL Status Dashboard | VIRP Build 3 | Story | 638231: ETL-070: ETL Status Dashboard |  | Done
574892 | ETL-080: ETL Status Reporting Information | VIRP Build 3 | Story | 638232: ETL-080: ETL Status Reporting Information | 161746: VIRP_NF_ETL Status Reporting Information | Done
574894 | ETL-100: Referral Data Format | VIRP Build 3 | Story | 638234: ETL-100: Referral Data Format | 161778: VIRP_NF_Referral Data Format | Done
574893 | ETL-090: Standard Terminology Services from CDW | VIRP Build 3 | Story | 638233: ETL-090: Standard Terminology Services from CDW | 161786: VIRP_NF_Standard Terminology Services from CDW | Done
574895 | ETL-110: Multiple Registry Referrals | VIRP Build 3 | Story | 638236: ETL-110: Multiple Registry Referrals |  | Done
574896 | ETL-120: Referral Criteria Match Indicator Flag | VIRP Build 3 | Story | 638237: ETL-120: Referral Criteria Match Indicator Flag |  | Done
574897 | ETL-130: Subsequent/Duplicate Referral Classification | VIRP Build 3 | Story | 638238: ETL-130: Subsequent/Duplicate Referral Classification |  | Done
574898 | ETL-140: Subsequent Referral Properties | VIRP Build 3 | Story | 638239: ETL-140: Subsequent Referral Properties |  | Done
574899 | ETL-150: Configuring ETL Schedules | VIRP Build 3 | Story | 638240: ETL-150: Configuring ETL Schedules | 161849: VIRP_NF_Configuring ETL Schedules | Done
574903 | FNM-010: Source Code Naming Conventions for File Types | VIRP Build 3 | Story | 638244: FNM-010: Source Code Naming Conventions for File Types | 162628: VIRP_NF_Source Code Naming Conventions for File Types | Done
574900 | ETL-160: Default ETL Schedule | VIRP Build 3 | Story | 638241: ETL-160: Default ETL Schedule |  | Done
574901 | ETL-170: ETL Retry Configuration | VIRP Build 3 | Story | 638237: ETL-120: Referral Criteria Match Indicator Flag 638242: ETL-170: ETL Retry Configuration |  | Done
574902 | ETL-180: ETL Retrieval Frequency | VIRP Build 3 | Story | 638243: ETL-180: ETL Retrieval Frequency | 162585: VIRP_NF_ETL Retrieval Frequency | Done
574904 | FNM-020: Source Code Naming Convention Prefix | VIRP Build 3 | Story | 638245: FNM-020: Source Code Naming Convention Prefix | 162626: VIRP_NF_Source Code Naming Convention Prefix | Done
574917 | MDU-040: Data Upload Status Notifications | VIRP Build 3 | Story | 638257: MDU-040: Data Upload Status Notifications | 161547: VIRP_NF_Data Upload Status Notification | Done
574914 | MDU-010: Manual Data Entry | VIRP Build 3 | Story | 638254: MDU-010: Manual Data Entry | 161613: VIRP_NF_Manual Data Entry | Done
574915 | MDU-020: Automating Manual Upload Processes | VIRP Build 3 | Story | 638255: MDU-020: Automating Manual Upload Processes | 161861: VIRP_NF_Automating Manual Upload Processes | Done
574916 | MDU-030: Logging Data Uploads | VIRP Build 3 | Story | 638256: MDU-030: Logging Data Uploads | 162589: VIRP_NF_Logging Data Uploads | Done
574905 | FNM-030: ETL Naming Convention Elements | VIRP Build 3 | Story | 638246: FNM-030: ETL Naming Convention Elements |  | Done
574906 | FNM-040: Source Code Tree Structure | VIRP Build 3 | Story | 638247: FNM-040: Source Code Tree Structure | 162625: VIRP_NF_Source Code Tree Structure | Done
574912 | INT-020: External Business Partners | VIRP Build 3 | Story | 638252: INT-020: External Business Partners | 161608: VIRP_NF_External Business Partners | Done
574911 | INT-010: Maintaining Existing Interfaces | VIRP Build 3 | Story | 638251: INT-010: Maintaining Existing Interfaces |  | Deferred
574913 | INT-030: VistA Interface Compliance | VIRP Build 3 | Story | 638253: INT-030: VistA Interface Compliance |  | Done
574957 | REG-010: Registry Interface Implementation | VIRP Build 3 | Story | 638355: REG-010: Registry Interface Implementation | 161563: VIRP - NF - Registry Interface Implementation | Done
574958 | REL-010: System Availability | VIRP Build 3 | Story | 641955: REL-010: System Availability | 161552: VIRP - NF - System Availability | Done
574959 | REL-020: System Maintenance Schedule | VIRP Build 3 | Story | 638358: REL-020: System Maintenance Schedule | 161554: VIRP - NF - System Maintenance Schedule | Done
574960 | REL-030: Performance Degradation Notification Timing | VIRP Build 3 | Story | 638359: REL-030: Performance Degradation Notification Timing | 162600: VIRP_NF_Performance Degradation Notification Timing | Done
574961 | REL-040: Performance Degradation Notification Contents | VIRP Build 3 | Story | 638360: REL-040: Performance Degradation Notification Contents | 162603: VIRP_NF_Performance Degradation Notification Contents | Done
574963 | REL-050: Automated Notification Report | VIRP Build 3 | Story | 638361: REL-050: Automated Notification Report | 162607: VIRP_NF_Automated Notfication Report | Done
574964 | REL-060: Advanced Maintenance Notification | VIRP Build 3 | Story | 638362: REL-060: Advanced Maintenance Notification | 161573: VIRP - NF - Advanced Maintenance Notification | Done
574965 | REL-070: Mean Time Between Failures | VIRP Build 3 | Story | 638363: REL-070: Mean Time Between Failures | 161589: VIRP - NF - Mean Time Between Failures | Done
574966 | REL-080: Mean Time to Repair | VIRP Build 3 | Story | 638364: REL-080: Mean Time to Repair | 161584: VIRP - NF - Mean Time to Repair | Done
574998 | SCI-020: Utilizing Common Framework and Platform | VIRP Build 3 | Story | 638397: SCI-020: Utilizing Common Framework and Platform | 162627: VIRP_NF_Utilizing Common Framework and Platform | Done
574999 | SCI-030: Interfacing With other Systems | VIRP Build 3 | Story | 638398: SCI-030: Interfacing With other Systems | 161690: VIRP_NF_Interfacing with other Systems | Done
575000 | SCI-040: Compliance With VA Enterprise Services Standards | VIRP Build 3 | Story | 638401: SCI-040: Compliance With VA Enterprise Services Standards | 161615: VIRP_NF_Compliance VA Enterprise Services Standards | Done
574991 | SA-020: View and Manage Log Files | VIRP Build 3 | Story | 638389: SA-020: View and Manage Log Files |  | Done
574990 | SA-010: System Configuration Settings | VIRP Build 3 | Story | 638388: SA-010: System Configuration Settings |  | Done
574992 | SA-030: Configure Log File Size | VIRP Build 3 | Story | 638390: SA-030: Configure Log File Size | 160167: VIRP - Configure Log File Size | Done
574993 | SA-040: System Logger Controls | VIRP Build 3 | Story | 638391: SA-040: System Logger Controls | 160172: VIRP - System Logger Controls | Done
574994 | SA-050: Configure ETL Default Schedule and Retry Settings | VIRP Build 3 | Story | 638392: SA-050: Configure ETL Default Schedule and Retry Settings |  | Done
574995 | SA-060: Editing Common Survey Questions/Answers | VIRP Build 3 | Story | 638393: SA-060: Editing Common Survey Questions/Answers |  | Done
574996 | SA-070: Logging Configuration Changes | VIRP Build 3 | Story | 638394: SA-070: Logging Configuration Changes |  | Done
574997 | SCI-010: Encompassing Multiple Registries | VIRP Build 3 | Story | 638395: SCI-010: Encompassing Multiple Registries | 161703: VIRP_NF_Encompassing Multiple Registries | Done
574854 | DBE-010: Registry Table Design | VIRP Build 3 | Story | 638176: DBE-010: Registry Table Design | 161529: VIRP - NF - Registry Table Design | Done
574855 | DBE-020: Use of Composite Primary Keys | VIRP Build 3 | Story | 638177: DBE-020: Use of Composite Primary Keys |  | Done
574856 | DBE-030: Use of Secondary Indexes | VIRP Build 3 | Story | 638178: DBE-030: Use of Secondary Indexes |  | Done
574857 | DBE-040: Mapping Patient Identifiers | VIRP Build 3 | Story | 638179: DBE-040: Mapping Patient Identifiers | 161533: VIRP - NF - Mapping Patient Identifiers | Done
574858 | DBS-010: Database Field Naming | VIRP Build 3 | Story | 638180: DBS-010: Database Field Naming | 161548: VIRP - NF - Database Field Naming | Done
574859 | DBS-020: Accessing Non-clinical Reference Terminology | VIRP Build 3 | Story | 638181: DBS-020: Accessing Non-clinical Reference Terminology | 161546: VIRP - NF - Accessing Non-clinical Reference Terminology | Done
574860 | DBS-030: Data Dictionary Table | VIRP Build 3 | Story | 638183: DBS-030: Data Dictionary Table | 161550: VIRP - NF - Data Dictionary Table | Done
574861 | DBS-040: Data Dictionary Mapping | VIRP Build 3 | Story | 638185: DBS-040: Data Dictionary Mapping | 161541: VIRP - NF - Data Dictionary Mapping | Done
574862 | DBS-050: Data Dictionary User Interface | VIRP Build 3 | Story | 638187: DBS-050: Data Dictionary User Interface | 160152: VIRP - Data Dictionary User Interface | Done
574863 | DBS-060: Data Conformance to National Standards | VIRP Build 3 | Story | 638188: DBS-060: Data Conformance to National Standards 638367: REP-020: Report Creation from Pre-existing Reports |  | Done
574864 | DBS-070: Conformance to Open Source Data Models | VIRP Build 3 | Story | 638190: DBS-070: Conformance to Open Source Data Models | 161560: VIRP - NF - Conformance to Open Source Data Models | Done
574865 | DBS-080: Conformance to Industry Best Practices | VIRP Build 3 | Story | 638191: DBS-080: Conformance to Industry Best Practices | 161570: VIRP - NF - Conformance to Industry Best Practices | Done
574868 | DC-070: Common Framework Components | VIRP Build 3 | Story | 638198: DC-070: Common Framework Components | 161577: VIRP - NF - Common Framework Components | Done
574869 | DC-080: Standard Application Programming Interfaces | VIRP Build 3 | Story | 638199: DC-080: Standard Application Programming Interfaces | 161566: VIRP - NF - Standard Application Programming | Done
574866 | DC-050: Leverage and Maximize Design Patterns | VIRP Build 3 | Story | 638196: DC-050: Leverage and Maximize Design Patterns | 162624: VIRP_NF_Leverage and Maximize Design Patterns | Done
574867 | DC-060: Providing Common Capabilities | VIRP Build 3 | Story | 638197: DC-060: Providing Common Capabilities | 161580: VIRP - NF - Providing Common Capabilities | Done
574870 | DR-010: Preserving Existing Disaster Recovery Procedures | VIRP Build 3 | Story | 638200: DR-010: Preserving Existing Disaster Recovery Procedures | 161587: VIRP - NF - Preserving Existing Disaster Recovery Procedures | Done
574871 | DR-020: Backup Verification | VIRP Build 3 | Story | 638205: DR-020: Backup Verification | 161617: VIRP - NF - Backup Verification | Done
574872 | DR-030: Disaster Recovery Solutions | VIRP Build 3 | Story | 638206: DR-030: Disaster Recovery Solutions | 161590: VIRP - NF - Disaster Recovery Solutions | Done
574873 | DR-040: Disaster Recovery Standard Compliance | VIRP Build 3 | Story | 638209: DR-040: Disaster Recovery Standard Compliance | 161582: VIRP - NF - Disaster Recovery Standard Compliance | Done
574874 | DR-050: RTO Support | VIRP Build 3 | Story | 638212: DR-050: RTO Support | 161619: VIRP - NF - RTO Support | Done
574875 | DR-060: RPO Support | VIRP Build 3 | Story | 638214: DR-060: RPO Support | 161620: VIRP - NF - Data-staging Upload Process | Done
574876 | DST-010: Data-staging Environment | VIRP Build 3 | Story | 638215: DST-010: Data-staging Environment | 161618: VIRP - NF - Data-staging Environment | Done
574877 | DST-020: Data Dependency Map | VIRP Build 3 | Story | 638216: DST-020: Data Dependency Map | 162609: VIRP_NF_Data Dependency Map | Done
574879 | DST-030: Data-staging Upload Process | VIRP Build 3 | Story | 638217: DST-030: Data-staging Upload Process | 161777: VIRP_NF_Data Staging Upload Process | Done
581499 | Contract Deliverables | VIRP Build 3 | Epic | 930825: _vI116Y3UEeew5esHMaxtpw |  | In Progress
654297 | Build Release Package January 12 | VIRP Build 3 | Task |  |  | Done
654338 | Updated Guide Package Security Guide February 9 | VIRP Build 3 | Task |  |  | Done
581930 | SQA Review Checklist | VIRP Build 3 | Story |  |  | Done
581936 | Data Migration Defect Log | VIRP Build 3 | Story |  |  | Done
581933 | Data Migration Validation | VIRP Build 3 | Story |  |  | Done
581932 | Release Package | VIRP Build 3 | Story |  |  | Done
581926 | Regression Testing Known Defect/Fix Log and Status Report | VIRP Build 3 | Story |  |  | Done
581929 | User Functionality Test Evaluation Summary | VIRP Build 3 | Story |  |  | Done
581927 | Regression Testing Evaluation Summary | VIRP Build 3 | Story |  |  | Done
581924 | Data Migration Plan | VIRP Build 3 | Story |  |  | Done
581922 | System Testing Package | VIRP Build 3 | Story |  |  | Done
607869 | Sprint Plan (September 20) | VIRP Build 3 | Story |  |  | Done
607853 | Updated Registry Implementation Developer's Guide (September 20) | VIRP Build 3 | Story |  |  | Done
607854 | Updated Configuration Management Plan (September 20) | VIRP Build 3 | Story |  |  | Done
607855 | Updated Source Code Repository Structure (September 20) | VIRP Build 3 | Story |  |  | Done
607856 | Defect/Fix Status Report (September 20) | VIRP Build 3 | Story |  |  | Done
607857 | Build Release Package (September 20) | VIRP Build 3 | Story |  |  | Done
607859 | Work Breakdown Structure (September 29) | VIRP Build 3 | Story |  |  | Done
607858 | Weekly Risk Management Status Report (September 29) | VIRP Build 3 | Story |  |  | Done
607860 | Integrated Master Schedule (September 29) | VIRP Build 3 | Story |  |  | Done
607861 | Onboarding Status Report (September 29) | VIRP Build 3 | Story |  |  | Done
607862 | Weekly Risk Management Status Report (September 22) | VIRP Build 3 | Story |  |  | Done
607864 | Integrated Master Schedule (September 22) | VIRP Build 3 | Story |  |  | Done
607863 | Work Breakdown Structure (September 22) | VIRP Build 3 | Story |  |  | Done
607865 | Onboarding Status Report (September 22) | VIRP Build 3 | Story |  |  | Done
607867 | Sprint Plan (September 29) | VIRP Build 3 | Story |  |  | Done
581900 | Updated Master Test Plan | VIRP Build 3 | Story |  |  | Done
654291 | Updated Guide Package User Guide January 12 | VIRP Build 3 | Task |  |  | Done
589499 | CPMP November Deliverable | VIRP Build 3 | Story |  |  | Done
654342 | Build Release Package February 9 | VIRP Build 3 | Task |  |  | Done
621804 | Updated Information Systems Continuity Plan November 17 | VIRP Build 3 | Story |  |  | Done
621803 | Updated Product Build Checklist November 17 | VIRP Build 3 | Story |  |  | Done
621805 | Updated Guide Package November 17 | VIRP Build 3 | Story |  |  | Done
621806 | Updated Guide Package (Technical Manual) November 17 | VIRP Build 3 | Story |  |  | Done
621807 | Updated Guide Package (Users Guide) November 17 | VIRP Build 3 | Story |  |  | Done
621808 | Updated Guide Package (Security Guide) November 17 | VIRP Build 3 | Story |  |  | Done
621809 | Updated Installation Guide November 17 | VIRP Build 3 | Story |  |  | Done
621812 | Source Code Repository Structure November 17 | VIRP Build 3 | Story |  |  | Done
621813 | Defect/Fix Status Report November 17 | VIRP Build 3 | Story |  |  | Done
621810 | Registry Implementation Developer's Guide November 17 | VIRP Build 3 | Story |  |  | Done
621811 | Configuration Management Plan November 17 | VIRP Build 3 | Story |  |  | Done
621814 | Build Release Package November 17 | VIRP Build 3 | Story |  |  | Done
621815 | Configuration Management Plan November 17 | VIRP Build 3 | Story |  |  | Done
621816 | Weekly Risk Management Status Report December 1 | VIRP Build 3 | Story |  |  | Done
621817 | Work Breakdown Structure December 1 | VIRP Build 3 | Story |  |  | Done
621818 | Integrated Master Schedule December 1 | VIRP Build 3 | Story |  |  | Done
621819 | Onboarding Status Report December 1 | VIRP Build 3 | Story |  |  | Done
621820 | Sprint Plan December 1 | VIRP Build 3 | Story |  |  | Done
621821 | Weekly Risk Management Status Report November 24 | VIRP Build 3 | Story |  |  | Done
621822 | Work Breakdown Structure November 24 | VIRP Build 3 | Story |  |  | Done
587942 | CPMP October Deliverable | VIRP Build 3 | Story | 930825: Contract Deliverables |  | Done
621823 | Weekly Risk Management Status Report November 17 | VIRP Build 3 | Story |  |  | Done
621827 | Onboarding Status Report November 17 | VIRP Build 3 | Story |  |  | Done
621824 | Work Breakdown Structure November 17 | VIRP Build 3 | Story |  |  | Done
621825 | Integrated Master Schedule November 24 | VIRP Build 3 | Story |  |  | Done
621826 | Integrated Master Schedule November 17 | VIRP Build 3 | Story |  |  | Done
621828 | Sprint Plan November 17 | VIRP Build 3 | Story |  |  | Done
621829 | Onboarding Status Report November 24 | VIRP Build 3 | Story |  |  | Done
621830 | Sprint Plan November 24 | VIRP Build 3 | Story |  |  | Done
581905 | New and Updated Test Cases/Scripts | VIRP Build 3 | Story |  |  | Done
607777 | Work Breakdown Structure (September 8) | VIRP Build 3 | Story |  |  | Done
607773 | Work Breakdown Structure (September 15) | VIRP Build 3 | Story |  |  | Done
607774 | Integrated Master Schedule (September 15) | VIRP Build 3 | Story |  |  | Done
607776 | Onboarding Status Report (September 15) | VIRP Build 3 | Story |  |  | Done
607769 | Defect Resolution Plan (September 15) | VIRP Build 3 | Story |  |  | Done
607770 | Backlog Plan (September 15) | VIRP Build 3 | Story |  |  | Done
607771 | Weekly Risk Management Status Report (September 15) | VIRP Build 3 | Story |  |  | Done
607782 | Requirements Package (September 15) | VIRP Build 3 | Story |  |  | Done
607778 | Integrated Master Schedule (September 8) | VIRP Build 3 | Story |  |  | Done
607779 | Onboarding Status Report (September 8) | VIRP Build 3 | Story |  |  | Done
607780 | Contractor Project Management Plan (September 15) | VIRP Build 3 | Story |  |  | Done
607783 | Product Operations Manual (September 15) | VIRP Build 3 | Story |  |  | Done
607784 | Build Plan (September 15) | VIRP Build 3 | Story |  |  | Done
632872 | Build Release Package December 15 | VIRP Build 3 | Task |  |  | Done
581908 | New, Updated, and Sanitized Test Data | VIRP Build 3 | Story |  |  | Done
637973 | Weekly Risk Management Status Report December 22 | VIRP Build 3 | Task |  |  | Done
637974 | Work Breakdown Structure December 22 | VIRP Build 3 | Task |  |  | Done
637975 | Integrated Master Schedule December 22 | VIRP Build 3 | Task |  |  | Done
637978 | Weekly Risk Management Status Report December 29 | VIRP Build 3 | Task |  |  | Done
637979 | Work Breakdown Structure December 29 | VIRP Build 3 | Task |  |  | Done
637976 | Onboarding Status Report December 22 | VIRP Build 3 | Task |  |  | Done
637977 | Sprint Plan December 22 | VIRP Build 3 | Task |  |  | Done
637980 | Integrated Master Schedule December 29 | VIRP Build 3 | Task |  |  | Done
637981 | Onboarding Status Report December 29 | VIRP Build 3 | Task |  |  | Done
637982 | Sprint Plan December 29 | VIRP Build 3 | Task |  |  | Done
581910 | Updated Installation Guide | VIRP Build 3 | Story |  |  | Done
612288 | Requirements Package (November 10) | VIRP Build 3 | Story |  |  | Done
581912 | Updated Guide Package | VIRP Build 3 | Story |  |  | Done
654293 | Updated Guide Package Technical Manual January 12 | VIRP Build 3 | Task |  |  | Done
581721 | Contractor Project Management Plan | VIRP Build 3 | Story |  |  | Done
581776 | Updates to Software Source Code, Compiled Code, and Supporting Documentation | VIRP Build 3 | Story |  |  | Done
581760 | Section 508 Self Certification Document | VIRP Build 3 | Story |  |  | Done
581762 | TRR/PRR Review Meeting Results | VIRP Build 3 | Story |  |  | Done
581778 | Initial Operating Capability (IOC) Entry Request and Exit Summary | VIRP Build 3 | Story |  |  | Done
581766 | Build Acceptance Form | VIRP Build 3 | Story |  |  | Done
581774 | Defect Resolution Plan | VIRP Build 3 | Story |  |  | Done
581773 | Defect/Fix Status Report | VIRP Build 3 | Story |  |  | Done
581769 | Build Release Package | VIRP Build 3 | Story |  |  | Done
581765 | Final Development Code Files, Compiled Code, and Supporting Documentation | VIRP Build 3 | Story |  |  | Done
654317 | Section 508 Self Certification Document January 15 | VIRP Build 3 | Task |  |  | Done
581793 | VA Eye Injury Data Store (EIDS) Registry Migration | VIRP Build 3 | Story |  |  | Deferred
581801 | Updated Operations Acceptance Plan | VIRP Build 3 | Story |  |  | Done
581799 | Updated Configuration Management Plan | VIRP Build 3 | Story |  |  | Done
581795 | Updated Source Code Repository Structure | VIRP Build 3 | Story |  |  | Done
581790 | Oncology Registry Migration | VIRP Build 3 | Story |  |  | Done
581788 | Prioritized Backlog (for each registry) | VIRP Build 3 | Story |  |  | Done
581783 | Create and Finalize New Registries Support | VIRP Build 3 | Story |  |  | Done
632866 | Updated Guide Package User’s Guide December 15 | VIRP Build 3 | Task |  |  | Done
632873 | Requirements Package December 8 | VIRP Build 3 | Task |  |  | Done
581914 | Updated Information Systems | VIRP Build 3 | Story |  |  | Done
612292 | Product Operations Manual (November 10) | VIRP Build 3 | Story |  |  | Done
581554 | Final Section 508 Compliance Test Results | VIRP Build 3 | Story |  |  | Done
581917 | Updated Product Build Checklist | VIRP Build 3 | Story |  |  | Done
654299 | Defect Resolution Plan January 5 | VIRP Build 3 | Task |  |  | Done
581504 | Sprint Plan | VIRP Build 3 | Story |  |  | Done
581507 | Version Description Document | VIRP Build 3 | Story |  |  | Done
581509 | Product Operations Manual | VIRP Build 3 | Story |  |  | Done
654339 | Updated Guide Package Technical Manual February 9 | VIRP Build 3 | Task |  |  | Done
581919 | Updated Software Source Code | VIRP Build 3 | Story |  |  | Done
581734 | Onboarding Status Report | VIRP Build 3 | Story |  |  | Done
581731 | VA Privacy and Information Security Awareness and Rules of Behavior Training Certificate | VIRP Build 3 | Story |  |  | Done
581732 | Signed Contractor Rules of Behavior | VIRP Build 3 | Story |  |  | Done
581733 | VA HIPAA Certificate of Completion | VIRP Build 3 | Story |  |  | Done
632875 | Defect Resolution Plan December 8 | VIRP Build 3 | Task |  |  | Done
581552 | Requirements Package | VIRP Build 3 | Story |  |  | Done
654294 | Registry Implementation Developer's Guide January 12 | VIRP Build 3 | Task |  |  | Done
581920 | Product Component Testing | VIRP Build 3 | Story |  |  | Done
581757 | VIRP Build | VIRP Build 3 | Story |  |  | Done
581525 | Sustainment Transition Plan | VIRP Build 3 | Story |  |  | Deferred
581502 | Build Plan | VIRP Build 3 | Story |  |  | Done
632868 | Updated Guide Package Technical Manual December 15 | VIRP Build 3 | Task |  |  | Done
654298 | Requirements Package January 5 | VIRP Build 3 | Task |  |  | Done
654343 | Defect/Fix Status Report February 9 | VIRP Build 3 | Task |  |  | Done
581741 | Weekly Risk Management Status Report | VIRP Build 3 | Story |  |  | Done
581737 | Integrated Master Schedule | VIRP Build 3 | Story |  |  | Done
581740 | Work Breakdown Structure | VIRP Build 3 | Story |  |  | Done
632677 | Updated Product Build Checklist December 15 | VIRP Build 3 | Task |  |  | Done
632685 | Integrated Master Schedule December 15 | VIRP Build 3 | Task |  |  | Done
632682 | Source Code Repository Structure December 15 | VIRP Build 3 | Task |  |  | Done
632683 | Weekly Risk Management Status Report December 15 | VIRP Build 3 | Task |  |  | Done
632684 | Work Breakdown Structure December 15 | VIRP Build 3 | Task |  |  | Done
632686 | Onboarding Status Report December 15 | VIRP Build 3 | Task |  |  | Done
632681 | Configuration Management Plan December 15 | VIRP Build 3 | Task |  |  | Done
632678 | Updated Information Systems Continuity Plan December 15 | VIRP Build 3 | Task |  |  | Done
632679 | Updated Guide Package Security Guide December 15 | VIRP Build 3 | Task |  |  | Done
632680 | Updated Installation Guide December 15 | VIRP Build 3 | Task |  |  | Done
632690 | Integrated Master Schedule December 8 | VIRP Build 3 | Task |  |  | Done
632687 | Sprint Plan December 15 | VIRP Build 3 | Task |  |  | Done
632688 | Weekly Risk Management Status Report December 8 | VIRP Build 3 | Task |  |  | Done
632689 | Work Breakdown Structure December 8 | VIRP Build 3 | Task |  |  | Done
632694 | Backlog December 8 | VIRP Build 3 | Task |  |  | Done
632691 | Onboarding Status Report December 8 | VIRP Build 3 | Task |  |  | Done
632692 | Sprint Plan December 8 | VIRP Build 3 | Task |  |  | Done
632693 | Contractor Project Management Plan December 8 | VIRP Build 3 | Task |  |  | Done
632695 | Build Plan December 8 | VIRP Build 3 | Task |  |  | Done
632696 | Production Operations Manual December 8 | VIRP Build 3 | Task |  |  | Done
581615 | CPMP September Deliverable | VIRP Build 3 | Story |  |  | Done
632697 | Production Operations Manual RACI December 8 | VIRP Build 3 | Task |  |  | Done
654340 | Updated Guide Package User Guide February 9 | VIRP Build 3 | Task |  |  | Done
581745 | Backlog Plan | VIRP Build 3 | Story |  |  | Done
607907 | VIRP - DOC - NF- Updated Product Build Checklist (October 20) | VIRP Build 3 | Story |  |  | Done
607908 | Updated Guide Package (October 20) | VIRP Build 3 | Story |  |  | Done
607909 | Updated Installation Guide (October 20) | VIRP Build 3 | Story |  |  | Done
607910 | Updated Registry Implementation Developer's Guide (October 20) | VIRP Build 3 | Story |  |  | Done
607911 | Updated Configuration Management Plan (October 20) | VIRP Build 3 | Story |  |  | Done
607912 | Updated Source Code Repository Structure (October 20) | VIRP Build 3 | Story |  |  | Done
607913 | VIRP - DOC - NF- Defect/Fix Status Report (October 20) | VIRP Build 3 | Story |  |  | Done
607914 | VIRP - DOC - NF- Build Release Package (October 20) | VIRP Build 3 | Story |  |  | Done
607915 | VIRP - DOC - NF- Weekly Risk Management Status Report (October 27) | VIRP Build 3 | Story |  |  | Done
607916 | VIRP - DOC - NF- Work Breakdown Structure (October 27) | VIRP Build 3 | Story |  |  | Done
607917 | VIRP - DOC - NF- Integrated Master Schedule (October 27) | VIRP Build 3 | Story |  |  | Done
607920 | VIRP - DOC - NF- Weekly Risk Management Status Report (October 20) | VIRP Build 3 | Story |  |  | Done
607918 | VIRP - DOC - NF- Onboarding Status Report (October 27) | VIRP Build 3 | Story |  | 162085: VIRP_NF_Onboarding Status Report (October 27,2017) | Done
607921 | VIRP - DOC - NF- Work Breakdown Structure (October 20) | VIRP Build 3 | Story |  |  | Done
607922 | VIRP - DOC - NF- Integrated Master Schedule (October 20) | VIRP Build 3 | Story |  |  | Done
607923 | VIRP - DOC - NF- Onboarding Status Report (October 20) | VIRP Build 3 | Story |  |  | Done
607924 | VIRP - DOC - NF- Updated Information Systems Continuity Plan (October 20) | VIRP Build 3 | Story |  |  | Done
607926 | VIRP - DOC - NF- Sprint Plan (October 27) | VIRP Build 3 | Story |  |  | Done
607927 | VIRP - DOC - NF- Sprint Plan (October 20) | VIRP Build 3 | Story |  |  | Done
654296 | Defect/Fix Status Report January 12 | VIRP Build 3 | Task |  |  | Done
654344 | Defect Resolution Plan February 2 | VIRP Build 3 | Task |  |  | Done
607789 | Weekly Risk Management Status Report (September 8) | VIRP Build 3 | Story |  |  | Done
632870 | Registry Implementation Developer's Guide December 15 | VIRP Build 3 | Task |  |  | Done
581804 | Updated Registry Implementation Developer's Guide | VIRP Build 3 | Story |  |  | Done
612239 | Defect Resolution Plan (November 10) | VIRP Build 3 | Story |  |  | Done
612240 | Backlog Plan (November 10) | VIRP Build 3 | Story |  |  | Done
612241 | Weekly Risk Management Status Report (November 3) | VIRP Build 3 | Story |  |  | Done
612242 | Weekly Risk Management Status Report (November 10) | VIRP Build 3 | Story |  |  | Done
612243 | Work Breakdown Structure (November 3) | VIRP Build 3 | Story |  |  | Done
612244 | Work Breakdown Structure (November 10) | VIRP Build 3 | Story |  |  | Done
612247 | Integrated Master Schedule (November 10) | VIRP Build 3 | Story |  |  | Done
612245 | Integrated Master Schedule (November 3) | VIRP Build 3 | Story |  |  | Done
612249 | Onboarding Status Report (November 3) | VIRP Build 3 | Story |  |  | Done
612250 | Onboarding Status Report (November 10) | VIRP Build 3 | Story |  |  | Done
612251 | Contractor Project Management Plan (November 10) | VIRP Build 3 | Story |  |  | Done
612253 | Sprint Plan (November 3) | VIRP Build 3 | Story |  |  | Done
612254 | Sprint Plan (November 10) | VIRP Build 3 | Story |  |  | Done
612256 | Build Plan (November 10) | VIRP Build 3 | Story |  |  | Done
607879 | Defect Resolution Plan (October 13) | VIRP Build 3 | Story |  |  | Done
607880 | Backlog Plan (October 13) | VIRP Build 3 | Story |  |  | Done
607881 | Weekly Risk Management Status Report (October 13) | VIRP Build 3 | Story |  |  | Done
607882 | Work Breakdown Structure (October 13) | VIRP Build 3 | Story |  |  | Done
607883 | Integrated Master Schedule (October 13) | VIRP Build 3 | Story |  |  | Done
607884 | Onboarding Status Report (October 13) | VIRP Build 3 | Story |  |  | Done
607885 | Weekly Risk Management Status Report (October 6) | VIRP Build 3 | Story |  |  | Done
607886 | Work Breakdown Structure (October 6) | VIRP Build 3 | Story |  |  | Done
607887 | Integrated Master Schedule (October 6) | VIRP Build 3 | Story |  |  | Done
607888 | Onboarding Status Report (October 6) | VIRP Build 3 | Story |  |  | Done
607889 | Contractor Project Management Plan (October 13) | VIRP Build 3 | Story |  |  | Done
607890 | Requirements Package (October 13) | VIRP Build 3 | Story |  |  | Done
607891 | Product Operations Manual (October 13) | VIRP Build 3 | Story |  |  | Done
607892 | Sprint Plan (October 13) | VIRP Build 3 | Story |  |  | Done
607893 | Sprint Plan (October 6) | VIRP Build 3 | Story |  |  | Done
607894 | Build Plan (October 13) | VIRP Build 3 | Story |  |  | Done
581921 | CI Evaluation Summary | VIRP Build 3 | Story |  |  | Done
581729 | Rational Training Certificates | VIRP Build 3 | Story |  |  | Done
654341 | Updated Registry Implementation Developer's Guide February 9 | VIRP Build 3 | Task |  |  | Done
654304 | Integrated Master Schedule January 19 | VIRP Build 3 | Task |  |  | Done
654305 | Onboarding Status Report January 19 | VIRP Build 3 | Task |  |  | Done
654306 | Sprint Plan January 19 | VIRP Build 3 | Task |  |  | Done
654302 | Weekly Risk Management Status Report January 19 | VIRP Build 3 | Task |  |  | Done
654303 | Work Breakdown Structure January 19 | VIRP Build 3 | Task |  |  | Done
654307 | TRR/PRR Review Meeting Results January 15 | VIRP Build 3 | Story |  |  | Done
654308 | Weekly Risk Management Status Report January 26 | VIRP Build 3 | Task |  |  | Done
654309 | Work Breakdown Structure January 26 | VIRP Build 3 | Task |  |  | Done
654310 | Integrated Master Schedule January 26 | VIRP Build 3 | Task |  |  | Done
654311 | Onboarding Status Report January 26 | VIRP Build 3 | Task |  |  | Done
654312 | Sprint Plan January 26 | VIRP Build 3 | Task |  |  | Done
581743 | Configuration Management Plan | VIRP Build 3 | Story |  |  | Done
654345 | Requirements Package February 2 | VIRP Build 3 | Task |  |  | Done
654256 | Updated Product Build Checklist January 12 | VIRP Build 3 | Task |  |  | Done
654257 | Updated Information Systems Continuity Plan January 12 | VIRP Build 3 | Task |  |  | Done
654258 | Updated Guide Package Security Guide January 12 | VIRP Build 3 | Task |  |  | Done
654259 | Updated Installation Guide January 12 | VIRP Build 3 | Task |  |  | Done
654260 | Configuration Management Plan January 12 | VIRP Build 3 | Task |  |  | Done
654263 | Work Breakdown Structure January 12 | VIRP Build 3 | Task |  |  | Done
654264 | Integrated Master Schedule January 12 | VIRP Build 3 | Task |  |  | Done
654261 | Source Code Repository Structure January 12 | VIRP Build 3 | Task |  |  | Done
654262 | Weekly Risk Management Status Report January 12 | VIRP Build 3 | Task |  |  | Done
654265 | Onboarding Status Report January 12 | VIRP Build 3 | Task |  |  | Done
654266 | Sprint Plan January 12 | VIRP Build 3 | Task |  |  | Done
654267 | Weekly Risk Management Status Report January 5 | VIRP Build 3 | Task |  |  | Done
654268 | Work Breakdown Structure January 5 | VIRP Build 3 | Task |  |  | Done
654269 | Integrated Master Schedule January 5 | VIRP Build 3 | Task |  |  | Done
654270 | Onboarding Status Report January 5 | VIRP Build 3 | Task |  |  | Done
654271 | Sprint Plan January 5 | VIRP Build 3 | Task |  |  | Done
654272 | Contractor Project Management Plan January 5 | VIRP Build 3 | Task |  |  | Done
654273 | Backlog January 5 | VIRP Build 3 | Task |  |  | Done
654274 | Build Plan January 5 | VIRP Build 3 | Task |  |  | Done
654275 | Production Operations Manual January 5 | VIRP Build 3 | Task |  |  | Done
654320 | Integrated Master Schedule February 2 | VIRP Build 3 | Task |  |  | Done
654323 | Contractor Project Management Plan February 2 | VIRP Build 3 | Task |  |  | Done
654321 | Onboarding Status Report February 2 | VIRP Build 3 | Task |  |  | Done
654322 | Sprint Plan February 2 | VIRP Build 3 | Task |  |  | Done
654324 | Production Operations Manual February 2 | VIRP Build 3 | Task |  |  | Done
654325 | Backlog February 2 | VIRP Build 3 | Task |  |  | Done
654326 | Build Plan February 2 | VIRP Build 3 | Task |  |  | Done
654318 | Weekly Risk Management Status Report February 2 | VIRP Build 3 | Task |  |  | Done
654319 | Work Breakdown Structure February 2 | VIRP Build 3 | Task |  |  | Done
654327 | Weekly Risk Management Status Report February 9 | VIRP Build 3 | Task |  |  | Done
654330 | Onboarding Status Report February 9 | VIRP Build 3 | Task |  |  | Done
654328 | Work Breakdown Structure February 9 | VIRP Build 3 | Task |  |  | Done
654329 | Integrated Master Schedule February 9 | VIRP Build 3 | Task |  |  | Done
654331 | Sprint Plan February 9 | VIRP Build 3 | Task |  |  | Done
654334 | Updated Source Code Repository Structure February 9 | VIRP Build 3 | Task |  |  | Done
654332 | TRR/PRR Review Meeting Results February 9 | VIRP Build 3 | Task |  |  | Done
654333 | Updated Configuration Management Plan February 9 | VIRP Build 3 | Task |  |  | Done
654335 | Updated Product Build Checklist February 9 | VIRP Build 3 | Task |  |  | Done
654336 | Updated Information Systems Continuity Plan February 9 | VIRP Build 3 | Task |  |  | Done
654337 | Updated Installation Guide February 9 | VIRP Build 3 | Task |  |  | Done
632871 | Defect/Fix Status Report December 15 | VIRP Build 3 | Task |  |  | Done
585650 | Compliance Deliverables | VIRP Build 3 | Epic | 934425: _8A-NA5fnEee2hbAcYU2NFA |  | In Progress
585654 | DE&A Compliance | VIRP Build 3 | Story |  |  | Done
585651 | 508 Compliance | VIRP Build 3 | Story |  |  | Done
612898 | 508 - Color Contrast Ratio >= 4.0 | VIRP Build 3 | Defect |  |  | Resolved
617516 | Submit 508 Audit request | VIRP Build 3 | Task |  |  | Done
630215 | VIRP -508 - The product contains functions which are not executable from a keyboard. | VIRP Build 3 | Defect |  |  | Resolved
612895 | 508 - A method shall be provided that permits users to skip repetitive navigation | VIRP Build 3 | Defect |  |  | Resolved
630221 | VIRP - 508 - The product does not in all cases provide a well-defined on-screen indication of the current focus that moves among interactive interface elements as the input focus changes. | VIRP Build 3 | Defect |  |  | Resolved
612892 | 508 - Images must have an alt attribute | VIRP Build 3 | Defect |  |  | Resolved
612901 | 508 - All Tables/GridViews must have a Caption Property | VIRP Build 3 | Defect |  |  | Resolved
630225 | VIRP - 508 - The product does not make the identity, operation, and state of all user interface elements available to assistive technology. | VIRP Build 3 | Defect |  |  | Resolved
612894 | 508 - Ensure all form fields have explicit labels | VIRP Build 3 | Defect |  |  | Resolved
630227 | VIRP - 508 - The product does not provide a method that permits users to skip repetitive navigation links. | VIRP Build 3 | Defect |  |  | Resolved
630229 | VIRP - 508 - The product contains information which requires user vision to be retrieved. | VIRP Build 3 | Defect |  |  | Resolved
617509 | Conduct 508 Internal Testing | VIRP Build 3 | Task |  |  | Done
585653 | Fortify Scan Compliance | VIRP Build 3 | Story |  |  | Done
617523 | Submit Fortify Scans for Quality Code | VIRP Build 3 | Task |  |  | Done
617524 | Submit Fortify Scans for Secure Code | VIRP Build 3 | Task |  |  | Done
596933 | Code Cleanup for Fortify Scans | VIRP Build 3 | Task |  |  | Done
617522 | Test the Fortify fixes | VIRP Build 3 | Task |  |  | Done
585656 | VIP Documentation | VIRP Build 3 | Epic | 934426: _wmG2w5foEee2hbAcYU2NFA |  | New
617775 | Upload and Provide Traceability Details (requirements to test cases/Test Execution/Test Results/Defect Log) | VIRP Build 3 | Task |  |  | In Progress
617763 | Upload VIRP SLA | VIRP Build 3 | Task |  |  | Done
585659 | Deployment Plan | VIRP Build 3 | Story |  |  | Done
585661 | User Guide | VIRP Build 3 | Story |  |  | Done
617772 | Upload Approved Requirements (Epics/User Stories) | VIRP Build 3 | Task |  |  | Done
617769 | Upload Financial Management Plan | VIRP Build 3 | Task |  |  | Done
617752 | Upload VIRP 508 Validation Statement | VIRP Build 3 | Task |  |  | Done
585660 | Production Operations Manual with RACI and/or Technical Manual | VIRP Build 3 | Story |  |  | Done
585658 | Version Description Document | VIRP Build 3 | Story |  |  | Done
617755 | Upload VIRP ATO Approval Memo | VIRP Build 3 | Task |  |  | Done
617758 | VIRP Risk Log | VIRP Build 3 | Task |  |  | Done
594268 | Proposed Enhancements | VIRP Build 3 | Epic |  |  | New
596051 | VIRP Issue Log | VIRP Build 3 | Epic |  |  | New
596217 | Determine How to deliver Core Registries for (KDR, AR, HR, TR) in Production | VIRP Build 3 | Issue |  |  | New
596064 | Need STAT teams identified for each registry and the VIRP platform | VIRP Build 3 | Issue |  |  | Resolved
601283 | VIRP- Case start date and Due date do not have rules | VIRP Build 3 | Task |  | 159291: VIRP - Specification of Work Stream Activities | New
601687 | VIRP - My Task> Edit Referrals fields should be disabled | VIRP Build 3 | Task |  |  | New
601937 | VIRP - User Admin - Validation should be set while editing the User information | VIRP Build 3 | Task |  |  | New
661125 | VIRP - Help files are still pointing to CRSe and not all pages have the help text | VIRP Build 3 | Defect |  | 159499: VIRP - Searchable Online Help | New
685825 | ONC: As the Oncology business owner, I need Oncology data that I export from the Rocky Mountain Cancer Data System (RMCDS) available in VIRP | VIRP Build 3 | Epic | 977770: As the Oncology business owner, I need Oncology data that I export from the Rocky Mountain Cancer Data System (RMCDS) available in VIRP. |  | New
685830 | ONC: As an Oncology business owner, I need to provide ONC data to the VIRP team | VIRP Build 3 | Epic | 977771: As an Oncology business owner, I need to provide ONC data to the VIRP team |  | New
685866 | ONC: As a business owner, I need to transfer the RMCDS export file to the VIRP SQL server | VIRP Build 3 | Story | 977776: As a business owner, I need to transfer the RMCDS export file to the VIRP SQL server |  | New
685979 | ONC: As the Oncology business owner, I need to export the data from RMCDS and provide that to the VIRP administrators | VIRP Build 3 | Story | 977773: As the Oncology business owner, I need to export the data from RMCDS and provide that to the VIRP administators |  | New
693133 | VIRP - Error for Vital Sign frame work data | VIRP Build 3 | Defect |  |  | Resolved
695435 | Update CDWPatientLoad stored procedure to log counts for inserted records. | VIRP Build 3 | Task |  |  | Done
696641 | Update framework ETL packages to load all records for each run. | VIRP Build 3 | Task |  |  | Done
703639 | VIRP - KDR - Duplicate patients displays in PROD KDR | VIRP Build 3 | Defect |  |  | Ready for Review
738909 | Amputee Registry Berg Balance Report is not accepting full Date format (XXXXXXXX)that does not include dash, comma etc. | VIRP Build 3 | Defect |  |  | New
601788 | VIRP - As an Admin I should be able to edit my user role | VIRP Build 3 | Task |  | 159490: VIRP - Role Based View and Update Capabilities | New
635449 | VIRP_Build 2_SQA Test Environment | VIRP Build 3 | Task |  |  | Invalid
716855 | VIRP - ONC - Column discrepancies in the ONC reports | VIRP Build 3 | Defect |  |  | Ready for Review
717322 | VIRP - ONC - Cohort>Oncology>Edit is showing an Unexpected error..."" | VIRP Build 3 | Defect |  |  | New
717936 | VIRP - Report in DEV is not working | VIRP Build 3 | Defect |  |  | New
719028 | VIRP - All registries - Selecting Add New Patient" button displays an unexpected error message" | VIRP Build 3 | Defect |  |  | New
721644 | VIRP - KDR - Renal care report is not loading | VIRP Build 3 | Defect |  | 170101: VIRP-KDR-As the Kidney Disease Registry I want to provide the data elements on disparity of renal care delivery across all facilities so that I can carry out an adequate analysis... 170098: VIRP-KDR-As a User I want to be able to report on data related to renal care delivery at multiple VA sites so that I can identify the differences in Kidney Disease identification and care given... | New
659237 | WASA Vulnerability 3 - Missing Security Headers | VIRP Build 3 - Sprint 15 | Task |  |  | Done
659238 | WASA Vulnerability 4 - Directory Listing Is Enabled On Multiple Directories | VIRP Build 3 - Sprint 15 | Task |  |  | Done
659239 | WASA Vulnerability 5 - Unencrypted Viewstate | VIRP Build 3 - Sprint 15 | Task |  |  | Done
706948 | Research Access Denied to Log Issue | VIRP Build 3 - Sprint 15 | Task |  |  | Done
706984 | Research Issue Reading/Writing to App Config File | VIRP Build 3 - Sprint 15 | Task |  |  | Done
714421 | Add validation check to the Patient drill down page to ensure a user has access to the selected Referral | VIRP Build 3 - Sprint 15 | Task |  |  | Done
718698 | TRACER Framework Data | VIRP Build 3 - Sprint 15 | Task |  |  | Ready for Review
723521 | Session Timeout Warning Message | VIRP Build 3 - Sprint 15 | Task |  |  | Ready for Review
685835 | ONC: As a developer, I need to define the file transfer process to the VIRP SQL server for the RMCDS export that will reside on the ONC server vhawasccaonc | VIRP Build 3 - Sprint 15 | Epic | 977775: As a developer, I need to define the file transfer process to the VIRP SQL server for the RMCDS export that will reside on the ONC server vhawasccaonc |  | Done
685840 | ONC: As a business analyst, I need to identify the reports that I believe are most useful to the Oncology users based on the previous implementation | VIRP Build 3 - Sprint 15 | Story | 977786: As a business analyst, I need to identify the reports that I believe are most useful to the Oncology users based on the previous implementation | 183515: VIRP - ONC: As a developer, I need to install the ONC SSRS reports into the SQA Report Server | Implemented
685849 | ONC: As an Oncology data user, I need the ability to run reports on the Oncology data in VIRP | VIRP Build 3 - Sprint 15 | Epic | 977785: As an Oncology data user, I need the ability to run reports on the Oncology data in VIRP |  | Ready for Review
685871 | ONC: As a developer, I need to implement Oncology Reports | VIRP Build 3 - Sprint 15 | Story | 977787: As a developer, I need to implement Oncology Reports | 183515: VIRP - ONC: As a developer, I need to install the ONC SSRS reports into the SQA Report Server | Done
685876 | ONC: As a developer, I need to install the Oncology custom components | VIRP Build 3 - Sprint 15 | Epic | 977789: As a developer, I need to install the Oncology custom components |  | Done
685878 | ONC: As a DBA, I need to install and execute the Oncology ETL on the Development servers | VIRP Build 3 - Sprint 15 | Story | 977790: As a DBA, I need to install and execute the Oncology ETL on the Development servers |  | Implemented
685881 | ONC: As a DBA, I need to install and execute the Oncology ETL on the SQA servers | VIRP Build 3 - Sprint 15 | Story | 977791: As a DBA, I need to install and execute the Oncology ETL on the SQA servers |  | Implemented
685883 | ONC: As a developer, I need to install the ONC SSRS reports into the Development Report Server | VIRP Build 3 - Sprint 15 | Story | 977792: As a developer, I need to install the ONC SSRS reports into the Development Report Server |  | Done
685887 | ONC: As a developer, I need to install the ONC SSRS reports into the SQA Report Server | VIRP Build 3 - Sprint 15 | Story | 977794: As a developer, I need to install the ONC SSRS reports into the SQA Report Server | 183515: VIRP - ONC: As a developer, I need to install the ONC SSRS reports into the SQA Report Server | Implemented
685945 | ONC: As the Oncology business owner, I need to export a subset of data from RMCDS and provide that to the VIRP development team for testing purposes | VIRP Build 3 - Sprint 15 | Story | 977772: As the Oncology business owner, I need to export a subset of data from RMCDS and provide that to the VIRP development team for testing purposes |  | Done
716587 | Update how ETLs get the ETLBatchID for VIRP and reinstate the STD_Registry_ID | VIRP Build 3 - Sprint 16 | Defect |  |  | New
738855 | Remove dependency to Web.Config Report Server settings | VIRP Build 3 - Sprint 16 | Task |  |  | In Progress
728752 | VIRP - ONC - Reduce row size | VIRP Build 3 - Sprint 16 | Defect |  |  | New
728765 | VIRP - ONC - Adding other filters to narrow down results. | VIRP Build 3 - Sprint 16 | Defect |  |  | New
685863 | ONC: As a VIRP team member, I need to coordinate with the Oncology end users to assist with access to the Development, SQA, and Pre-Production environments | VIRP Build 3 - Sprint 16 | Story | 977788: As a VIRP team member, I need to coordinate with the Oncology end users to assist with access to the Development, SQA, and Pre-Production environments |  | In Progress
692046 | Review Audiology Data | VIRP Build 3 - Sprint 16 | Task |  |  | In Progress
727689 | VIRP - ONC - Display total number of record when the report is loaded | VIRP Build 3 - Sprint 16 | Defect |  |  | New
727716 | VIRP - ONC - List the name for the codes to select during running the reports | VIRP Build 3 - Sprint 16 | Defect |  |  | New