## VIRP Build 1 - Build Plan
Id | Primary Location | Summary | Plan Parent ID | Group | Story Points | Effective Estimate | Progress:Completed Story Points | Progress:Total Story Points | Progress:Completed Hours | Progress:Total Hours | Status | Implements Requirement | Work Item Type
596051 | FALSE | VIRP Issue Log |  | VIRP Build 1 | 3 pts |  | 0 | 3 |  |  | New |  | Epic
596064 | TRUE | Need STAT teams identified for each registry and the VIRP platform | 596051 | VIRP Build 1 | [6 empty] | Resolved |  | Issue
605964 | TRUE | User Story 574808 Role Based User Navigation and Privileges first initial steps are incomplete tester need first initial steps to complete test. |  | VIRP Build 1 | [6 empty] | Resolved |  | Defect
574583 | TRUE | eHMP Integration |  | VIRP Build 1 | 5 pts |  | 13 | 13 |  |  | Deferred | 919112: eHMP Integration | Epic
574824 | TRUE | CRE-010: Interface Display Within eHMP | 574583 | VIRP Build 1 | 1 pt | [5 empty] | Deferred | 638144: CRE-010: Interface Display Within eHMP | Story
574825 | TRUE | CRE-020: Interface Authentication Requirements | 574583 | VIRP Build 1 | 1 pt | [5 empty] | Deferred | 638145: CRE-020: Interface Authentication Requirements | Story
574827 | TRUE | CRE-030: Patient Data Retrieval | 574583 | VIRP Build 1 | 1 pt | [5 empty] | Deferred | 638146: CRE-030: Patient Data Retrieval | Story
574835 | TRUE | CRE-110: CRUD Capability Limits | 574583 | VIRP Build 1 | 1 pt | [5 empty] | Deferred | 638154: CRE-110: CRUD Capability Limits | Story
574836 | TRUE | CRE-120: Cohort Search Execution | 574583 | VIRP Build 1 | 1 pt | [5 empty] | Deferred | 638156: CRE-120: Cohort Search Execution | Story
574908 | TRUE | HMP-010: eHMP Web Service | 574583 | VIRP Build 1 | 1 pt | [5 empty] | Deferred | 638248: HMP-010: eHMP Web Service | Story
574909 | TRUE | HMP-020: eHMP User Interface | 574583 | VIRP Build 1 | 1 pt | [5 empty] | Deferred | 638249: HMP-020: eHMP User Interface | Story
574910 | TRUE | HMP-030: eHMP IAM Authentication | 574583 | VIRP Build 1 | 1 pt | [5 empty] | Deferred | 638250: HMP-030: eHMP IAM Authentication | Story
581499 | FALSE | Contract Deliverables |  | VIRP Build 1 | 5 pts |  | 230 | 255 |  |  | In Progress | 930825: _vI116Y3UEeew5esHMaxtpw | Epic
581502 | TRUE | Build Plan | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581504 | TRUE | Sprint Plan | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581507 | TRUE | Version Description Document | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581509 | TRUE | Product Operations Manual | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581525 | TRUE | Sustainment Transition Plan | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Deferred |  | Story
581552 | TRUE | Requirements Package | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581554 | TRUE | Final Section 508 Compliance Test Results | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581615 | TRUE | CPMP September Deliverable | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581721 | TRUE | Contractor Project Management Plan | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581729 | TRUE | Rational Training Certificates | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581731 | TRUE | VA Privacy and Information Security Awareness and Rules of Behavior Training Certificate | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581732 | TRUE | Signed Contractor Rules of Behavior | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581733 | TRUE | VA HIPAA Certificate of Completion | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581734 | TRUE | Onboarding Status Report | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581737 | TRUE | Integrated Master Schedule | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581740 | TRUE | Work Breakdown Structure | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581741 | TRUE | Weekly Risk Management Status Report | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581743 | TRUE | Configuration Management Plan | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581745 | TRUE | Backlog Plan | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581757 | TRUE | VIRP Build | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581760 | TRUE | Section 508 Self Certification Document | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581762 | TRUE | TRR/PRR Review Meeting Results | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581765 | TRUE | Final Development Code Files, Compiled Code, and Supporting Documentation | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581766 | TRUE | Build Acceptance Form | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581769 | TRUE | Build Release Package | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581773 | TRUE | Defect/Fix Status Report | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581774 | TRUE | Defect Resolution Plan | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581776 | TRUE | Updates to Software Source Code, Compiled Code, and Supporting Documentation | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581778 | TRUE | Initial Operating Capability (IOC) Entry Request and Exit Summary | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581783 | TRUE | Create and Finalize New Registries Support | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581788 | TRUE | Prioritized Backlog (for each registry) | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581790 | TRUE | Oncology Registry Migration | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581793 | TRUE | VA Eye Injury Data Store (EIDS) Registry Migration | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Deferred |  | Story
581795 | TRUE | Updated Source Code Repository Structure | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581799 | TRUE | Updated Configuration Management Plan | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581801 | TRUE | Updated Operations Acceptance Plan | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581804 | TRUE | Updated Registry Implementation Developer's Guide | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581900 | TRUE | Updated Master Test Plan | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581905 | TRUE | New and Updated Test Cases/Scripts | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581908 | TRUE | New, Updated, and Sanitized Test Data | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581910 | TRUE | Updated Installation Guide | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581912 | TRUE | Updated Guide Package | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581914 | TRUE | Updated Information Systems | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581917 | TRUE | Updated Product Build Checklist | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581919 | TRUE | Updated Software Source Code | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581920 | TRUE | Product Component Testing | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581921 | TRUE | CI Evaluation Summary | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581922 | TRUE | System Testing Package | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581924 | TRUE | Data Migration Plan | 581499 | VIRP Build 1 | 0 pts | [5 empty] | Done |  | Story
581926 | TRUE | Regression Testing Known Defect/Fix Log and Status Report | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581927 | TRUE | Regression Testing Evaluation Summary | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581929 | TRUE | User Functionality Test Evaluation Summary | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581930 | TRUE | SQA Review Checklist | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581932 | TRUE | Release Package | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581933 | TRUE | Data Migration Validation | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
581936 | TRUE | Data Migration Defect Log | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
587942 | TRUE | CPMP October Deliverable | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done | 930825: Contract Deliverables | Story
589499 | TRUE | CPMP November Deliverable | 581499 | VIRP Build 1 | 2 pts | [5 empty] | Done |  | Story
606313 | TRUE | 574995 Editing Common Survey Questions/Answers- Missing Add Survey Field option |  | VIRP Build 1 | [6 empty] | Resolved |  | Defect
580904 | TRUE | Requirements Elaboration for VIRP Framework |  | VIRP Build 1 - Sprint 1 | 5 pts |  | 13 | 13 |  |  | Done | 930532: _N04ZMYzUEeecZaYUrvGJ7A | Epic
581071 | TRUE | Internal Review of Requirements | 580904 | VIRP Build 1 - Sprint 1 | 2 pts | [5 empty] | Done |  | Story
581082 | TRUE | Review Requirements with Business Owners | 580904 | VIRP Build 1 - Sprint 1 | 2 pts | [5 empty] | Done |  | Story
581198 | TRUE | Implementation Guide | 581082 | VIRP Build 1 - Sprint 1 | [6 empty] | Done |  | Task
581203 | TRUE | DST-020 Capability | 581082 | VIRP Build 1 - Sprint 1 | [6 empty] | Done |  | Task
581208 | TRUE | MDU-010 through 040 leave white and sell off as part of build acceptance | 581082 | VIRP Build 1 - Sprint 1 | [6 empty] | Done |  | Task
581213 | TRUE | INT-010 ensure covered as part of the Migration efforts for each registry and development of new registries | 581082 | VIRP Build 1 - Sprint 1 | [6 empty] | Done |  | Task
581218 | TRUE | Update TS-10 to discuss clarify documents required | 581082 | VIRP Build 1 - Sprint 1 | [6 empty] | Done |  | Task
581096 | TRUE | Requirements Analysis | 580904 | VIRP Build 1 - Sprint 1 | 2 pts | [5 empty] | Done |  | Story
581099 | TRUE | Project Schedule Updates | 580904 | VIRP Build 1 - Sprint 1 | 2 pts | [5 empty] | Done |  | Story
581499 | FALSE | Contract Deliverables |  | VIRP Build 1 - Sprint 2 | 5 pts |  | 230 | 255 |  |  | In Progress | 930825: _vI116Y3UEeew5esHMaxtpw | Epic
607789 | TRUE | Weekly Risk Management Status Report (September 8) | 581499 | VIRP Build 1 - Sprint 2 | 1 pt | [5 empty] | Done |  | Story
607769 | TRUE | Defect Resolution Plan (September 15) | 581499 | VIRP Build 1 - Sprint 2 | 1 pt | [5 empty] | Done |  | Story
607770 | TRUE | Backlog Plan (September 15) | 581499 | VIRP Build 1 - Sprint 2 | 1 pt | [5 empty] | Done |  | Story
607771 | TRUE | Weekly Risk Management Status Report (September 15) | 581499 | VIRP Build 1 - Sprint 2 | 1 pt | [5 empty] | Done |  | Story
607773 | TRUE | Work Breakdown Structure (September 15) | 581499 | VIRP Build 1 - Sprint 2 | 1 pt | [5 empty] | Done |  | Story
607774 | TRUE | Integrated Master Schedule (September 15) | 581499 | VIRP Build 1 - Sprint 2 | 1 pt | [5 empty] | Done |  | Story
607776 | TRUE | Onboarding Status Report (September 15) | 581499 | VIRP Build 1 - Sprint 2 | 1 pt | [5 empty] | Done |  | Story
607777 | TRUE | Work Breakdown Structure (September 8) | 581499 | VIRP Build 1 - Sprint 2 | 1 pt | [5 empty] | Done |  | Story
607778 | TRUE | Integrated Master Schedule (September 8) | 581499 | VIRP Build 1 - Sprint 2 | 1 pt | [5 empty] | Done |  | Story
607779 | TRUE | Onboarding Status Report (September 8) | 581499 | VIRP Build 1 - Sprint 2 | 1 pt | [5 empty] | Done |  | Story
607780 | TRUE | Contractor Project Management Plan (September 15) | 581499 | VIRP Build 1 - Sprint 2 | 1 pt | [5 empty] | Done |  | Story
607782 | TRUE | Requirements Package (September 15) | 581499 | VIRP Build 1 - Sprint 2 | 1 pt | [5 empty] | Done |  | Story
607783 | TRUE | Product Operations Manual (September 15) | 581499 | VIRP Build 1 - Sprint 2 | 1 pt | [5 empty] | Done |  | Story
607784 | TRUE | Build Plan (September 15) | 581499 | VIRP Build 1 - Sprint 2 | 1 pt | [5 empty] | Done |  | Story
589642 | TRUE | Initial VIRP Source Code Checkin |  | VIRP Build 1 - Sprint 3 | [6 empty] | Done |  | Task
574564 | FALSE | Referrals and Cohorts |  | VIRP Build 1 - Sprint 3 | 5 pts | [5 empty] | Done | 919111: Referrals and Cohorts | Epic
574819 | TRUE | BR-190: Referral Work Stream Requirements | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638139: BR-190: Referral Work Stream Requirements | Story
574820 | TRUE | BR-200: Work Stream Activity Requirements | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638140: BR-200: Work Stream Activity Requirements | Story
574821 | TRUE | BR-210: Referral Status Options | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638141: BR-210: Referral Status Options | Story
574822 | TRUE | BR-220: Work Stream State Options | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638142: BR-220: Work Stream State Options | Story
574828 | TRUE | CRE-040: Active Patient Indicator | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638147: CRE-040: Active Patient Indicator | Story
574830 | TRUE | CRE-060: Cohort Creation and Management | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638149: CRE-060: Cohort Creation and Management | Story
574831 | TRUE | CRE-070: Cohort Top Menu | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638150: CRE-070: Cohort Top Menu | Story
574832 | TRUE | CRE-080: Cohort Sub-Menu | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638151: CRE-080: Cohort Sub-Menu | Story
574833 | TRUE | CRE-090: Cohort Attributes | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Invalid | 638152: CRE-090: Cohort Attributes | Story
574834 | TRUE | CRE-100: Cohort Classification Rules | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638153: CRE-100: Cohort Classification Rules | Story
574837 | TRUE | CRE-130: Cohort Search Limits | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638157: CRE-130: Cohort Search Limits | Story
574839 | TRUE | CRE-150: Cohort Member Patient Listing | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638159: CRE-150: Cohort Member Patient Listing | Story
574842 | TRUE | CRE-170: Cohort Report Generation | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638161: CRE-170: Cohort Report Generation | Story
574843 | TRUE | CRE-180: Cohort and Patient Data Through Web Services | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638164: CRE-180: Cohort and Patient Data Through Web Services | Story
574844 | TRUE | CRE-190: Web Service for Cohort Listing | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638166: CRE-190: Web Service for Cohort Listing | Story
574845 | TRUE | CRE-200: Web Service for Cohort Criteria | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638167: CRE-200: Web Service for Cohort Criteria | Story
574847 | TRUE | CRE-210: Web Service for Patient Listing | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638168: CRE-210: Web Service for Patient Listing | Story
574848 | TRUE | CRE-230: Web Service for Patient Data | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638170: CRE-230: Web Service for Patient Data | Story
574850 | TRUE | CRE-250: Cohort Data Displays | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638172: CRE-250: Cohort Data Displays | Story
574851 | TRUE | CRE-260: Patient View Design | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638173: CRE-260: Patient View Design | Story
574853 | TRUE | CRE-280: Cohort Dashboard | 574564 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638175: CRE-280: Cohort Dashboard | Story
574584 | FALSE | Registry Wizard |  | VIRP Build 1 - Sprint 3 | 5 pts | [5 empty] | Done | 919113: Registry Wizard | Epic
574907 | TRUE | General Registry Information from Registry Wizard | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638376: General Registry Information from Registry Wizard | Story
574927 | TRUE | PTL-010: Single Registries Access Point | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638274: PTL-010: Single Registries Access Point | Story
574928 | TRUE | PTL-020: Single System Access User Interface | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638275: PTL-020: Single System Access User Interface | Story
574929 | TRUE | PTL-030: VA Approved User Authentication | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638277: PTL-030: VA Approved User Authentication | Story
574930 | TRUE | PTL-040: Generic and Registry Specific Menus | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638278: PTL-040: Generic and Registry Specific Menus | Story
574932 | TRUE | PTL-060: Dynamic Left Menu Creation | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638281: PTL-060: Dynamic Left Menu Creation | Story
574933 | TRUE | PTL-070: Default Left Menu items | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638282: PTL-070: Default Left Menu items | Story
574934 | TRUE | PTL-080: User Specification of Default Registry | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638283: PTL-080: User Specification of Default Registry | Story
574936 | TRUE | PTL-100: Ability to Switch Between Registries | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638285: PTL-100: Ability to Switch Between Registries | Story
574937 | TRUE | PTL-110: Ability to Open Multiple Registry Windows | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638287: PTL-110: Ability to Open Multiple Registry Windows | Story
574938 | TRUE | PTL-120: Ability To Display Multiple Registry Windows in Additional Browser Windows | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638288: PTL-120: Ability To Display Multiple Registry Windows in Additional Browser Windows | Story
574940 | TRUE | PTL-140: Drill Down, Add, and Update Capability | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638291: PTL-140: Drill Down, Add, and Update Capability | Story
574941 | TRUE | PTL-150: Single Referral Drill Down View | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638292: PTL-150: Single Referral Drill Down View | Story
574942 | TRUE | PTL-160: Patient Information Rollup | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638293: PTL-160: Patient Information Rollup | Story
574943 | TRUE | PTL-170: Search Filter Functionality | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638294: PTL-170: Search Filter Functionality | Story
574944 | TRUE | PTL-180: eHMP Sytle Guide Utilization | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638320: PTL-180: eHMP Sytle Guide Utilization | Story
574945 | TRUE | PTL-190: Design Pattern Usage | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638337: PTL-190: Design Pattern Usage | Story
574946 | TRUE | PTL-200: Common User Interface Displays | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638338: PTL-200: Common User Interface Displays | Story
574947 | TRUE | PTL-210: Common Data Displays | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638339: PTL-210: Common Data Displays | Story
574948 | TRUE | PTL-220: Searchable Online Help | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638340: PTL-220: Searchable Online Help | Story
574950 | TRUE | PTL-240: Work Flow Management Interface and Service | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638342: PTL-240: Work Flow Management Interface and Service | Story
574951 | TRUE | PTL-250: Manual Referral Entry | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638344: PTL-250: Manual Referral Entry | Story
574952 | TRUE | PTL-260: Distinguishing Between Manual and Automatic Referrals | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638347: PTL-260: Distinguishing Between Manual and Automatic Referrals | Story
574953 | TRUE | PTL-270: Common Survey Questions | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638349: PTL-270: Common Survey Questions | Story
574954 | TRUE | PTL-280: Survey Free Text Comments | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638350: PTL-280: Survey Free Text Comments | Story
574955 | TRUE | PTL-290: Referral Disqualification | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638352: PTL-290: Referral Disqualification | Story
574956 | TRUE | PTL-300: Referral Cancellation | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638354: PTL-300: Referral Cancellation | Story
574977 | TRUE | RW-010: Core Registry Creation | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 649068: RW-010: Core Registry Creation | Story
574978 | TRUE | RW-020: The Registry Wizard shall provide the ability to specify general Core Registry information | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 927051: RW-020: The Registry Wizard shall provide the ability to specify general Core Registry information | Story
574979 | TRUE | RW-030: Specification of Referral Work Streams | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638377: RW-030: Specification of Referral Work Streams | Story
574981 | TRUE | RW-050: Specification of Data Framework | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638379: RW-050: Specification of Data Framework | Story
574982 | TRUE | RW-060: Registry Wizard Data Selection | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638380: RW-060: Registry Wizard Data Selection | Story
574983 | TRUE | RW-070: Registry Wizard Referral Criteria Specification | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638381: RW-070: Registry Wizard Referral Criteria Specification | Story
574984 | TRUE | RW-080: Field Label Editing | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638382: RW-080: Field Label Editing | Story
574987 | TRUE | RW-110: Patient and Provider Data Retrieval | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638385: RW-110: Patient and Provider Data Retrieval | Story
574988 | TRUE | RW-120: Manually Entered Referral Data Retrieval | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638386: RW-120: Manually Entered Referral Data Retrieval | Story
574989 | TRUE | RW-130: Registry Configuration Settings | 574584 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638387: RW-130: Registry Configuration Settings | Story
574588 | FALSE | Platform and Business |  | VIRP Build 1 - Sprint 3 | 5 pts | [5 empty] | Done | 919116: Platform and Business | Epic
574796 | TRUE | BM-010: Encapsulate Common or Shared Methods | 574588 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638110: BM-010: Encapsulate Common or Shared Methods | Story
574797 | TRUE | BM-020: Extension of Core Business Manager Capability to Registry Specific Business Manager | 574588 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638111: BM-020: Extension of Core Business Manager Capability to Registry Specific Business Manager | Story
574798 | TRUE | BM-030: Implementation of Common and Registry-Specific Functionality | 574588 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638112: BM-030: Implementation of Common and Registry-Specific Functionality | Story
574799 | TRUE | BM-040: Verification of Manually Entered Referral Information | 574588 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Invalid | 638113: BM-040: Verification of Manually Entered Referral Information | Story
574800 | TRUE | BM-050: Saving of Survey Information | 574588 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638114: BM-050: Saving of Survey Information | Story
574801 | TRUE | BM-060: Survey Time Stamping | 574588 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638115: BM-060: Survey Time Stamping | Story
574802 | TRUE | BR-010: VIRP Management | 574588 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638116: BR-010: VIRP Management | Story
574804 | TRUE | BR-030: Preservation of Existing Functionality | 574588 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done | 638118: BR-030: Preservation of Existing Functionality | Story
581499 | FALSE | Contract Deliverables |  | VIRP Build 1 - Sprint 3 | 5 pts |  | 230 | 255 |  |  | In Progress | 930825: _vI116Y3UEeew5esHMaxtpw | Epic
607853 | TRUE | Updated Registry Implementation Developer's Guide (September 20) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
607854 | TRUE | Updated Configuration Management Plan (September 20) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
607855 | TRUE | Updated Source Code Repository Structure (September 20) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
607856 | TRUE | Defect/Fix Status Report (September 20) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
607857 | TRUE | Build Release Package (September 20) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
607858 | TRUE | Weekly Risk Management Status Report (September 29) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
607859 | TRUE | Work Breakdown Structure (September 29) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
607860 | TRUE | Integrated Master Schedule (September 29) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
607861 | TRUE | Onboarding Status Report (September 29) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
607862 | TRUE | Weekly Risk Management Status Report (September 22) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
607863 | TRUE | Work Breakdown Structure (September 22) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
607864 | TRUE | Integrated Master Schedule (September 22) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
607865 | TRUE | Onboarding Status Report (September 22) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
607867 | TRUE | Sprint Plan (September 29) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
607869 | TRUE | Sprint Plan (September 20) | 581499 | VIRP Build 1 - Sprint 3 | 1 pt | [5 empty] | Done |  | Story
610370 | TRUE | Initial VIRP source database check in. |  | VIRP Build 1 - Sprint 4 |  | 1 |  |  |  |  | Done |  | Task
574564 | FALSE | Referrals and Cohorts |  | VIRP Build 1 - Sprint 4 | 5 pts | [5 empty] | Done | 919111: Referrals and Cohorts | Epic
574814 | TRUE | BR-140: Patient Table Data Requirements | 574564 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638132: BR-140: Patient Table Data Requirements | Story
574815 | TRUE | BR-150: Patient Table Inclusions | 574564 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638133: BR-150: Patient Table Inclusions | Story
574816 | TRUE | BR-160: Patient Table Eligibility | 574564 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638135: BR-160: Patient Table Eligibility | Story
574823 | TRUE | BR-230: Cohorts and Data Integration | 574564 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638143: BR-230: Cohorts and Data Integration | Story
574829 | TRUE | CRE-050: Patient and Provider Data Refresh | 574564 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638148: CRE-050: Patient and Provider Data Refresh | Story
574838 | TRUE | CRE-140: Cohort Search Requirements | 574564 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638158: CRE-140: Cohort Search Requirements | Story
574841 | TRUE | CRE-160: Cohort Search Options | 574564 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638160: CRE-160: Cohort Search Options | Story
574846 | TRUE | CRE-200: Web Service for Evaluation Results | 574564 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638169: CRE-200: Web Service for Evaluation Results | Story
574849 | TRUE | CRE-240: Cohort Table Design | 574564 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638171: CRE-240: Cohort Table Design | Story
574852 | TRUE | CRE-270: Cohort Status Notification | 574564 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638174: CRE-270: Cohort Status Notification | Story
574584 | FALSE | Registry Wizard |  | VIRP Build 1 - Sprint 4 | 5 pts | [5 empty] | Done | 919113: Registry Wizard | Epic
574985 | TRUE | RW-090: Metadata Linking | 574584 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638383: RW-090: Metadata Linking | Story
574986 | TRUE | RW-100: Registry Wizard Data Table | 574584 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638384: RW-100: Registry Wizard Data Table | Story
574585 | FALSE | User and Access Management |  | VIRP Build 1 - Sprint 4 | 5 pts | [5 empty] | Done | 919114: User and Access Management | Epic
574803 | TRUE | BR-020: Access Through Single Interface | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638117: BR-020: Access Through Single Interface | Story
574805 | TRUE | BR-040: Access from Multiple VA Facilities | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638120: BR-040: Access from Multiple VA Facilities | Story
574806 | TRUE | BR-050: Access to All Registries Through a Single Platform | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638121: BR-050: Access to All Registries Through a Single Platform | Story
574808 | TRUE | BR-060: Role-Based User Navigation and Privileges | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638122: BR-060: Role-Based User Navigation and Privileges | Story
574809 | TRUE | BR-070: Common User Role Set | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638123: BR-070: Common User Role Set | Story
574811 | TRUE | BR-090: Access Requirement Compliance | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638125: BR-090: Access Requirement Compliance | Story
575008 | TRUE | UDR-010: User Role and Registry Configuration | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638477: UDR-010: User Role and Registry Configuration | Story
575009 | TRUE | UDR-020: User Registry Access | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638478: UDR-020: User Registry Access | Story
575011 | TRUE | UDR-030: Unique User Roles for Each Registry | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638479: UDR-030: Unique User Roles for Each Registry | Story
575012 | TRUE | UDR-040: Registry User Role Configuration | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638480: UDR-040: Registry User Role Configuration | Story
575013 | TRUE | UDR-050: Menu/Tab Access By User Role | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638481: UDR-050: Menu/Tab Access By User Role | Story
575014 | TRUE | UDR-060: Menu Item Access by User Role | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638482: UDR-060: Menu Item Access by User Role | Story
575015 | TRUE | UDR-070: User Role Configuration Data | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638483: UDR-070: User Role Configuration Data | Story
575016 | TRUE | UDR-080: System Configuration Data | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638484: UDR-080: System Configuration Data | Story
575017 | TRUE | UDR-090: Configuration Change Log | 574585 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638485: UDR-090: Configuration Change Log | Story
574586 | FALSE | Non Functional Requirements |  | VIRP Build 1 - Sprint 4 | 5 pts | [5 empty] | In Progress | 919118: Non Functional Requirements | Epic
574854 | TRUE | DBE-010: Registry Table Design | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638176: DBE-010: Registry Table Design | Story
574857 | TRUE | DBE-040: Mapping Patient Identifiers | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638179: DBE-040: Mapping Patient Identifiers | Story
574858 | TRUE | DBS-010: Database Field Naming | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638180: DBS-010: Database Field Naming | Story
574859 | TRUE | DBS-020: Accessing Non-clinical Reference Terminology | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638181: DBS-020: Accessing Non-clinical Reference Terminology | Story
574860 | TRUE | DBS-030: Data Dictionary Table | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638183: DBS-030: Data Dictionary Table | Story
574861 | TRUE | DBS-040: Data Dictionary Mapping | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638185: DBS-040: Data Dictionary Mapping | Story
574862 | TRUE | DBS-050: Data Dictionary User Interface | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638187: DBS-050: Data Dictionary User Interface | Story
574863 | TRUE | DBS-060: Data Conformance to National Standards | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638188: DBS-060: Data Conformance to National Standards 638367: REP-020: Report Creation from Pre-existing Reports | Story
574864 | TRUE | DBS-070: Conformance to Open Source Data Models | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638190: DBS-070: Conformance to Open Source Data Models | Story
574865 | TRUE | DBS-080: Conformance to Industry Best Practices | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638191: DBS-080: Conformance to Industry Best Practices | Story
574866 | TRUE | DC-050: Leverage and Maximize Design Patterns | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638196: DC-050: Leverage and Maximize Design Patterns | Story
574867 | TRUE | DC-060: Providing Common Capabilities | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638197: DC-060: Providing Common Capabilities | Story
574868 | TRUE | DC-070: Common Framework Components | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638198: DC-070: Common Framework Components | Story
574869 | TRUE | DC-080: Standard Application Programming Interfaces | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638199: DC-080: Standard Application Programming Interfaces | Story
574870 | TRUE | DR-010: Preserving Existing Disaster Recovery Procedures | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638200: DR-010: Preserving Existing Disaster Recovery Procedures | Story
574871 | TRUE | DR-020: Backup Verification | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638205: DR-020: Backup Verification | Story
574872 | TRUE | DR-030: Disaster Recovery Solutions | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638206: DR-030: Disaster Recovery Solutions | Story
574873 | TRUE | DR-040: Disaster Recovery Standard Compliance | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638209: DR-040: Disaster Recovery Standard Compliance | Story
574874 | TRUE | DR-050: RTO Support | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638212: DR-050: RTO Support | Story
574875 | TRUE | DR-060: RPO Support | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638214: DR-060: RPO Support | Story
574876 | TRUE | DST-010: Data-staging Environment | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638215: DST-010: Data-staging Environment | Story
574877 | TRUE | DST-020: Data Dependency Map | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638216: DST-020: Data Dependency Map | Story
574879 | TRUE | DST-030: Data-staging Upload Process | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638217: DST-030: Data-staging Upload Process | Story
574880 | TRUE | DST-040: Production Database Upload | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638370: REP-040: Graphical Report Creation | Story
574881 | TRUE | DST-050: Data-staging Environment Usage | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638219: DST-050: Data-staging Environment Usage | Story
574883 | TRUE | ERR-010: Error Handling and Logging | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638223: ERR-010: Error Handling and Logging | Story
574884 | TRUE | ERR-020: Distinguishing Between Errors and Tracing Events | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638224: ERR-020: Distinguishing Between Errors and Tracing Events | Story
574885 | TRUE | ETL-010: Maximized Use of Common ETLs | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638225: ETL-010: Maximized Use of Common ETLs | Story
574886 | TRUE | ETL-020: Consolidating ETL Processes | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638226: ETL-020: Consolidating ETL Processes | Story
574887 | TRUE | ETL-030: ETL Error Handling | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638227: ETL-030: ETL Error Handling | Story
574888 | TRUE | ETL-040: ETL Logging, Tracking, and Monitoring | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638228: ETL-040: ETL Logging, Tracking, and Monitoring | Story
574889 | TRUE | ETL-050: ETL Status Notification Capability | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638229: ETL-050: ETL Status Notification Capability | Story
574890 | TRUE | ETL-060: ETL Status Notification List | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638230: ETL-060: ETL Status Notification List | Story
574891 | TRUE | ETL-070: ETL Status Dashboard | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638231: ETL-070: ETL Status Dashboard | Story
574892 | TRUE | ETL-080: ETL Status Reporting Information | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638232: ETL-080: ETL Status Reporting Information | Story
574893 | TRUE | ETL-090: Standard Terminology Services from CDW | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638233: ETL-090: Standard Terminology Services from CDW | Story
574894 | TRUE | ETL-100: Referral Data Format | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638234: ETL-100: Referral Data Format | Story
574899 | TRUE | ETL-150: Configuring ETL Schedules | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638240: ETL-150: Configuring ETL Schedules | Story
574900 | TRUE | ETL-160: Default ETL Schedule | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638241: ETL-160: Default ETL Schedule | Story
574902 | TRUE | ETL-180: ETL Retrieval Frequency | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638243: ETL-180: ETL Retrieval Frequency | Story
574903 | TRUE | FNM-010: Source Code Naming Conventions for File Types | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638244: FNM-010: Source Code Naming Conventions for File Types | Story
574904 | TRUE | FNM-020: Source Code Naming Convention Prefix | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638245: FNM-020: Source Code Naming Convention Prefix | Story
574906 | TRUE | FNM-040: Source Code Tree Structure | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638247: FNM-040: Source Code Tree Structure | Story
574911 | TRUE | INT-010: Maintaining Existing Interfaces | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638251: INT-010: Maintaining Existing Interfaces | Story
574912 | TRUE | INT-020: External Business Partners | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638252: INT-020: External Business Partners | Story
574913 | TRUE | INT-030: VistA Interface Compliance | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638253: INT-030: VistA Interface Compliance | Story
574914 | TRUE | MDU-010: Manual Data Entry | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638254: MDU-010: Manual Data Entry | Story
574915 | TRUE | MDU-020: Automating Manual Upload Processes | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638255: MDU-020: Automating Manual Upload Processes | Story
574916 | TRUE | MDU-030: Logging Data Uploads | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638256: MDU-030: Logging Data Uploads | Story
574917 | TRUE | MDU-040: Data Upload Status Notifications | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638257: MDU-040: Data Upload Status Notifications | Story
574919 | TRUE | P-010: Defining Performance Metrics | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638259: P-010: Defining Performance Metrics | Story
574920 | TRUE | P-020: Transaction Processing Performance | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638262: P-020: Transaction Processing Performance | Story
574921 | TRUE | P-030: Concurrent User Capacity | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638263: P-030: Concurrent User Capacity | Story
574922 | TRUE | P-040: Scalability and Maintaining Required Performance | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638266: P-040: Scalability and Maintaining Required Performance | Story
574923 | TRUE | P-050: Scalability and Supporting Additional Registries | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638269: P-050: Scalability and Supporting Additional Registries | Story
574926 | TRUE | P-080: ETL Execution Time | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638273: P-080: ETL Execution Time | Story
574957 | TRUE | REG-010: Registry Interface Implementation | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638355: REG-010: Registry Interface Implementation | Story
574958 | TRUE | REL-010: System Availability | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 641955: REL-010: System Availability | Story
574959 | TRUE | REL-020: System Maintenance Schedule | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638358: REL-020: System Maintenance Schedule | Story
574960 | TRUE | REL-030: Performance Degradation Notification Timing | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638359: REL-030: Performance Degradation Notification Timing | Story
574961 | TRUE | REL-040: Performance Degradation Notification Contents | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638360: REL-040: Performance Degradation Notification Contents | Story
574963 | TRUE | REL-050: Automated Notification Report | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638361: REL-050: Automated Notification Report | Story
574964 | TRUE | REL-060: Advanced Maintenance Notification | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638362: REL-060: Advanced Maintenance Notification | Story
574965 | TRUE | REL-070: Mean Time Between Failures | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638363: REL-070: Mean Time Between Failures | Story
574966 | TRUE | REL-080: Mean Time to Repair | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638364: REL-080: Mean Time to Repair | Story
574990 | TRUE | SA-010: System Configuration Settings | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638388: SA-010: System Configuration Settings | Story
574994 | TRUE | SA-050: Configure ETL Default Schedule and Retry Settings | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638392: SA-050: Configure ETL Default Schedule and Retry Settings | Story
574996 | TRUE | SA-070: Logging Configuration Changes | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638394: SA-070: Logging Configuration Changes | Story
574997 | TRUE | SCI-010: Encompassing Multiple Registries | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638395: SCI-010: Encompassing Multiple Registries | Story
574998 | TRUE | SCI-020: Utilizing Common Framework and Platform | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638397: SCI-020: Utilizing Common Framework and Platform | Story
574999 | TRUE | SCI-030: Interfacing With other Systems | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638398: SCI-030: Interfacing With other Systems | Story
575000 | TRUE | SCI-040: Compliance With VA Enterprise Services Standards | 574586 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638401: SCI-040: Compliance With VA Enterprise Services Standards | Story
574588 | FALSE | Platform and Business |  | VIRP Build 1 - Sprint 4 | 5 pts | [5 empty] | Done | 919116: Platform and Business | Epic
574812 | TRUE | BR-100: Quality Control Plan | 574588 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638126: BR-100: Quality Control Plan | Story
574813 | TRUE | BR-110: Release Acceptance | 574588 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done | 638127: BR-110: Release Acceptance | Story
581499 | FALSE | Contract Deliverables |  | VIRP Build 1 - Sprint 4 | 5 pts |  | 230 | 255 |  |  | In Progress | 930825: _vI116Y3UEeew5esHMaxtpw | Epic
607879 | TRUE | Defect Resolution Plan (October 13) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607880 | TRUE | Backlog Plan (October 13) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607881 | TRUE | Weekly Risk Management Status Report (October 13) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607882 | TRUE | Work Breakdown Structure (October 13) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607883 | TRUE | Integrated Master Schedule (October 13) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607884 | TRUE | Onboarding Status Report (October 13) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607885 | TRUE | Weekly Risk Management Status Report (October 6) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607886 | TRUE | Work Breakdown Structure (October 6) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607887 | TRUE | Integrated Master Schedule (October 6) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607888 | TRUE | Onboarding Status Report (October 6) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607889 | TRUE | Contractor Project Management Plan (October 13) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607890 | TRUE | Requirements Package (October 13) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607891 | TRUE | Product Operations Manual (October 13) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607892 | TRUE | Sprint Plan (October 13) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607893 | TRUE | Sprint Plan (October 6) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
607894 | TRUE | Build Plan (October 13) | 581499 | VIRP Build 1 - Sprint 4 | 1 pt | [5 empty] | Done |  | Story
600994 | TRUE | Mammogram Questionnaire Section The Word Questionnaire" is Misspelled"- " |  | VIRP Build 1 - Sprint 5 |  | 8 |  |  |  |  | Resolved |  | Defect
600997 | TRUE | Cohort Attributes |  | VIRP Build 1 - Sprint 5 |  | 8 |  |  |  |  | Resolved |  | Defect
601000 | TRUE | Verification of Manually Entered Referral Information |  | VIRP Build 1 - Sprint 5 |  | 8 |  |  |  |  | Resolved | 638113: BM-040: Verification of Manually Entered Referral Information | Defect
601421 | TRUE | VIRP - Automatically Created" has been checked | the Workstream for the Referral is not created" |  | VIRP Build 1 - Sprint 5 |  | 8 |  |  |  | - | Resolved |  | Defect
610268 | TRUE | Referral Defects |  | VIRP Build 1 - Sprint 5 | [6 empty] | Resolved |  | Defect
611928 | TRUE | Referral disqualify comments not displayed |  | VIRP Build 1 - Sprint 5 | [6 empty] | Resolved | 638139: BR-190: Referral Work Stream Requirements | Defect
574564 | TRUE | Referrals and Cohorts |  | VIRP Build 1 - Sprint 5 | 5 pts | [5 empty] | Done | 919111: Referrals and Cohorts | Epic
574814 | FALSE | BR-140: Patient Table Data Requirements | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638132: BR-140: Patient Table Data Requirements | Story
574815 | FALSE | BR-150: Patient Table Inclusions | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638133: BR-150: Patient Table Inclusions | Story
574816 | FALSE | BR-160: Patient Table Eligibility | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638135: BR-160: Patient Table Eligibility | Story
574819 | FALSE | BR-190: Referral Work Stream Requirements | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638139: BR-190: Referral Work Stream Requirements | Story
574820 | FALSE | BR-200: Work Stream Activity Requirements | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638140: BR-200: Work Stream Activity Requirements | Story
574821 | FALSE | BR-210: Referral Status Options | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638141: BR-210: Referral Status Options | Story
574822 | FALSE | BR-220: Work Stream State Options | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638142: BR-220: Work Stream State Options | Story
574823 | FALSE | BR-230: Cohorts and Data Integration | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638143: BR-230: Cohorts and Data Integration | Story
574828 | FALSE | CRE-040: Active Patient Indicator | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638147: CRE-040: Active Patient Indicator | Story
574829 | FALSE | CRE-050: Patient and Provider Data Refresh | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638148: CRE-050: Patient and Provider Data Refresh | Story
574830 | FALSE | CRE-060: Cohort Creation and Management | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638149: CRE-060: Cohort Creation and Management | Story
574831 | FALSE | CRE-070: Cohort Top Menu | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638150: CRE-070: Cohort Top Menu | Story
574832 | FALSE | CRE-080: Cohort Sub-Menu | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638151: CRE-080: Cohort Sub-Menu | Story
574833 | FALSE | CRE-090: Cohort Attributes | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Invalid | 638152: CRE-090: Cohort Attributes | Story
574834 | FALSE | CRE-100: Cohort Classification Rules | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638153: CRE-100: Cohort Classification Rules | Story
574837 | FALSE | CRE-130: Cohort Search Limits | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638157: CRE-130: Cohort Search Limits | Story
574838 | FALSE | CRE-140: Cohort Search Requirements | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638158: CRE-140: Cohort Search Requirements | Story
574839 | FALSE | CRE-150: Cohort Member Patient Listing | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638159: CRE-150: Cohort Member Patient Listing | Story
574841 | FALSE | CRE-160: Cohort Search Options | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638160: CRE-160: Cohort Search Options | Story
574842 | FALSE | CRE-170: Cohort Report Generation | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638161: CRE-170: Cohort Report Generation | Story
574843 | FALSE | CRE-180: Cohort and Patient Data Through Web Services | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638164: CRE-180: Cohort and Patient Data Through Web Services | Story
574844 | FALSE | CRE-190: Web Service for Cohort Listing | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638166: CRE-190: Web Service for Cohort Listing | Story
574845 | FALSE | CRE-200: Web Service for Cohort Criteria | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638167: CRE-200: Web Service for Cohort Criteria | Story
574846 | FALSE | CRE-200: Web Service for Evaluation Results | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638169: CRE-200: Web Service for Evaluation Results | Story
574847 | FALSE | CRE-210: Web Service for Patient Listing | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638168: CRE-210: Web Service for Patient Listing | Story
574848 | FALSE | CRE-230: Web Service for Patient Data | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638170: CRE-230: Web Service for Patient Data | Story
574849 | FALSE | CRE-240: Cohort Table Design | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638171: CRE-240: Cohort Table Design | Story
574850 | FALSE | CRE-250: Cohort Data Displays | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638172: CRE-250: Cohort Data Displays | Story
574851 | FALSE | CRE-260: Patient View Design | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638173: CRE-260: Patient View Design | Story
574852 | FALSE | CRE-270: Cohort Status Notification | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638174: CRE-270: Cohort Status Notification | Story
574853 | FALSE | CRE-280: Cohort Dashboard | 574564 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638175: CRE-280: Cohort Dashboard | Story
574584 | FALSE | Registry Wizard |  | VIRP Build 1 - Sprint 5 | 5 pts | [5 empty] | Done | 919113: Registry Wizard | Epic
574931 | TRUE | PTL-050: Role and Registry Based Dynamic Menu and Workspace Content Creation | 574584 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638280: PTL-050: Role and Registry Based Dynamic Menu and Workspace Content Creation | Story
574585 | TRUE | User and Access Management |  | VIRP Build 1 - Sprint 5 | 5 pts | [5 empty] | Done | 919114: User and Access Management | Epic
574803 | FALSE | BR-020: Access Through Single Interface | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638117: BR-020: Access Through Single Interface | Story
574805 | FALSE | BR-040: Access from Multiple VA Facilities | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638120: BR-040: Access from Multiple VA Facilities | Story
574806 | FALSE | BR-050: Access to All Registries Through a Single Platform | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638121: BR-050: Access to All Registries Through a Single Platform | Story
574808 | FALSE | BR-060: Role-Based User Navigation and Privileges | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638122: BR-060: Role-Based User Navigation and Privileges | Story
574809 | FALSE | BR-070: Common User Role Set | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638123: BR-070: Common User Role Set | Story
574811 | FALSE | BR-090: Access Requirement Compliance | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638125: BR-090: Access Requirement Compliance | Story
575008 | FALSE | UDR-010: User Role and Registry Configuration | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638477: UDR-010: User Role and Registry Configuration | Story
575009 | FALSE | UDR-020: User Registry Access | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638478: UDR-020: User Registry Access | Story
575011 | FALSE | UDR-030: Unique User Roles for Each Registry | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638479: UDR-030: Unique User Roles for Each Registry | Story
575012 | FALSE | UDR-040: Registry User Role Configuration | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638480: UDR-040: Registry User Role Configuration | Story
575013 | FALSE | UDR-050: Menu/Tab Access By User Role | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638481: UDR-050: Menu/Tab Access By User Role | Story
575014 | FALSE | UDR-060: Menu Item Access by User Role | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638482: UDR-060: Menu Item Access by User Role | Story
575015 | FALSE | UDR-070: User Role Configuration Data | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638483: UDR-070: User Role Configuration Data | Story
575016 | FALSE | UDR-080: System Configuration Data | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638484: UDR-080: System Configuration Data | Story
575017 | FALSE | UDR-090: Configuration Change Log | 574585 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638485: UDR-090: Configuration Change Log | Story
574587 | FALSE | Reporting |  | VIRP Build 1 - Sprint 5 | 5 pts | [5 empty] | Done | 919115: Reporting | Epic
574969 | TRUE | REP-030: National, VISN, and Facility Level Reporting | 574587 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638369: REP-030: National, VISN, and Facility Level Reporting | Story
574971 | TRUE | REP-050: Exporting Reports | 574587 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638371: REP-050: Exporting Reports | Story
574588 | FALSE | Platform and Business |  | VIRP Build 1 - Sprint 5 | 5 pts | [5 empty] | Done | 919116: Platform and Business | Epic
574810 | TRUE | BR-080: Coordination With VA CDI Initiative | 574588 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done | 638124: BR-080: Coordination With VA CDI Initiative | Story
581499 | FALSE | Contract Deliverables |  | VIRP Build 1 - Sprint 5 | 5 pts |  | 230 | 255 |  |  | In Progress | 930825: _vI116Y3UEeew5esHMaxtpw | Epic
607907 | TRUE | VIRP - DOC - NF- Updated Product Build Checklist (October 20) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607908 | TRUE | Updated Guide Package (October 20) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607909 | TRUE | Updated Installation Guide (October 20) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607910 | TRUE | Updated Registry Implementation Developer's Guide (October 20) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607911 | TRUE | Updated Configuration Management Plan (October 20) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607912 | TRUE | Updated Source Code Repository Structure (October 20) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607913 | TRUE | VIRP - DOC - NF- Defect/Fix Status Report (October 20) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607914 | TRUE | VIRP - DOC - NF- Build Release Package (October 20) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607915 | TRUE | VIRP - DOC - NF- Weekly Risk Management Status Report (October 27) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607916 | TRUE | VIRP - DOC - NF- Work Breakdown Structure (October 27) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607917 | TRUE | VIRP - DOC - NF- Integrated Master Schedule (October 27) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607918 | TRUE | VIRP - DOC - NF- Onboarding Status Report (October 27) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607920 | TRUE | VIRP - DOC - NF- Weekly Risk Management Status Report (October 20) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607921 | TRUE | VIRP - DOC - NF- Work Breakdown Structure (October 20) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607922 | TRUE | VIRP - DOC - NF- Integrated Master Schedule (October 20) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607923 | TRUE | VIRP - DOC - NF- Onboarding Status Report (October 20) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607924 | TRUE | VIRP - DOC - NF- Updated Information Systems Continuity Plan (October 20) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607926 | TRUE | VIRP - DOC - NF- Sprint Plan (October 27) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
607927 | TRUE | VIRP - DOC - NF- Sprint Plan (October 20) | 581499 | VIRP Build 1 - Sprint 5 | 1 pt | [5 empty] | Done |  | Story
600511 | TRUE | VIRP - Delete function on Referrals page is displaying an error message |  | VIRP Build 1 - Sprint 5 |  | 8 |  |  |  |  | Resolved |  | Defect
600513 | TRUE | VIRP - Cohort Criteria - Back button should take them back to Registries and Cohorts home page |  | VIRP Build 1 - Sprint 5 | [6 empty] | Resolved |  | Defect
601248 | TRUE | VIRP - Add New Field" is missing when the user select User Defined Fields"" |  | VIRP Build 1 - Sprint 5 |  | 8 |  |  |  |  | Resolved |  | Defect
601250 | TRUE | VIRP - Cohorts>Activities>Sort Order field is required but is not allowing any values |  | VIRP Build 1 - Sprint 5 |  | 8 |  |  |  |  | Resolved |  | Defect
601277 | TRUE | VIRP - Error displays when user add a new Activity |  | VIRP Build 1 - Sprint 5 |  | 8 |  |  |  |  | Resolved |  | Defect
601419 | TRUE | VIRP - Cohorts>Work Streams>Edit>Is saving values with out user selecting Save |  | VIRP Build 1 - Sprint 5 |  | 8 |  |  |  |  | Resolved |  | Defect
601668 | TRUE | VIRP - Cohort > The left hand menu options should be disabled on the Cohort home page |  | VIRP Build 1 - Sprint 5 |  | 8 |  |  |  |  | Resolved |  | Defect
601925 | TRUE | VIRP - Administrator can not Delete the User |  | VIRP Build 1 - Sprint 5 |  | 8 |  |  |  |  | Resolved |  | Defect
608633 | TRUE | Deploy Build to DEV Environment |  | VIRP Build 1 - Sprint 5 | [6 empty] | Done |  | Task
608635 | TRUE | Finish Development and Code |  | VIRP Build 1 - Sprint 5 | [6 empty] | Done |  | Task
615060 | TRUE | Move VIRP ETLs to RTC source for SQA build. |  | VIRP Build 1 - Sprint 6 | [6 empty] | Done |  | Task
616563 | TRUE | Implement IAM Requested Items |  | VIRP Build 1 - Sprint 6 | [6 empty] | Done |  | Task
618406 | TRUE | Updated Database Objects |  | VIRP Build 1 - Sprint 6 | [6 empty] | Done |  | Task
601418 | TRUE | VIRP - Administration>Settings>View file is giving an exception error |  | VIRP Build 1 - Sprint 6 |  | 8 |  |  |  |  | Resolved |  | Defect
574584 | FALSE | Registry Wizard |  | VIRP Build 1 - Sprint 6 | 5 pts | [5 empty] | Done | 919113: Registry Wizard | Epic
574935 | TRUE | PTL-090: Role Based Menu and Page Presentation | 574584 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638284: PTL-090: Role Based Menu and Page Presentation | Story
574939 | TRUE | PTL-130: Default Registry Clinical Data | 574584 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638290: PTL-130: Default Registry Clinical Data | Story
574949 | TRUE | PTL-230: Role Based View and Update Capabilities | 574584 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638341: PTL-230: Role Based View and Update Capabilities | Story
574980 | TRUE | RW-040: Specification of Work Stream Activities | 574584 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638378: RW-040: Specification of Work Stream Activities | Story
574586 | FALSE | Non Functional Requirements |  | VIRP Build 1 - Sprint 6 | 5 pts | [5 empty] | In Progress | 919118: Non Functional Requirements | Epic
574905 | TRUE | FNM-030: ETL Naming Convention Elements | 574586 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638246: FNM-030: ETL Naming Convention Elements | Story
574991 | TRUE | SA-020: View and Manage Log Files | 574586 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638389: SA-020: View and Manage Log Files | Story
574992 | TRUE | SA-030: Configure Log File Size | 574586 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638390: SA-030: Configure Log File Size | Story
574993 | TRUE | SA-040: System Logger Controls | 574586 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638391: SA-040: System Logger Controls | Story
574995 | TRUE | SA-060: Editing Common Survey Questions/Answers | 574586 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638393: SA-060: Editing Common Survey Questions/Answers | Story
574587 | TRUE | Reporting |  | VIRP Build 1 - Sprint 6 | 5 pts | [5 empty] | Done | 919115: Reporting | Epic
574967 | TRUE | REP-010: Ad Hoc Report Creation | 574587 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638365: REP-010: Ad Hoc Report Creation | Story
574968 | TRUE | REP-020: Report Creation from Pre-existing Reports | 574587 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638367: REP-020: Report Creation from Pre-existing Reports | Story
574969 | FALSE | REP-030: National, VISN, and Facility Level Reporting | 574587 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638369: REP-030: National, VISN, and Facility Level Reporting | Story
574970 | TRUE | REP-040: Graphical Report Creation | 574587 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638370: REP-040: Graphical Report Creation | Story
574971 | FALSE | REP-050: Exporting Reports | 574587 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638371: REP-050: Exporting Reports | Story
574973 | TRUE | REP-060: Saving to User Reports Menu | 574587 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638372: REP-060: Saving to User Reports Menu | Story
574974 | TRUE | REP-070: Registry Metric Common Reports | 574587 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638373: REP-070: Registry Metric Common Reports | Story
574975 | TRUE | REP-080: Saving Reports to Report Store | 574587 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638374: REP-080: Saving Reports to Report Store | Story
574588 | TRUE | Platform and Business |  | VIRP Build 1 - Sprint 6 | 5 pts | [5 empty] | Done | 919116: Platform and Business | Epic
574796 | FALSE | BM-010: Encapsulate Common or Shared Methods | 574588 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638110: BM-010: Encapsulate Common or Shared Methods | Story
574797 | FALSE | BM-020: Extension of Core Business Manager Capability to Registry Specific Business Manager | 574588 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638111: BM-020: Extension of Core Business Manager Capability to Registry Specific Business Manager | Story
574798 | FALSE | BM-030: Implementation of Common and Registry-Specific Functionality | 574588 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638112: BM-030: Implementation of Common and Registry-Specific Functionality | Story
574799 | FALSE | BM-040: Verification of Manually Entered Referral Information | 574588 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Invalid | 638113: BM-040: Verification of Manually Entered Referral Information | Story
574800 | FALSE | BM-050: Saving of Survey Information | 574588 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638114: BM-050: Saving of Survey Information | Story
574801 | FALSE | BM-060: Survey Time Stamping | 574588 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638115: BM-060: Survey Time Stamping | Story
574802 | FALSE | BR-010: VIRP Management | 574588 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638116: BR-010: VIRP Management | Story
574804 | FALSE | BR-030: Preservation of Existing Functionality | 574588 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638118: BR-030: Preservation of Existing Functionality | Story
574810 | FALSE | BR-080: Coordination With VA CDI Initiative | 574588 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638124: BR-080: Coordination With VA CDI Initiative | Story
574812 | FALSE | BR-100: Quality Control Plan | 574588 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638126: BR-100: Quality Control Plan | Story
574813 | FALSE | BR-110: Release Acceptance | 574588 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638127: BR-110: Release Acceptance | Story
574589 | FALSE | Documentation and Training |  | VIRP Build 1 - Sprint 6 | 5 pts | [5 empty] | In Progress | 919117: Documentation and Training | Epic
575007 | TRUE | TS-020: Implementation Guide | 574589 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done | 638476: TS-020: Implementation Guide | Story
581499 | FALSE | Contract Deliverables |  | VIRP Build 1 - Sprint 6 | 5 pts |  | 230 | 255 |  |  | In Progress | 930825: _vI116Y3UEeew5esHMaxtpw | Epic
612288 | TRUE | Requirements Package (November 10) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612292 | TRUE | Product Operations Manual (November 10) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612239 | TRUE | Defect Resolution Plan (November 10) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612240 | TRUE | Backlog Plan (November 10) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612241 | TRUE | Weekly Risk Management Status Report (November 3) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612242 | TRUE | Weekly Risk Management Status Report (November 10) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612243 | TRUE | Work Breakdown Structure (November 3) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612244 | TRUE | Work Breakdown Structure (November 10) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612245 | TRUE | Integrated Master Schedule (November 3) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612247 | TRUE | Integrated Master Schedule (November 10) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612249 | TRUE | Onboarding Status Report (November 3) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612250 | TRUE | Onboarding Status Report (November 10) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612251 | TRUE | Contractor Project Management Plan (November 10) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612253 | TRUE | Sprint Plan (November 3) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612254 | TRUE | Sprint Plan (November 10) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
612256 | TRUE | Build Plan (November 10) | 581499 | VIRP Build 1 - Sprint 6 | 1 pt | [5 empty] | Done |  | Story
608636 | TRUE | Developer Testing in DEV Environment |  | VIRP Build 1 - Sprint 6 | [6 empty] | Done |  | Task
608640 | TRUE | Deploy Build to SQA Environment |  | VIRP Build 1 - Sprint 6 | [6 empty] | Done |  | Task
608642 | TRUE | Test Engineer Testing in SQA Environment |  | VIRP Build 1 - Sprint 6 | [6 empty] | Done |  | Task