## VSA-P2.5 Cover
VistA Services Assembler Phase 2.5 (VSA-P2.5)
Increment 4
VistA.js Request Validation Test Scripts
October 2016
Version: 1.1
Department of Veterans Affairs (VA)

## Revision History
Revision History
Date | Version | Description | Author
2016-10-11 | 1.1 | Update test steps | Apex Data Solutions
2016-08-09 | 1 | Increment 3 Final Version | Apex Data Solutions
2016-08-05 | 0.4 | Changed EDE Environment steps | Apex Data Solutions
2016-07-13 | 0.3 | Changed font to Arial 11 and added requirements to test steps. Added TC006 | Apex Data Solutions
2016-07-05 | 0.2 | Updated Template | Apex Data Solutions
2016-06-08 | 0.1 | Initial Version | Apex Data Solutions
Place latest revisions at top of table.

## Test Summary
Project Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) | Tester Name: | Enter Test Engineer
Test Phase: | Increment 4 | Date Executed: | Enter Date
Release/Build Number: | v3.0.10
Environment Tested: | VA EDE Environment
Prerequisites: | Access Code and Verify Code required. Internet Explorer required.
Category: | VistA.js Request Validation Test Scripts
Test Objective: | Test Request Validation functionality.
Requirements | Requirements Definitions | Test Results | Comments
IP | The system shall display the URL of the service to be tested.
IP | The system shall provide the user with the ability to test and execute a deployed Web service.
IP6 | VSA shall not manipulate (change) the consuming application’s user identity or authorization attributes.
IP0 | VSA generated services shall support the execution of a single RPC or routine API.
IP3 | VSA shall validate the presence of required information in ‘service requests’ including user identity, input parameters, federation routing, etc.
IP2 | VSA shall facilitate the logging of ‘service request’ transactions.
IP3 | VSA transaction logging data shall include date/time of transaction, ‘consuming application’, service invoked and destination VistA systems.
IP3 | VSA federation functionality shall facilitate routing of “service requests” to all VistA systems to which a specified patient is known (“treating facilities”).
IP8 | VSA shall facilitate the return of aggregated “service request” responses from multiple VistA systems that are incomplete due to time-out, non-responsiveness, etc. of one or more VistA systems.
IP3 | IP3 Refuse a request if required information not present in a service request
IP5 | VSA shall return standard HTTP error codes as related to Representational State Transfer (REST) services.
IP6 | VSA shall return VistA error information when exceptions occur in that environment.

## TC001
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC001_VistA.js Request Validation |  | Date_Executed: | Enter Date
Test_Description: | Execute a valid REST Call and verify the response. Also verify the transaction is logged correctly. |  | Test_Phase: | Increment 4
Requirements: | IP, IP, IP0, IP2 |  | Release/Build Number: | v3.0.10
Prerequisites: | Access Code and Verify Code required. Internet Explorer required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
Pre-requisites specific for test continued… | VPS GET SITES has been restified. | n/a | n/a
Step 1 | Access the VSA Server. Scroll to the bottom and locate Application Name: API Definition Browser. Click Launch Application. | Authorization agreement window is displayed.
Step 2 | Click Proceed. | VistA.js Federated REST Services API Browser vx.x.x page is displayed.
Step 3 | Select Available Servers. (Please select a server from the list displays an arrow pointing to the Servers link.) | A dropdown menu is displayed listing the following: baypines haley sanjuan westpalm Note: Listing of servers may differ depending on environment accessed.
Step 4 | Select baypines from the dropdown menu. | Login to baypines access window is displayed.
Step 5 | Enter an Access Code <AC> for the VistA instance. Enter a Verify Code <VC> for the VistA instance. Click Connect. | User is logged in successfully. baypines is the selected server. User's name is displayed in the top right corner of the web page. Log out button is available.
Step 6 | Select the Available Services link. | A dropdown menu is displayed listing the following: sync veterans session server patients rpcs
Step 7 | Select rpcs. | VistA.js RPC REST Service page is displayed. Services listed: Restify RPCS Service
Step 8 | Select RPCS. | VistA.js RPC REST Service page is displayed. List of RPCS Get and Post operations is displayed.
Step 9 | Scroll through and select POST /by-name/vps get sites/call link. | Operation window is expanded.
Step 10 | In the VPSSN Parameter field, type 666892222. Click Try it out! | Note: A security alert may display depending on the environment you are accessing. Click Yes to proceed. API Browser displays a post response : Curl Request URL Response Body Response Code Response Headers |  | IP IP
Step 11 | Select the Curl response: Click in front of the curl (in the response body) scrolling to the right, press and hold the shift key and then click at the end on the curl response. Copy the selected Curl line. (Rt-click Copy or ctrl+c) | The entire Curl line is selected and copied. |  | IP2
Step 12 | Open Notepad. Paste the curl line into Notepad. (Rt-click Paste or ctrl+v) | Curl line is displayed in a notepad and is editable.
Step 13 | Add a space at the end of the curl. Type -k after the space. | Display should be similar to: curl -X POST --header 'Content-Type: application/x-www-form-urlencoded' --header 'Accept: application/json' --header 'VJS-SESSION-TOKEN: 0921dad1-4114-417d-9d99-7788e4c4c977' -d 'VPSSN=666892222' 'https://DNSVSAAPPDEV11.aac.DNS:PORT/vistas/baypines/rpcs/by-name/vps%20get%20sites/call' -k
Step 14 | Open a VM using attachmate connection (EDE). | A command prompt window opens.
Step 15 | Authenticate using valid credentials. | Valid credentials have been accepted. Note: if the tester is already logged in an additional login is not necessary
Step 16 | Paste the modified curl line into the command line prompt . Press Enter. | A response is displayed.
Step 17 | Verify the following similar response is displayed: { "data": { "1": "672^SAN JUAN VAMC^3040101^^VAMC", "2": "516^BAY PINES VAMC^3010101^^VAMC", "3": "673^TAMPA (JAH VAH)^3020101^^VAMC", "4": "548^WEST PALM BEACH VAMC^3030101^^VAMC" }, "statusCode": 200 } | The following similar response is displayed: { "data": { "1": "672^SAN JUAN VAMC^3040101^^VAMC", "2": "516^BAY PINES VAMC^3010101^^VAMC", "3": "673^TAMPA (JAH VAH)^3020101^^VAMC", "4": "548^WEST PALM BEACH VAMC^3030101^^VAMC" }, "statusCode": 200 } |  | IP0
Step 18 | Leave Command Line window open for additional tests. | Command Line window remains open.

## TC002
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC002_VistA.js Request Validation |  | Date_Executed: | Enter Date
Test_Description: | Execute a REST Call with an RPC not saved on the server to verify the Server error response |  | Test_Phase: | Increment 4
Requirements: | IP6 |  | Release/Build Number: | v3.0.10
Prerequisites: | Access Code and Verify Code required. Internet Explorer required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
Pre-requisite specific for test | User has already accessed the API browser and is logged into the baypines server. |  | n/a
Step 1 | Access the API browser. Select the Available Services link. | A dropdown menu is displayed listing the following: sync veterans session server patients rpcs
Step 2 | Select rpcs. Select RPCS. | VistA.js RPC REST Service page is displayed. List of RPCS Get and Post operations is displayed.
Step 3 | Scroll through and select POST /by-name/vps get sites/call link. | Operation window is expanded.
Step 4 | In the VPSSN Parameter field, type 666000028 Click Try it out! | Note: A security alert may display depending on the environment you are accessing. Click Yes to proceed. API Browser displays a post response : Curl Request URL Response Body Response Code Response Headers
Step 5 | Select the Curl response: Click in front of the curl (in the response body) scrolling to the right, press and hold the shift key and then click at the end on the curl response. Copy the selected Curl line. (Rt-click Copy or ctrl+c) | The entire Curl line is selected and copied.
Step 6 | Open Notepad. Paste the curl line into Notepad. (Rt-click Paste or ctrl+v) | Curl line is displayed in a notepad and is editable.
Step 7 | Replace the name of the server using your own name. Add a space at the end of the curl. Type -k after the space. | Display should be similar to: curl -X POST --header 'Content-Type: application/x-www-form-urlencoded' --header 'Accept: application/json' --header 'VJS-SESSION-TOKEN: a9f7c761-59da-436d-bb20-7ba532be945d' -d 'VPSSN=666000028' 'https://IP:PORT/vistas/myname/rpcs/by-name/vps%20get%20sites/call' -k
Step 8 | Open a VM using attachmate connection (EDE). | Valid credentials have been accepted. Note: if the tester is already logged in, an additional login is not necessary
Step 9 | Authenticate using valid credentials. | Valid credentials have been accepted.
Step 10 | Paste the modified curl line into the command line prompt . Press Enter. | A response is displayed.
Step 11 | Verify the following similar response is displayed: { "error": "Target 'myname' is unknown to this federator." } | The following similar response is displayed: { "error": "Target 'myname' is unknown to this federator." } |  | IP6
Step 12 | Leave Command Line window open for additional tests. | Command Line window remains open.

## TC003
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC003_VistA.js Request Validation |  | Date_Executed: | Enter Date
Test_Description: | Execute a connection refuse error. |  | Test_Phase: | Increment 4
Requirements: | IP8 |  | Release/Build Number: | v3.0.10
Prerequisites: | Access Code and Verify Code required. Internet Explorer required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
Pre-requisite specific for test | User is already accessed the API browser and is logged into the baypines server. | n/a | n/a
Step 1 | Open a VM using attachmate connection (EDE). | A command prompt window opens.
Step 2 | Authenticate using valid credentials. | Valid credentials have been accepted. Note: If a session is already open, login will not be necessary
Step 3 | Type su - cacheusr. Enter the password for cacheusr. Press Enter. | Similar response displays: [cacheuser@DNSVSAAPPDEV11 "]$
Step 4 | Type cd vjs-environment/. Press Enter. | Similar response displays: [cacheuser@DNSVSAAPPDEV11 vjs-environment]$
Step 5 | Type source ./use_node.js. Press Enter. Type cd /srv/vista/vsa/user/ Press Enter. | Similar response displays: [cacheuser@DNSVSAAPPDEV11 user]$
Step 6 | Type ll. (lower case L's) Press Enter. | Similar response displays: total 16 drwxr-x---. 2 cacheusr cacheusr 4096 Oct 4 08:PORT certs drwxr-x---. 8 cacheusr cacheusr 4096 Oct 17 13:PORT vistajs_30104 drwxr-x---. 9 cacheusr cacheusr 4096 Oct 17 13:PORT vistajs_3081 drwxr-x---. 8 cacheusr cacheusr 4096 Aug 18 13:PORT vistajs-3092 [cacheusr@DNSVSAAPPDEV11 user]$
Step 7 | Type cd vistajs_30104 (note: access the build you are wanting) Type Enter. | Response (similar) displays: total 52 drwxr-x---. 13 cacheusr cacheusr 4096 Oct 17 09:PORT baypines -rw-r-----. 1 cacheusr cacheusr 1753 Oct 14 07:PORT baypines-config.js -rw-r-----. 1 cacheusr cacheusr 1758 Oct 14 08:PORT federator-config.js drwxr-x---. 13 cacheusr cacheusr 4096 Oct 14 08:PORT haley -rw-r-----. 1 cacheusr cacheusr 1747 Oct 14 08:PORT haley-config.js drwxr-x---. 13 cacheusr cacheusr 4096 Oct 14 08:PORT sanjuan -rw-r-----. 1 cacheusr cacheusr 1751 Oct 14 08:PORT sanjuan-config.js drwxr-x---. 13 cacheusr cacheusr 4096 Oct 17 09:PORT vjs-federator -rw-r-----. 1 cacheusr cacheusr 2929 Oct 14 07:PORT vjs-vista-router.js -rw-r-----. 1 cacheusr cacheusr 1701 Oct 14 08:PORT web-config.js drwxr-x---. 13 cacheusr cacheusr 4096 Oct 17 09:PORT webux drwxr-x---. 13 cacheusr cacheusr 4096 Oct 14 08:PORT westpalm -rw-r-----. 1 cacheusr cacheusr 1753 Oct 14 08:PORT westpalm-config.js [cacheusr@DNSVSAAPPDEV11 vistajs_30104]$
Step 8 | Type netstat -plnt ¦ grep node. Press Enter. | Similar response displays: (Not all processes could be identified, non-owned process info will not be shown, you would have to be root to see it all.) tcp 0 0 IP:PORT IP:* LISTEN 2046/node tcp 0 0 IP:PORT IP:* LISTEN 13139/node tcp 0 0 IP:PORT IP:* LISTEN 28488/node tcp 0 0 IP:PORT IP:* LISTEN 29658/node tcp 0 0 IP:PORT IP:* LISTEN 1742/node tcp 0 0 IP:PORT IP:* LISTEN 1584/node tcp 0 0 IP:PORT IP:* LISTEN 20639/node [cacheusr@DNSVSAAPPDEV11 vistajs_30104]$
Step 9 | Note the node that you want to stop: (Note: the server that should be stopped is haley - :PORT) Type kill 13139. Type Enter. Type netstat -plnt ¦ grep node. Press Enter. Verify the selected node is no longer listed. | Similar response displays: (Not all processes could be identified, non-owned process info will not be shown, you would have to be root to see it all.) tcp 0 0 IP:PORT IP:* LISTEN 2046/node tcp 0 0 IP:PORT IP:* LISTEN 28488/node tcp 0 0 IP:PORT IP:* LISTEN 29658/node tcp 0 0 IP:PORT IP:* LISTEN 1742/node tcp 0 0 IP:PORT IP:* LISTEN 1584/node tcp 0 0 IP:PORT IP:* LISTEN 20639/node [cacheusr@DNSVSAAPPDEV11 vistajs_30104]$
Step 10 | Access the API browser. Select the Available Services link. Note: If user is no longer logged into the API Browser, log into and access the baypines server. | A dropdown menu is displayed listing the following: sync veterans session server patients rpcs
Step 11 | Select rpcs. Select RPCS. | VistA.js RPC REST Service page is displayed. List of RPCS Get and Post operations is displayed.
Step 12 | Scroll through and select POST /by-name/vps get sites/call link. | Operation window is expanded.
Step 13 | In the VPSSN Parameter field, type 666892222 Click Try it out! | Note: A security alert may display depending on the environment you are accessing. Click Yes to proceed. API Browser displays a post response : Curl Request URL Response Body Response Code Response Headers
Step 14 | Select the Curl response: Click in front of the curl (in the response body) scrolling to the right, press and hold the shift key and then click at the end on the curl response. Copy the selected Curl line. (Rt-click Copy or ctrl+c) | The entire Curl line is selected and copied.
Step 15 | Open Notepad. Paste the curl line into Notepad. (Rt-click Paste or ctrl+v) | Curl line is displayed in a notepad and is editable.
Step 16 | Replace baypines with all. Add a space at the end of the curl. Type -k after the space. Press Enter. | Display should be similar to: curl -X POST --header 'Content-Type: application/x-www-form-urlencoded' --header 'Accept application/json' --header 'VJS-SESSION-TOKEN: 473c600d-b574-4039-bbec-69197a39d296' -d 'VPSSN=666892222' 'https://DNSVSAAPPDEV11 .aac.DNS:PORT/vistas/all/rpcs/by-name/vps%20get%20sites/call' -k
Step 17 | Open a VM using attachmate connection (EDE). | A command prompt window opens.
Step 18 | Authenticate using valid credentials. | Valid credentials have been accepted. Note: if the tester is already logged in an additional login is not necessary
Step 19 | Paste the modified curl line into the command line prompt . Press Enter. | A response is displayed.
Step 20 | Verify the following similar response is displayed: { "haley": { "code": "ECONNREFUSED", "error": "Connection Refused" }, "westpalm": { "error": "Session is no longer valid. Please log in again.", "statusCode": 400 }, "sanjuan": { "error": "Session is no longer valid. Please log in again.", "statusCode": 400 }, "baypines": { "data": { "1": "672^SAN JUAN VAMC^3040101^^VAMC", "2": "516^BAY PINES VAMC^3010101^^VAMC", "3": "673^TAMPA (JAH VAH)^3020101^^VAMC", "4": "548^WEST PALM BEACH VAMC^3030101^^VAMC" }, "statusCode": 200 } }[cacheusr@DNSVSAAPPDEV11 vistajs_30104]$ | The following similar response is displayed: { "haley": { "code": "ECONNREFUSED", "error": "Connection Refused" }, "westpalm": { "error": "Session is no longer valid. Please log in again.", "statusCode": 400 }, "sanjuan": { "error": "Session is no longer valid. Please log in again.", "statusCode": 400 }, "baypines": { "data": { "1": "672^SAN JUAN VAMC^3040101^^VAMC", "2": "516^BAY PINES VAMC^3010101^^VAMC", "3": "673^TAMPA (JAH VAH)^3020101^^VAMC", "4": "548^WEST PALM BEACH VAMC^3030101^^VAMC" }, "statusCode": 200 } }[cacheusr@DNSVSAAPPDEV11 vistajs_30104]$ |  | IP3 IP8
Step 21 | Leave Command Line window open for additional tests. | Command Line window remains open.
Step 22 | Note: haley needs to be restarted: cd haley nohup ca-apm-run node_modules/vsa-server/bin/vsa-server start & To verify haley has restarted. netstat -plnt ¦ grep node | Command Line window remains open.

## TC004
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC004_VistA.js Request Validation |  | Date_Executed: | Enter Date
Test_Description: | Execute a REST Call with no federated routing |  | Test_Phase: | Increment 4
Requirements: | IP3 |  | Release/Build Number: | v3.0.10
Prerequisites: | Access Code and Verify Code required. Internet Explorer required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
Pre-requisite specific for test | User is already accessed the API browser and is logged into the baypines server. VPS GET ALLERGIES has been restified. | n/a | n/a
Step 1 | Access the API browser. Select the Available Services link. | A dropdown menu is displayed listing the following: sync veterans session server patients rpcs
Step 2 | Select rpcs. Select RPCS. | VistA.js RPC REST Service page is displayed. List of RPCS Get and Post operations is displayed.
Step 3 | Scroll through and select POST /by-name/vps get allergies/call link. | Operation window is expanded.
Step 4 | In the VPSDFN Parameter field, type 236. Click Try it out! | Note: A security alert may display depending on the environment you are accessing. Click Yes to proceed. API Browser displays a post response : Curl Request URL Response Body Response Code Response Headers
Step 5 | Select the Curl response: Click in front of the curl (in the response body) scrolling to the right, press and hold the shift key and then click at the end on the curl response. Copy the selected Curl line. (Rt-click Copy or ctrl+c) | The entire Curl line is selected and copied.
Step 6 | Open Notepad. Paste the curl line into Notepad. (Rt-click Paste or ctrl+v) | Curl line is displayed in a notepad and is editable.
Step 7 | Type other where the server is named. Add a space at the end of the curl. Type -k after the space. | Display should be similar to: curl -X POST --header 'Content-Type: application/x-www-form-urlencoded' --header 'Accept: application/json' --header 'VJS-SESSION-TOKEN: ae5503a4-5371-4286-b60b-49e8c01d823d' -d 'VPSDFN=236' 'https://IP:PORT/vistas/other/rpcs/by-name/vps%20get%20allergies/call' -k
Step 8 | Open a VM using attachmate connection (EDE). | Valid credentials have been accepted. Note: if the tester is already logged in, an additional login is not necessary
Step 9 | Authenticate using valid credentials. | Valid credentials have been accepted.
Step 10 | Paste the modified curl line into the command line prompt . Press Enter. | A response is displayed.
Step 11 | Verify the following similar response is displayed: response displays similar to: { "error": "Target 'other' is unknown to this federator." } | The following similar response is displayed: { "error": "Target 'other' is unknown to this federator." } |  | IP3
Step 12 | Leave Command Line window open for additional tests. | Command Line window remains open.

## TC005
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC005_VistA.js Request Validation |  | Date_Executed: | Enter Date
Test_Description: | Execute a REST Call without the required Input Parameter |  | Test_Phase: | Increment 4
Functional_Requirements: | IP6 |  | Release/Build Number: | v3.0.10
Prerequisites: | Access Code and Verify Code required. Internet Explorer required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
Pre-requisite specific for test | User is already accessed the API browser and is logged into the baypines server. VPS GET ALLERGIES has been restified. | n/a | n/a
Step 1 | Access the API browser. Select the Available Services link. | A dropdown menu is displayed listing the following: sync veterans session server patients rpcs
Step 2 | Select rpcs. Select RPCS. | VistA.js RPC REST Service page is displayed. List of RPCS Get and Post operations is displayed.
Step 3 | Scroll through and select POST /by-name/vps get allergies/call link. | Operation window is expanded.
Step 4 | In the VPSDFN Parameter field, type 236. Click Try it out! | Note: A security alert may display depending on the environment you are accessing. Click Yes to proceed. API Browser displays a post response : Curl Request URL Response Body Response Code Response Headers
Step 5 | Select the Curl response: Click in front of the curl (in the response body) scrolling to the right, press and hold the shift key and then click at the end on the curl response. Copy the selected Curl line. (Rt-click Copy or ctrl+c) | The entire Curl line is selected and copied.
Step 6 | Open Notepad. Paste the curl line into Notepad. (Rt-click Paste or ctrl+v) | Curl line is displayed in a notepad and is editable.
Step 7 | Remove the patient dfn. Add a space at the end of the curl. Type -k after the space. | Display should be similar to: curl -X POST --header 'Content-Type: application/x-www-form-urlencoded' --header 'Accept: application/json' --header 'VJS-SESSION-TOKEN: 1a047a08-33fc-44ce-822a-5911bb766266' -d 'VPSDFN=' 'https://IP:PORT/vistas/baypines/rpcs/by-name/vps%20get%20allergies/call'
Step 8 | Open a VM using attachmate connection (EDE). | Valid credentials have been accepted. Note: if the tester is already logged in, an additional login is not necessary
Step 9 | Authenticate using valid credentials. | Valid credentials have been accepted.
Step 10 | Paste the modified curl line into the command line prompt . Press Enter. | A response is displayed. |  | IP6
Step 11 | Verify the following similar response is displayed: { "data": { "0": "99^PATIENT DFN not sent" }, "statusCode": 200 } | The following similar response is displayed: { "data": { "0": "99^PATIENT DFN not sent" }, "statusCode": 200 }
Step 12 | Leave Command Line window open for additional tests. | Command Line window remains open.

## TC006
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC006_VistA.js Request Validation |  | Date_Executed: | Enter Date
Test_Description: | Execute a REST Call with access to all vistas |  | Test_Phase: | Increment 4
Functional_Requirements: | IP5 |  | Release/Build Number: | v3.0.10
Prerequisites: | Access Code and Verify Code required. Internet Explorer required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
Pre-requisite specific for test | User has already accessed the API browser and is logged into the baypines server. | n/a | n/a
Step 1 | Select the Available Services link. Select rpcs. Select RPCS. | VistA.js RPC REST Service page is displayed. List of RPCS Get and Post operations is displayed.
Step 2 | Select GET /by-name/{rpcName}. Enter VPS GET into the rpcName Parameter Value field. Click Try it out! | API Browser displays a response: Curl Request URL Response Body: { "error": "No matching RPC Swagger definition found for: VPS GET", "statusCode": 400 } Response Code: 400 Response Headers |  | IP5
Step 3 | Select Session in the Available Services dropdown menu. | Session Authentication Management page is displayed. The following operations are listed and available for selection: default Login Session
Step 4 | Select Login. Select Post /login/by-av/new. | Post /login/by-av/new operation expands.
Step 5 | Enter access code;verify code into the credentials Value text field. Note: User the current users credentials. | access code;verify code is entered into the Value text field.
Step 6 | Click Try it out! Note: A security alert may display depending on the environment you are accessing. If displayed, click Yes. | API Browser displays a response: Curl Request URL Response Body: Logged in users information is displayed. Response Code: 200 Response Headers |  | IP5
Step 7 | Select the Curl response: Click in front of the curl (in the response body) scrolling to the right, press and hold the shift key and then click at the end on the curl response. Copy the selected Curl line. (Rt-click Copy or ctrl+c) | The entire Curl line is selected and copied.
Step 8 | Open Notepad. Paste the curl line into Notepad. (Rt-click Paste or ctrl+v) Note: This will be used after the next test. | Curl line is displayed in a notepad and is editable.
Step 9 | Using an incorrect access code and verify code, enter the acess code;verify code into the credentials Value text field. Click Try it out! | API Browser displays a response: Curl Request URL Response Body: { "error": "Invalid Kernel logon credentials. [Security Type: Not a valid ACCESS CODE/VERIFY CODE pair.] ", "data": { "code": "182305", "error type": "XSAPXACC - A/V Logon", "fault actor": "XSAPXACC - A/V Logon", "fault string": "Internal Application Error" }, "statusCode": 401 } Response Code: 401 Response Headers |  | IP5
Step 10 | Leave Command Line window open for additional tests. | Command Line window remains open.

## TC007
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC007_VistA.js Request Validation |  | Date_Executed: | Enter Date
Test_Description: | Execute a REST Call with access to all vistas |  | Test_Phase: | Increment 4
Functional_Requirements: | IP3 |  | Release/Build Number: | v3.0.10
Prerequisites: | Access Code and Verify Code required. Internet Explorer required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
Pre-requisite specific for test | User has access to all vista servers. User is already accessed the API browser and is logged into the baypines server. VPS GET ALLERGIES has been restified. | n/a | n/a
Step 1 | Access the API browser. Select the Available Services link. | A dropdown menu is displayed listing the following: sync veterans session server patients rpcs
Step 2 | Select rpcs. Select RPCS. | VistA.js RPC REST Service page is displayed. List of RPCS Get and Post operations is displayed.
Step 3 | Scroll through and select POST /by-name/vps get allergies/call link. | Operation window is expanded.
Step 4 | In the VPSDFN Parameter field, type 60. Click Try it out! | Note: A security alert may display depending on the environment you are accessing. Click Yes to proceed. API Browser displays a post response : Curl Request URL Response Body Response Code Response Headers
Step 5 | Select the Curl response: Click in front of the curl (in the response body) scrolling to the right, press and hold the shift key and then click at the end on the curl response. Copy the selected Curl line. (Rt-click Copy or ctrl+c) | The entire Curl line is selected and copied.
Step 6 | Open Notepad. Paste the curl line into Notepad. (Rt-click Paste or ctrl+v) | Curl line is displayed in a notepad and is editable.
Step 7 | Type all where the server is named. Add a space at the end of the curl. Type -k after the space. | Display should be similar to: curl -X POST --header 'Content-Type: application/x-www-form-urlencoded' --header 'Accept: application/json' --header 'VJS-SESSION-TOKEN: ae5503a4-5371-4286-b60b-49e8c01d823d' -d 'VPSDFN=236' 'https://IP:PORT/vistas/all/rpcs/by-name/vps%20get%20allergies/call' -k
Step 8 | Open a VM using attachmate connection (EDE). | Valid credentials have been accepted. Note: if the tester is already logged in, an additional login is not necessary
Step 9 | Authenticate using valid credentials. | Valid credentials have been accepted.
Step 10 | Paste the modified curl line into the command line prompt . Press Enter. | A response is displayed.
Step 11 | Verify the correct response is displayed for baypines. | The correct response is displayed for baypines.
Step 12 | Verify the following is displayed for westpalm: { "westpalm": { "error": "Session is no longer valid. Please log in again.", "statusCode": 400 } | The following is displayed for westpalm: { "westpalm": { "error": "Session is no longer valid. Please log in again.", "statusCode": 400 }
Step 13 | Verify the following is displayed for haley: { "westpalm": { "error": "Session is no longer valid. Please log in again.", "statusCode": 400 } | The following is displayed for westpalm: { "westpalm": { "error": "Session is no longer valid. Please log in again.", "statusCode": 400 }
Step 14 | Using the previous modified Curl command: Replace all with westpalm. | Display should be similar to: curl -X POST --header 'Content-Type: application/x-www-form-urlencoded' --header 'Accept: application/json' --header 'VJS-SESSION-TOKEN: 379c4ca0-4f36-49b5-a920-36a261e9c706' -d 'VPSDFN=60' 'https://IP:PORT/vistas/westpalm/rpcs/by-name/vps%20get%20allergies/call' -k
Step 15 | Paste the modified curl line into the command line prompt . Press Enter. | A response is displayed.
Step 16 | Verify the correct response is displayed for westpalm. | The correct response is displayed for westpalm.
Step 17 | Using the previous modified Curl command: Replace westpalm with haley. | Display should be similar to: curl -X POST --header 'Content-Type: application/x-www-form-urlencoded' --header 'Accept: application/json' --header 'VJS-SESSION-TOKEN: 379c4ca0-4f36-49b5-a920-36a261e9c706' -d 'VPSDFN=60' 'https://IP:PORT/vistas/haley/rpcs/by-name/vps%20get%20allergies/call' -k
Step 18 | Paste the modified curl line into the command line prompt . Press Enter. | A response is displayed.
Step 19 | Verify the correct response is displayed for haley. | The correct response is displayed for haley.
Step 20 | Using the previous modified Curl command: Replace haley with all. | Display should be similar to: curl -X POST --header 'Content-Type: application/x-www-form-urlencoded' --header 'Accept: application/json' --header 'VJS-SESSION-TOKEN: 379c4ca0-4f36-49b5-a920-36a261e9c706' -d 'VPSDFN=60' 'https://IP:PORT/vistas/all/rpcs/by-name/vps%20get%20allergies/call' -k
Step 21 | Paste the modified curl line into the command line prompt . Press Enter. | A response is displayed.
Step 22 | Verify a correct response is returned for all three vistas (baypines, haley, & westpalm). | The correct responses are returned for baypines, haley, and westpalm. |  | IP3
Step 23 | Leave Command Line window open for additional tests. | Command Line window remains open.

## TC008
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC008_VistA.js Request Validation |  | Date_Executed: | Enter Date
Test_Description: | Verify the requirement IP3: VSA transaction logging data shall include date/time of transaction, ‘consuming application’, service invoked and destination VistA systems. |  | Test_Phase: | Increment 4
Functional_Requirements: | IP3, IP3 |  | Release/Build Number: | v3.0.10
Prerequisites: | Access Code and Verify Code required. Internet Explorer required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
Pre-requisite specific for test | User already has access to vjs-docker in the command line window. | n/a | n/a
Step 1 | Type docker exec -it webux bash at the command line prompt. Press Enter. | Response returned (similar output below): [root@875626ea5746 /]#
Step 2 | Type ll (lower case L's). Press Enter. | Response returned.
Step 3 | Type cd vistajs. Press Enter. | Changed directory response (similar output) below: [root@875626ea5746 vistajs]#
Step 4 | Type cd log. Press Enter. | Response returned (similar output)below: [root@875626ea5746 log]#
Step 5 | Type ll (lower case L's). Press Enter. | Response returned (similar output below): requests-VistA Services Assembler acti onserver-IP.log Note: Look for the log with the most recent date. That is the log that should be accessed.
Step 6 | Type cat r. Press the tab key. Add the log that will be accessed. (i.e. 4.log) to the partial log file name. Press Enter. | Log file will be displayed.
Step 7 | Verify the logs displayed have the following labels: The instance name The time of the request The url/resource they are accessing The IP of the request (will use X-FORWARDED-FOR if sent) The username if available. If not, then "Anonymous" is logged Log Type (Incoming Request, Call to VistA site) Time of log entry | The following (similar) information is displayed: {"instanceName":"webux", "requestTime":"2016-10-11T15:PORT:PORT.680Z", "ip":"IP", "username":"Anonymous", "url":"/api/vsa-api-browser/vistas/baypines/rpcs/definition", "logType":"Incoming Request", "level":"requests", "message":"", "timestamp":"2016-10-11T15:PORT:PORT.680Z"} |  | IP3 IP3
Step 8 | Type Exit. Press Enter. Type Exit. Press Enter. | Command Line window closes.

## DataSheet
| TC1 | TC2 | TC3 | TC4 | TC5
RPC | /by-name/vps-get-sites/call | /by-name/vps-get-sites/call | /by-name/vps-get-sites/call | /by-name/vps-get-allergies/call | /by-name/vps-get-allergies/call
NAME | VPSSN | VPSSN
VALUE | 666892222 | 666000001
NAME_1
VALUE_1
NAME_2
VALUE_2
DEST | baypines | baypines | haley | baypine | baypines
SERVER | baypines | baypines | baypines | baypines | baypines
APP | IP
OUTPUT | "1": "672^SAN JUAN VAMC^3040101^^VAMC"
OUTPUT_1 | "2": "516^BAY PINES VAMC^3010101^^VAMC"
OUTPUT_2 | 3: "673^TAMPA (JAH VAH)^3020101^^VAMC" |  |  | Unknown VistA target
ERR_6 | "4": "548^WEST PALM BEACH VAMC^3030101^^VAMC |  |  |  | 99^PATIENT DFN not sent
ERR_4
ERR |  | error: "RPC REST definition not found for
ERR_1 |  |  | couldn't connect to host

## Approval Signatures
Approval Signatures
REVIEW DATE:
SCRIBE: Apex Data Solutions
Signed:
Mike Davis, Business Sponsor | Date
Russell Holt, Program Manager | Date
Lori Warren, Project Manager | Date