## VSA-P2.5 Cover
VistA Services Assembler Phase 2.5 (VSA-P2.5)
Increment 4
EDE Smoke Test Case
October 2016
Version: 1.1
Department of Veterans Affairs (VA)

## Revision History
Revision History
Date | Version | Description | Author
2016-09-28 | 1.1 | Update of Test Steps | Apex Data Solutions
2016-08-05 | 1 | Increment 3 Final Version | Apex Data Solutions
2016-08-01 | 0.4 | Updated test with 3.0.8-beta.4 changes | Apex Data Solutions
2016-07-11 | 0.3 | Updated Font to Arial 11 | Apex Data Solutions
2016-06-30 | 0.2 | Updated to New Template | Apex Data Solutions
2016-06-08 | 0.1 | Initial Version | Apex Data Solutions
Place latest revisions at top of table.

## Test Summary
Project Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) | Tester Name: | Enter Test Engineer
Test Phase: | Increment 4 | Date Executed: | Enter Date
Release/Build Number: | v3.0.10
Environment Tested In: | VA EDE Environment
Prerequisites: | Two (2) users for each Vista will be needed. UserA - RPC Wizard UserB - API Browser Access Code and Verify Code required. Internet Explorer Browser is required.
Category: | VistA.js Smoke Test Case
Test Objective: | To know whether the essential functionality of the applications are working or not.
Test Case Name_Number: | Test Results | Comments
TC001_SMOKE TEST_VistAjsSplashPage
TC001_SMOKE TEST_RPC Wizard
TC002_SMOKE TEST_RPC Wizard
TC003_SMOKE TEST_RPC Wizard
TC004_SMOKE TEST_RPC Wizard
TC001_SMOKE TEST_API Browser
TC002_SMOKE TEST_API Browser
TC003_SMOKE TEST_API Browser
TC004_SMOKE TEST_API Browser

## VistAjsSplashPage
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC001_SMOKE TEST_VistAjsSplashPage |  | Date_Executed: | Enter Date
Test_Description: | To know whether the essential functionality of the applications are working or not. |  | Test_Phase: | Increment 4
Requirements: | n/a |  | Release/Build Number: | v3.0.10
Prerequisites: | Two (2) users for each Vista will be needed. UserA - RPC Wizard UserB - API Browser Access Code and Verify Code required. Internet Explorer Browser is required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
Step 1 | Open an Internet Explorer browser. | Internet Explorer browser opens.
Step 2 | Launch the Primary VistA.js Splash page: https://.DNS:PORT/ | Note: Certificate Error Notification page may not display depending on the environment you are accessing. Warning message: There is a problem with this website security certificate. The security certificate presented by this website was not issued by a trusted certificate authority. The security certificate presented by this website was issued for a different website's address. Security certificate problems may indicate an attempt to fool you or intercept any data you send to the server. We recommend that you close this webpage and do not continue to this website.
Step 3 | If Certificate Error Notification is displayed: Select "Continue to this website (not recommended)." If Certificate Error Notification is not displayed: Verify the VSA Server page is displayed. | VSA SERVER page should be displayed: VSA Server The Highly Configurable, Reusable, Open Source and Scalable Enterprise API Server Congratulations! Your VistA Services Assembled Server is working and ready to improve the lives of United States Veterans. About VSA Server VSA stands for VistA Services Assembler. VSA Server is a component of VSA, providing a multi-transport API Server generable to the VSA VistA.js Platform and featuring integrated cluster capabilities, extensible transport-agnostic, action-based server APIs, and delayed tasks. VSA Server is based on Evan Tahler's forward-thinking actionhero framework, rebranded and streamlined to support VSA VistA.js and potentially other VA open source healthcare initiatives. VSA Server was built from the ground up to include all the features you expect from a modern API framework. This includes all the features listed below and more. VSA Server also knows when to get out of the way to allow you to customize your stack to fit your needs. This Server Server Information: Server Name: federator******** VSA Server Version: x.x.x Installed Applications: Application Name: API Definition Browser Description: Permits viewing of API swagger definitions. Version: x.x.x URL: Launch Application Application Name: VSA RPC Wizard Description: An application for restification of VistA RPCs Version: x.x.x URL: Launch Application
Step 4 | Scroll to the bottom and locate Application Name: VSA RPC Wizard. Click Launch Application url. | The RPC Wizard screen displays in the background. Authorization agreement window is displayed.
Step 5 | Click Proceed. | VistA.js RPC REST Wizard vx.x.x page is displayed.
Step 6 | Launch the API Definition Browser from https://.DNS:PORT/vsa-rpc-wizard . | Certificate Error Notification page is displayed. Note: Certificate Error Notification page may not display depending on the environment you are accessing.
Step 7 | If Certificate Error Notification is displayed: Select "Continue to this website (not recommended)." If Certificate Error Notification is not displayed: Verify the VSA Server page is displayed. | VSA Server page is displayed.
Step 8 | Scroll to the bottom and locate Application Name: API Definition Browser. Click Launch Application url. | The API browser screen displays in the background. Authorization agreement window is displayed.
Step 9 | Click Proceed. | VistA.js Federated REST Services API Browser vx.x.x page is displayed.

## RPC_TC001
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC001_SMOKE TEST_RPC Wizard |  | Date_Executed: | Enter Date
Test_Description: | To know whether the essential functionality of the applications are working or not. |  | Test_Phase: | Increment 4
Requirements: | n/a |  | Release/Build Number: | v3.0.10
Prerequisites: | Two (2) users for each Vista will be needed. UserA - RPC Wizard UserB - API Browser Access Code and Verify Code required. Internet Explorer Browser is required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
Step 1 | Launch the RPC Wizard Splash: https://.DNS:PORT/vsa-rpc-wizard Note: If continuing after VistAjsSplashpage test, skip to Step 5.. | Certificate Error Notification page is displayed. Note: Certificate Error Notification page may not display depending on the environment you are accessing.
Step 2 | If Certificate Error Notification is displayed: Select "Continue to this website (not recommended)." If Certificate Error Notification is not displayed: Verify the VSA Server page is displayed. | VSA Server page is displayed.
Step 3 | Scroll to the bottom and locate Application Name: VSA RPC Wizard. Click Launch Application url. | The RPC Wizard screen displays in background. Authorization agreement window is displayed.
Step 4 | Click Proceed. | VistA.js RPC REST Wizard page is displayed.
Step 5 | Select Vista Servers. (Please select a server from the list displays an arrow pointing to the VistA Servers link.) | A dropdown menu is displayed listing the following: baypines haley sanjuan westpalm Note: Listing of servers may differ depending on environment.
Step 6 | Click baypines. | Login to baypines access window is displayed.
Step 7 | Enter an Access Code <AC> for the VistA instance. Enter a Verify Code <VC> for the VistA instance. Click Connect. | User is logged in successfully. Select RPC page is displayed. baypines is the selected server. User's name is located in the upper right hand corner of the application. Log out button is available.
Step 8 | Type the following into the RPC Search test field: VPS GET ALLERGIES Verify as you begin to populate the text field, all applicable RPCs populate in the search results area until VPS GET ALLERGIES is the only RPC listed. | Search results displays (1) result: VPS GET ALLERGIES.
Step 9 | Click VPS GET ALLERGIES link. | Notice message window is displayed: All the fields marked with * are required Note: Notice only displays on initial RPC search.
Step 10 | Click Proceed. | Edit Definition page is displayed.
Step 11 | Verify VPS GET ALLERGIES Edit Definition displays the following Summary information: Name: VPS GET ALLERGIES Summary: GET^VPSALL01(.tRESULT,VPSDFN) Description: Called by the Vetlink Kiosk system. VPS GET ALLEGIES retrieves patient allergy data stored in an entry or entries in the PATIENT ALLERGIES file (120.8). The retrieved data is made available to the Vetlink system. | The Summary information displays the following: Name: VPS GET ALLERGIES Summary: GET^VPSALL01(.tRESULT,VPSDFN) Description: Called by the Vetlink Kiosk system. VPS GET ALLEGIES retrieves patient allergy data stored in an entry or entries in the PATIENT ALLERGIES file (120.8). The retrieved data is made available to the Vetlink system.
Step 12 | Verify VPS GET ALLERGIES Edit Definition displays the following Input Parameters information: VPSDFN Name: VPSDFN Description: The patient DFN is used to collect the various allergy related fields stored in the Adverse Reaction Tracking package. Parameter Type: LITERAL Swagger Type: String Required: Checkbox checked | The Input Parameters information displays the following: Name: VPSDFN Description: The patient DFN is used to collect the various allergy related fields stored in the Adverse Reaction Tracking package. Parameter Type: LITERAL Swagger Type: String Required: Checkbox checked
Step 13 | Verify VPS GET ALLERGIES Edit Definition displays the following Output Parameter information: Return Parameter Description: Data taken from an entry or entries stored in the PATIENT ALLERGIES field is defined 3. iens are the internal entry numbers at which the allergy record is stored. This element can have either the entry level ien for non-multiple or it can have both the entry level ien and the sub-entry ien. It is constructed as "sub-entry ien, entry ien" for data coming from sub-files (multiples)4. field number is the numeric field reference from where the data has been retrieved5. field label is the name of the field6. data value is the data that was retrieved from the fieldfile (120.8) are populated into the local array. Each element in the subscripted array is constructed as:subscriptedArray(n)= "file number^iens (sub-entry ien, ien)^field number^field label^data value"1. where n is an incremental number that acts as an index in the array2. file number is the file or sub-file reference from where the Return Type: ARRAY | The Output Parameter information displays the following: Return Parameter Description: Data taken from an entry or entries stored in the PATIENT ALLERGIES field is defined 3. iens are the internal entry numbers at which the allergy record is stored. This element can have either the entry level ien for non-multiple or it can have both the entry level ien and the sub-entry ien. It is constructed as "sub-entry ien, entry ien" for data coming from sub-files (multiples)4. field number is the numeric field reference from where the data has been retrieved5. field label is the name of the field6. data value is the data that was retrieved from the fieldfile (120.8) are populated into the local array. Each element in the subscripted array is constructed as:subscriptedArray(n)= "file number^iens (sub-entry ien, ien)^field number^field label^data value"1. where n is an incremental number that acts as an index in the array2. file number is the file or sub-file reference from where the Return Type: ARRAY
Step 14 | Edit the Description field for Input Parameter VPSDFN by adding the following: Patient Allergies | The Description field for VPSDFN now displays the following: Patient Allergies
Step 15 | Click Next. | Review Swagger page is displayed.
Step 16 | Scroll through the Swagger information. Locate the recent modification that was completed on the Edit Definition page. | Swagger information has the following: "parameters": [ { "name": "VPSDFN", "description": "Patient Allergies [Fileman Type: LITERAL]", "in": "formData", "type": "string", "required": true }
Step 17 | Click Next. | The Save Definition page is displayed. Save Swagger button is available and enabled.
Step 18 | Click Save Swagger. | Message displays: Post successful! Click 'Complete' to reset the wizard.
Step 19 | Click Complete. | Select RPC page is displayed.
Step 20 | Use the Select Existing Definition dropdown menu. Select VPS GET ALLERGIES | The Edit Definition page is displayed.
Step 21 | Verify the changes that were made were saved successfully. | The Description field for VPSDFN now displays the following: Patient Allergies
Step 22 | Click Prev. | The Select RPC page is displayed.

## RPC_TC002
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC002_SMOKE TEST_RPC Wizard |  | Date_Executed: | Enter Date
Test_Description: | To know whether the essential functionality of the applications are working or not. |  | Test_Phase: | Increment 4
Requirements: | n/a |  | Release/Build Number: | v3.0.10
Prerequisites: | Two (2) users for each Vista will be needed. UserA - RPC Wizard UserB - API Browser Access Code and Verify Code required. Internet Explorer Browser is required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
| Note: if you are no longer logged into theVistA.js RPC REST Wizard , please access and log in again. |  | n/a
Step 1 | Click baypines in the Server dropdown menu. Select haley. | Login to haley access window is displayed.
Step 2 | Enter an Access Code <AC> for the VistA instance. Enter a Verify Code <VC> for the VistA instance. Click Connect. | User is logged in successfully. Select RPC page is displayed. haley is the selected server. User's name is located in the upper right hand corner of the application. Log out button is available.
Step 3 | Type the following into the RPC Search test field: VPS FULLSSN Verify as you begin to populate the text field, all applicable RPCs populate in the search results area until VPS FULLSSN is the only RPC listed. | Search results displays (1) result: VPS FULLSSN.
Step 4 | Click VPS FULLSSN link. Note: Notice only displays on initial RPC search. If notice displays, click Proceed. | Edit Definition page is displayed.
Step 5 | Verify VPS FULLSSN Edit Definition displays the following Summary information: Name: VPS FULLSSN Summary: FULLSSN^VPSRPC5(.tRESULT,VPSID) Description: Returns a list of patients with SSNs that match the value stored in ID. | The Summary information displays the following: Name: VPS FULLSSN Summary: FULLSSN^VPSRPC5(.tRESULT,VPSID) Description: Returns a list of patients with SSNs that match the value stored in ID.
Step 6 | Verify VPS FULLSSN Edit Definition displays the following Input Parameters information: VPSID Name: VPSID Description: Patient's 9-digit SSN value. Parameter Type: LITERAL Swagger Type: String Required: Checkbox checked | The Input Parameters information displays the following: VPSID Name: VPSID Description: Patient's 9-digit SSN value. Parameter Type: LITERAL Swagger Type: String Required: Checkbox checked
Step 7 | Verify VPS FULLSSN Edit Definition displays the following Output Parameter information: Return Parameter Description: LST is an array passed by reference and will contain a list of patients that have an SSN matching the value in SSN. The results will have for each matching patient the patient's IEN in file #2, full name, date of birth, and SSN. Return Type: ARRAY | The Output Parameter information displays the following: Return Parameter Description: LST is an array passed by reference and will contain a list of patients that have an SSN matching the value in SSN. The results will have for each matching patient the patient's IEN in file #2, full name, date of birth, and SSN. Return Type: ARRAY
Step 8 | Edit the Description field for Output Parameter Return Parameter by adding the following: Patient Information | The Description field for Output Parameter Return Parameter now displays the following: Patient Information
Step 9 | Click Next. | Review Swagger page is displayed.
Step 10 | Scroll through the Swagger information. Locate the recent modification that was completed on the Edit Definition page. | Swagger information has the following: "responses": { "200": { "description": "Patient Information", "schema": { "$ref": "#/definitions/ARRAY" }
Step 11 | Click Next. | The Save Definition page is displayed. Save Swagger button is available and enabled.
Step 12 | Click Save Swagger. | Message displays: Post successful! Click 'Complete' to reset the wizard.
Step 13 | Click Complete. | Select RPC page is displayed.
Step 14 | Use the Select Existing Definition dropdown menu. Select VPS FULLSSN | The Edit Definition page is displayed.
Step 15 | Verify the changes that were made were saved successfully. | The Description field for Output Parameter Return Parameter now displays the following: Patient Information
Step 16 | Click Prev. | The Select RPC page is displayed.

## RPC_TC003
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC003_SMOKE TEST_RPC Wizard |  | Date_Executed: | Enter Date
Test_Description: | To know whether the essential functionality of the applications are working or not. |  | Test_Phase: | Increment 4
Requirements: | n/a |  | Release/Build Number: | v3.0.10
Prerequisites: | Two (2) users for each Vista will be needed. UserA - RPC Wizard UserB - API Browser Access Code and Verify Code required. Internet Explorer Browser is required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
| Note: if you are no longer logged into theVistA.js RPC REST Wizard , please access and log in again. |  | n/a
Step 1 | Click haley in the Server dropdown menu. Select westpalm | Login to westpalm access window is displayed.
Step 2 | Enter an Access Code <AC> for the VistA instance. Enter a Verify Code <VC> for the VistA instance. Click Connect. | User is logged in successfully. Select RPC page is displayed. westpalm is the selected server. User's name is located in the upper right hand corner of the application. Log out button is available.
Step 3 | Type the following into the RPC Search test field: VPS GET DFN Verify as you begin to populate the text field, all applicable RPCs populate in the search results area until VPS GET DFN is the only RPC listed. | Search results displays (1) result: VPS GET DFN.
Step 4 | Click VPS GET DFN link. Note: Notice only displays on initial RPC search. If notice displays, click Proceed. | Edit Definition page is displayed.
Step 5 | Verify VPS GET DFN Edit Definition displays the following Summary information: Name: VPS GET DFN Summary: GETDFN^VPSRPC5(.tRESULT,VPSSN) Description: Called by the Vetlink Kiosk system. Patient SSN is the input value. Returns patient DFN associated with SSN on record. | The Summary information displays the following: Name: VPS GET DFN Summary: GETDFN^VPSRPC5(.tRESULT,VPSSN) Description: Called by the Vetlink Kiosk system. Patient SSN is the input value. Returns patient DFN associated with SSN on record.
Step 6 | Verify VPS GET DFN Edit Definition displays the following Input Parameters information: VPSSN Name: VPSSN Description: blank (Please enter a value (Required) Parameter Type: LITERAL Swagger Type: String Required: Checkbox checked | The Input Parameters information displays the following: VPSSN Name: VPSSN Description: blank (Please enter a value (Required) Parameter Type: LITERAL Swagger Type: String Required: Checkbox checked
Step 7 | Verify VPS GET DFN Edit Definition displays the following Output Parameter information: Return Parameter Description: Patient DFN will be returned. Otherwise if no record found using the passed in SSN value then exception value is returned. Success:="1^"_DFN Exception:="99^"_exception text Return Type: SINGLE VALUE | The Output Parameter information displays the following: Return Parameter Description: Patient DFN will be returned. Otherwise if no record found using the passed in SSN value then exception value is returned. Success:="1^"_DFN Exception:="99^"_exception text Return Type: SINGLE VALUE
Step 8 | Add the following to the Description field for VPSSN Input Parameter: Patient SSN | The Description field for VPSSN Input Parameter now displays the following: Patient SSN
Step 9 | Click Next. | Review Swagger page is displayed.
Step 10 | Scroll through the Swagger information. Locate the recent modification that was completed on the Edit Definition page. | Swagger information has the following: "parameters": [ { "name": "VPSSN", "description": "Patient SSN [Fileman Type: LITERAL]", "in": "formData", "type": "string", "required": true }
Step 11 | Click Next. | The Save Definition page is displayed. Save Swagger button is available and enabled.
Step 12 | Click Save Swagger. | Message displays: Post successful! Click 'Complete' to reset the wizard.
Step 13 | Click Complete. | Select RPC page is displayed.
Step 14 | Use the Select Existing Definition dropdown menu. Select VPS GET DFN | The Edit Definition page is displayed.
Step 15 | Verify the changes that were made were saved successfully. | The Description field for VPSSN Input Parameter now displays the following: Patient SSN
Step 16 | Click Prev. | The Select RPC page is displayed.
Step 17 | If testing internally, Click Logout. Click OK. | User is successfully logged out.
Step 18 | If testing in the EDE, continue to RPC_TC004. | Testing Continues…

## RPC_TC004
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC004_SMOKE TEST_RPC Wizard |  | Date_Executed: | Enter Date
Test_Description: | To know whether the essential functionality of the applications are working or not. |  | Test_Phase: | Increment 4
Requirements: | n/a |  | Release/Build Number: | v3.0.10
Prerequisites: | Two (2) users for each Vista will be needed. UserA - RPC Wizard UserB - API Browser Access Code and Verify Code required. Internet Explorer Browser is required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
| Note: if you are no longer logged into theVistA.js RPC REST Wizard , please access and log in again. |  | n/a
Step 1 | Click westpalm in the Server dropdown menu. Select sanjuan. | Login to sanjuan access window is displayed.
Step 2 | Enter an Access Code <AC> for the VistA instance. Enter a Verify Code <VC> for the VistA instance. Click Connect. | User is logged in successfully. Select RPC page is displayed. sanjuan is the selected server. User's name is located in the upper right hand corner of the application. Log out button is available.
Step 3 | Type the following into the RPC Search test field: VPS GET SITES Verify as you begin to populate the text field, all applicable RPCs populate in the search results area until VPS GET SITES is the only RPC listed. | Search results displays (1) result: VPS GET SITES.
Step 4 | Click VPS GET SITES link. Note: Notice message displays on initial RPC search. If notice displays, click Proceed. | Edit Definition page is displayed.
Step 5 | Verify VPS GET SITES Edit Definition displays the following Summary information: Name: VPS GET SITES Summary: GETSITES^VPSRPC5(.tRESULT,VPSSN) Description: Called by the Vetlink Kiosk system. Patient SSN is the input value. Return value is a list of treating facilities associated with the patient given the SSN. | The Summary information displays the following: Name: VPS GET SITES Summary: GETSITES^VPSRPC5(.tRESULT,VPSSN) Description: Called by the Vetlink Kiosk system. Patient SSN is the input value. Return value is a list of treating facilities associated with the patient given the SSN.
Step 6 | Verify VPS GET SITES Edit Definition displays the following Input Parameters information: VPSSN Name: VPSSN Description: Patient SSN Parameter Type: LITERAL Swagger Type: String Required: Checkbox checked | The Input Parameters information displays the following: VPSSN Name: VPSSN Description: Patient SSN Parameter Type: LITERAL Swagger Type: String Required: Checkbox checked
Step 7 | Verify VPS GET SITES Edit Definition displays the following Output Parameter information: Return Parameter Description: Local ARRAY that returns the list of treating facilities by a given where 99 means an exception has occurred and text is a description of theexception.patient.output structure: LocalArray(n)="1^SITE ID" where 1 equals successful return of facility's site id at which the patient has been treated(e.g.,500 for Albany VAMC). LocalArray(n)="99^text" Return Type: ARRAY | The Output Parameter information displays the following: Return Parameter Description: Local ARRAY that returns the list of treating facilities by a given where 99 means an exception has occurred and text is a description of theexception.patient.output structure: LocalArray(n)="1^SITE ID" where 1 equals successful return of facility's site id at which the patient has been treated(e.g.,500 for Albany VAMC). LocalArray(n)="99^text" Return Type: ARRAY
Step 8 | Click Next. | Review Swagger page is displayed.
Step 9 | Click Next. | The Save Definition page is displayed. Save Swagger button is available and enabled.
Step 10 | Click Save Swagger. | Message displays: Post successful! Click 'Complete' to reset the wizard.
Step 11 | Click Complete. | Select RPC page is displayed.
Step 12 | Click Log out Click OK. | User is successfully logged out.

## API_TC001
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC001_SMOKE TEST_API Browser |  | Date_Executed: | Enter Date
Test_Description: | To know whether the essential functionality of the applications are working or not. |  | Test_Phase: | Increment 4
Requirements: | n/a |  | Release/Build Number: | v3.0.10
Prerequisites: | Two (2) users for each Vista will be needed. UserA - RPC Wizard UserB - API Browser Access Code and Verify Code required. Internet Explorer Browser is required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
Step 1 | Launch the API Definition Browser : https://.DNS:PORT/vsa-api-browser Note: If API Browser is already accessed, skip to Step 5. | Certificate Error Notification page is displayed. Note: Certificate Error Notification page may not display depending on the environment you are accessing.
Step 2 | If Certificate Error Notification is displayed: Select "Continue to this website (not recommended)." If Certificate Error Notification is not displayed: Verify the VSA Server page is displayed. | VSA Server page is displayed.
Step 3 | Scroll to the bottom and locate Application Name: API Definition Browser. Click Launch Application url. | Authorization agreement window is displayed.
Step 4 | Click Proceed. | VistA.js Federated REST Services API Browser vx.x.x is displayed.
Step 5 | Select Available Servers. | A dropdown menu is displayed listing the following: baypines haley sanjuan westpalm Note: Listing of servers may differ depending on environment.
Step 6 | Click baypines. | Login to baypines access window is displayed.
Step 7 | Enter an Access Code <AC> for the VistA instance. Enter a Verify Code <VC> for the VistA instance. Click Connect. | User is logged in successfully. VistA.js Federated REST Services API Browser vx.x.x is displayed. baypines is the selected server. User's name is located in the upper right hand corner of the application. Log out button is available.
Step 8 | Select the Available Services dropdown menu. | A dropdown menu is displayed listing the following: sync veterans session server patients rpcs
Step 9 | Click rpcs. | VistA.js RPC REST Service page is displayed. The following services are listed and available for selection: Restify RPCS Service
Step 10 | Click RPCS. | A list of available operations are listed.
Step 11 | Select GET /by-name/restified/all link. | Operation panel is expanded.
Step 12 | Click Try it out! Note: Security Alert dialog window may display depending on the environment you are accessing. If displayed, click Yes. | Additional Information is displayed: Curl: Request URL: Response Body: List of RPCs Response Code: 200 Response Headers: Should display date accessed
Step 13 | Click List Operations to close the expanded operation panel. | RPCS GET/DELETE/POST operations list is displayed.
Step 14 | Select POST /by-name/vps get allergies/call link. | Operation panel is expanded displaying: Implementation Notes Response Class (Status 200) Parameters Try it out! Button
Step 15 | Type 237 into the Parameters VPSDFN TEST Value text field. Click Try it out! | Additional data is displayed: Curl Request URL Response Body Response Code Response Headers
Step 16 | Verify the following is displayed in the response: Response Body: Identifies PATIENT 237 Response Code: 200 | The following is displayed: Response Body: Identifies PATIENT 237 Response Code: 200
Step 17 | Select sync service. | The following is displayed: Synchronization service The Vista.js Synchronization service [ base url: /sync , api version: 0.0.1 ]

## API_TC002
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC002_SMOKE TEST_API Browser |  | Date_Executed: | Enter Date
Test_Description: | To know whether the essential functionality of the applications are working or not. |  | Test_Phase: | Increment 4
Requirements: | n/a |  | Release/Build Number: | v3.0.10
Prerequisites: | Two (2) users for each Vista will be needed. UserA - RPC Wizard UserB - API Browser Access Code and Verify Code required. Internet Explorer Browser is required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
| Note: if you are no longer logged into theVistA.js RPC REST Wizard , please access and log in again. |  | n/a
Step 1 | Click baypines in the Server dropdown menu. Select haley. | Login to haley access window is displayed.
Step 2 | Enter an Access Code <AC> for the VistA instance. Enter a Verify Code <VC> for the VistA instance. Click Connect. | User is logged in successfully. Synchronization service page is displayed. haley is the selected server. Username is located in the upper right hand corner of the application. Log out button is available.
Step 3 | Click sync for the services dropdown menu. Select rpcs. | VistA.js RPC REST Service page is displayed. The following services are listed and available for selection: Restify RPCS Service
Step 4 | Click RPCS. | A list of available operations are listed.
Step 5 | Select POST /by-name/vps fullssn/call link. | Operation panel is expanded displaying: Implementation Notes Response Class (Status 200) Parameters Try it out! Button
Step 6 | Enter 666892222 into the Parameters VPSID Value text field. Click Try it out! | Additional data is displayed: Curl Request URL Response Body Response Code Response Headers
Step 7 | Verify the following is displayed in the response: Response Body: { "data": { "1": "253^UMANSKY,BART D^2380407^666892222" }, "statusCode": 200 } Response Code: 200 | The following is displayed: Response Body: { "data": { "1": "253^UMANSKY,BART D^2380407^666892222" }, "statusCode": 200 } Response Code: 200
Step 8 | Select sync service. | The following is displayed: Synchronization service The Vista.js Synchronization service [ base url: /sync , api version: 0.0.1 ]

## API_TC003
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC003_SMOKE TEST_API Browser |  | Date_Executed: | Enter Date
Test_Description: | To know whether the essential functionality of the applications are working or not. |  | Test_Phase: | Increment 4
Requirements: | n/a |  | Release/Build Number: | v3.0.10
Prerequisites: | Two (2) users for each Vista will be needed. UserA - RPC Wizard UserB - API Browser Access Code and Verify Code required. Internet Explorer Browser is required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
| Note: if you are no longer logged into theVistA.js RPC REST Wizard , please access and log in again. |  | n/a
Step 1 | Click haley in the Server dropdown menu. Select westpalm. | Login to westpalm access window is displayed.
Step 2 | Enter an Access Code <AC> for the VistA instance. Enter a Verify Code <VC> for the VistA instance. Click Connect. | User is logged in successfully. Synchronization service page is displayed. westpalm is the selected server. Username is located in the upper right hand corner of the application. Log out button is available.
Step 3 | Click sync for the services dropdown menu. Select rpcs. | VistA.js RPC REST Service page is displayed. The following services are listed and available for selection: Restify RPCS Service
Step 4 | Click RPCS. | A list of available operations are listed.
Step 5 | Select POST /by-name/vps get dfn/call link. | Operation panel is expanded displaying: Implementation Notes Response Class (Status 200) Parameters Try it out! Button
Step 6 | Enter 666118699 into the Parameters VPSSN Value text field. Click Try it out! | Additional data is displayed: Curl Request URL Response Body Response Code Response Headers
Step 7 | Verify the following is displayed in the response: Response Body: { "data": { "result": "1^80" }, "statusCode": 200 } Response Code: 200 | The following is displayed: Response Body: { "data": { "result": "1^80" }, "statusCode": 200 } Response Code: 200
Step 8 | Select sync services. | The following is displayed: Synchronization service The Vista.js Synchronization service [ base url: /sync , api version: 0.0.1 ]
Step 9 | If testing internally, Click Logout. Click OK. | User is successfully logged out.
Step 10 | If testing in the EDE, continue to API_TC004. | Testing Continues…

## API_TC4
Project_ Title: | VistA Services Assembler Phase 2.5 (VSA-P2.5) |  | Tester_Name: | Enter Test Engineer
Test Case Name_Number: | TC004_SMOKE TEST_API Browser |  | Date_Executed: | Enter Date
Test_Description: | To know whether the essential functionality of the applications are working or not. |  | Test_Phase: | Increment 4
Requirements: | n/a |  | Release/Build Number: | v3.0.10
Prerequisites: | Two (2) users for each Vista will be needed. UserA - RPC Wizard UserB - API Browser Access Code and Verify Code required. Internet Explorer Browser is required. |  | Environment Tested In: | VA EDE Environment
STEP_NUMBER | ACTION | EXPECTED_RESULTS | PASS/FAIL | REQUIREMENTS | COMMENTS
| Note: if you are no longer logged into the VistA.js API Browser , please access and log in again. |  | n/a
Step 1 | Click westpalm in the Server dropdown menu. Select sanjuan. | Login to sanjuan access window is displayed.
Step 2 | Enter an Access Code <AC> for the VistA instance. Enter a Verify Code <VC> for the VistA instance. Click Connect. | User is logged in successfully. Synchronization service page is displayed. sanjuan is the selected server. User's name is located in the upper right hand corner of the application. Log out button is available.
Step 3 | Click sync for the services dropdown menu. Select rpcs. | VistA.js RPC REST Service page is displayed. The following services are listed and available for selection: Restify RPCS Service
Step 4 | Click RPCS. | A list of available operations are listed.
Step 5 | Select POST /by-name/vps get sites/call link. | Operation panel is expanded displaying: Implementation Notes Response Class (Status 200) Parameters Try it out! Button
Step 6 | Enter 666118699 into the Parameters VPSSN Value text field. Click Try it out! | Additional data is displayed: Curl Request URL Response Body Response Code Response Headers
Step 7 | Verify the following is displayed in the response: Response Body: { "data": { "1": "516^BAY PINES VAMC^3010101^^VAMC", "2": "673^TAMPA (JAH VAH)^3020101^^VAMC", "3": "548^WEST PALM BEACH VAMC^3030101^^VAMC" }, "statusCode": 200 Response Code: 200 | The following is displayed: Response Body: { "data": { "1": "516^BAY PINES VAMC^3010101^^VAMC", "2": "673^TAMPA (JAH VAH)^3020101^^VAMC", "3": "548^WEST PALM BEACH VAMC^3030101^^VAMC" }, "statusCode": 200 Response Code: 200
Step 8 | Select sync services. | The following is displayed: Synchronization service The Vista.js Synchronization service [ base url: /sync , api version: 0.0.1 ]
Step 9 | Click Log out. Click OK. | User is successfully logged out.

## Approval Signatures
Approval Signatures
REVIEW DATE:
SCRIBE: Apex Data Solutions
Signed:
Mike Davis, Business Sponsor | Date
Russell Holt, Program Manager | Date
Lori Warren, Project Manager | Date